## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 2, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18227 | MID | KERMIT | 1 | FUEL VALVES | 2002-01-07 08:00 | 2002-01-21 16:00 | 14.3 |  | OPS |  | 0 | 0 | They need the fuel valves repaired. They will take them off and send them in for repairs. Also the will do anual maintenance on the unit while it is down. |  |  |  | 0 | P | N | N
2 | 17150 | MID | SEMINOLE | 1 | OVERHAUL | 2002-03-05 08:00 | 2002-04-01 16:00 | 27.3 |  | OPS |  | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 | P | N | N
3 | 16142 | MID | WT 2 | 201 | OVERHAUL | 2002-03-05 08:00 | 2002-04-05 16:00 | 31.3 |  | OPS |  | 0 | 0 | Overhaul |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 2, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18227 | MID | KERMIT | 1 | FUEL VALVES | 2002-01-07 08:00 | 2002-01-21 16:00 | 14.3 |  | OPS |  | 0 | 0 | They need the fuel valves repaired. They will take them off and send them in for repairs. Also the will do anual maintenance on the unit while it is down. |  |  |  | 0 | P | N | N
2 | 17150 | MID | SEMINOLE | 1 | OVERHAUL | 2002-03-05 08:00 | 2002-04-01 16:00 | 27.3 |  | OPS |  | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 | P | N | N
3 | 16142 | MID | WT 2 | 201 | OVERHAUL | 2002-03-05 08:00 | 2002-04-05 16:00 | 31.3 |  | OPS |  | 0 | 0 | Overhaul |  |  |  | 0 | P | N | N