## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Minneapolis Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 2, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17153 | MIN | CARLTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Cooper 12-V250 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 18235 | MIN | FARMINGTON | 4 | REXA FUEL VALVE | 2001-12-28 14:00 | 2001-12-31 16:00 | 3.1 |  | OPS |  | 0 | 0 | Working on Rexa fuel valve. |  | 2001-12-28 14:00 |  | 0 | U | N | N
3 | 17157 | MIN | FARMINGTON | 4 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT606 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
4 | 17158 | MIN | FARMINGTON | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-07-26 16:00 | 18.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT616 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
5 | 17156 | MIN | FARMINGTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS48 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 18190 | MIN | GARNER | LNG | BEARING FAILURE | 2001-12-04 08:00 | 2002-01-04 16:00 | 31.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is down. Having some bearing problems. Working with York Techs to find the problem. They want to make sure they have all the parts on hand when they take it apart. |  | 2001-12-04 08:00 |  | 0 | U | N | N
7 | 18240 | MIN | NORTH BRANCH | 3 | MP2 & MAINTENANCE | 2002-01-14 07:00 | 2002-01-31 15:30 | 17.3 |  | OPS |  | 0 | 0 | MP2 - Torque anchor bolts inspect all chains and gears inspect x-heads & shoe clearance inspect bearing clearance check comp. piston clearance start air valve maintenace crank shaft deflection comp. rod run out and analyze the unit(recip. trap). |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Minneapolis Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted January 2, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17153 | MIN | CARLTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Cooper 12-V250 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 18235 | MIN | FARMINGTON | 4 | REXA FUEL VALVE | 2001-12-28 14:00 | 2001-12-31 16:00 | 3.1 |  | OPS |  | 0 | 0 | Working on Rexa fuel valve. |  | 2001-12-28 14:00 |  | 0 | U | N | N
3 | 17157 | MIN | FARMINGTON | 4 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT606 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
4 | 17158 | MIN | FARMINGTON | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-07-26 16:00 | 18.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT616 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
5 | 17156 | MIN | FARMINGTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS48 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 18190 | MIN | GARNER | LNG | BEARING FAILURE | 2001-12-04 08:00 | 2002-01-04 16:00 | 31.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is down. Having some bearing problems. Working with York Techs to find the problem. They want to make sure they have all the parts on hand when they take it apart. |  | 2001-12-04 08:00 |  | 0 | U | N | N
7 | 18240 | MIN | NORTH BRANCH | 3 | MP2 & MAINTENANCE | 2002-01-14 07:00 | 2002-01-31 15:30 | 17.3 |  | OPS |  | 0 | 0 | MP2 - Torque anchor bolts inspect all chains and gears inspect x-heads & shoe clearance inspect bearing clearance check comp. piston clearance start air valve maintenace crank shaft deflection comp. rod run out and analyze the unit(recip. trap). |  |  |  | 0 | P | N | N