## 020103a
PLANNED AND UNPLANNED OUTAGES AFFECTING THE BUSHTON UNIVERSE.
2002-01-03
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 | 5 | 0.6 | 1500 hour inspection. |  |  | 0 | P
18250 | AMA | BEAVER 6 | 3 | 1500 HR. INSPECTION | 2002-01-15 10:00 | 2002-01-15 12:00 | 0.1 | 6 | 0.5 | 1500 hour inspection. |  |  | 0 | P
18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 | 3 | 0.9 | 1500 hour inspection. |  |  | 0 | P
18246 | AMA | ELLIS 1 | 2 | 1500 HR. INSPECTION | 2002-02-05 09:00 | 2002-02-05 12:00 | 0.1 | 7 | 0.9 | 1500 hour inspection. |  |  | 0 | P
18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 | 3 | 0.3 | 1500 hour inspection. |  |  | 0 | P
18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 | 7 | 0.9 | 1500 hour inspection. |  |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
18244 | BEA | BUSHTON | 28 | ANNUAL PM | 2002-01-10 08:00 | 2002-01-11 16:00 | 1.3 | 0 | 0 | Annual PM's. (Can do the PM If unit is down for no demand). |  |  | 0 | U
17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-09-02 08:00 | 2002-10-04 16:00 | 32.3 | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
18055 | LIB | FINNEY 1 | 4 | MAINTENANCE | 2002-01-14 08:00 | 2002-01-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance - work orders & DET list. |  |  | 0 | P
18001 | LIB | FINNEY 2 | 1 | MAINTENANCE | 2002-02-05 09:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18012 | LIB | FINNEY 2 | 1 | MAINTENANCE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18003 | LIB | FINNEY 2 | 2 | MAINTENANCE | 2002-02-07 09:00 | 2002-02-07 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18013 | LIB | FINNEY 2 | 2 | MAINTENANCE | 2002-03-07 08:00 | 2002-03-08 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18005 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18014 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18006 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-02-14 09:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18016 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-03-18 08:00 | 2002-03-18 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17995 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-01-17 09:00 | 2002-01-17 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18007 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-02-19 09:00 | 2002-02-19 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18017 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17997 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-01-22 09:00 | 2002-01-22 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18008 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-02-21 09:00 | 2002-02-21 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18018 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-03-21 08:00 | 2002-03-22 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17999 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-01-24 09:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18009 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-02-26 09:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18019 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-03-26 08:00 | 2002-03-27 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18000 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-01-29 09:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18010 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-02-28 09:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18020 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-03-28 08:00 | 2002-03-29 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17992 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-01-10 09:00 | 2002-01-10 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18004 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-02-08 09:00 | 2002-02-08 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18047 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-12-06 08:00 | 2002-12-06 16:00 | 0.3 | 0 | 0 | Scheduled maintenance - work orders & DET list. |  |  | 0 | P
17991 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-01-08 09:00 | 2002-01-08 16:00 | 0.3 | 3 | 0.9 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18002 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-02-05 09:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18015 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-03-14 09:00 | 2002-03-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17698 | LIB | FINNEY 4 | 1 | BEARING SENSOR | 2001-10-05 14:00 | 2002-06-30 16:30 | 268.1 | 0 | 0 | Lost main bearing sensor. Pulled doors off to check sensor and found metal in crankcase. Drained oil and located problem. Unit will have to be re-worked. | 2001-10-05 14:00 |  | 0 | U
17993 | LIB | FINNEY 4 | 1 | MAINTENANCE | 2002-01-10 09:00 | 2002-01-10 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18011 | LIB | FINNEY 4 | 1 | MAINTENANCE | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17994 | LIB | FINNEY 4 | 2 | MAINTENANCE | 2002-01-15 09:00 | 2002-01-15 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17996 | LIB | FINNEY 4 | 3 | MAINTENANCE | 2002-01-17 09:00 | 2002-01-17 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17998 | LIB | FINNEY 4 | 4 | MAINTENANCE | 2002-01-22 09:00 | 2002-01-22 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17837 | LIB | HOLCOMB | 1 | ANNUAL MAINTENANCE | 2002-01-17 08:00 | 2002-01-18 16:00 | 1.3 | 0 | 0 | Doing their annual maintenance. |  |  | 0 | P
17838 | LIB | HOLCOMB | 2 | ANNUAL MAINTENANCE | 2002-02-15 08:00 | 2002-02-16 16:00 | 1.3 | 0 | 0 | Annual maintenance. |  |  | 0 | P
17835 | LIB | HOLCOMB | 6 | MAJOR OVERHAUL | 2002-03-01 08:00 | 2002-04-01 16:00 | 31.3 | 0 | 0 | Major ovehaul on engine and compressors. |  |  | 0 | P
17836 | LIB | HOLCOMB | 10 | REPLACE PISTONS & RINGS | 2002-05-01 08:00 | 2002-05-31 16:00 | 30.3 | 0 | 0 | Replace pistons and rings overhaul 2 & 3 compressors. |  |  | 0 | P
17839 | LIB | HOLCOMB | ESD | ANNUAL ESD | 2002-05-14 08:00 | 2002-05-16 16:00 | 2.3 | 135 | 315 | Annual ESD and maintenance. |  |  | 0 | P
17840 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD | 2002-05-14 08:00 | 2002-05-16 16:00 | 2.3 | 0 | 0 | Outage coordinated with Holcomb's Annual ESD. |  |  | 0 | P
18057 | LIB | HUGOTON | 16 | MAINTENANCE | 2002-01-17 08:00 | 2002-01-17 14:00 | 0.3 | 15 | 3.8 | Service & maintenance. 1800 HP |  |  | 0 | P
18099 | LIB | HUGOTON | 16 | MAINTENANCE | 2002-05-01 08:00 | 2002-05-01 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 1800 HP |  |  | 0 | P
18101 | LIB | HUGOTON | 16 | SERVICE | 2002-08-13 08:00 | 2002-08-13 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 1800 HP |  |  | 0 | P
18103 | LIB | HUGOTON | 16 | SERVICE | 2002-11-26 08:00 | 2002-11-26 14:00 | 0.3 | 0 | 0 | Service and maintenance. 1800 HP |  |  | 0 | P
18058 | LIB | HUGOTON | 17 | MAINTENANCE | 2002-03-20 08:00 | 2002-03-20 14:00 | 0.3 | 15 | 3.8 | Service and maintenance. 1800 HP |  |  | 0 | P
18100 | LIB | HUGOTON | 17 | SERVICE | 2002-07-02 08:00 | 2002-07-02 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 1800 HP |  |  | 0 | P
18102 | LIB | HUGOTON | 17 | SERVICE | 2002-10-15 08:00 | 2002-10-15 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 1800 HP |  |  | 0 | P
18089 | LIB | HUGOTON | ALL | ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 100 | 233.3 | Planned ESD. |  |  | 0 | P
17634 | LIB | MORTON 1 | 3 | MP2 | 2002-07-08 07:30 | 2002-07-26 16:00 | 18.4 | 0 | 0 | MP2 8 000 hour inspection. |  |  | 0 | P
17644 | LIB | MORTON 1 | 3 | CONTROLS PM | 2002-12-02 07:30 | 2002-12-06 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17630 | LIB | MORTON 1 | 4 | MP2 | 2002-06-10 07:30 | 2002-06-21 16:00 | 11.4 | 0 | 0 | MP2 8 000 hr inspection |  |  | 0 | P
17645 | LIB | MORTON 1 | 4 | CONTROLS PM | 2002-12-09 07:30 | 2002-12-11 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17614 | LIB | MORTON 1 | 5 | CONTROLS PM | 2002-01-09 07:30 | 2002-01-11 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17615 | LIB | MORTON 1 | 6 | CONTROLS PM | 2002-01-16 07:30 | 2002-01-18 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17616 | LIB | MORTON 1 | 7 | CONTROLS PM | 2002-02-04 07:30 | 2002-02-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17639 | LIB | MORTON 1 | 8 | CONTROLS PM | 2002-09-05 07:30 | 2002-09-07 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17641 | LIB | MORTON 1 | 9 | CONTROLS PM | 2002-09-12 07:30 | 2002-09-14 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17617 | LIB | MORTON 1 | 10 | CONTROLS PM | 2002-02-11 07:30 | 2002-02-15 16:00 | 4.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17640 | LIB | MORTON 1 | 10 | MP2 | 2002-09-05 07:30 | 2002-09-23 16:00 | 18.4 | 0 | 0 | MP2 8 000 hour inspection |  |  | 0 | P
17637 | LIB | MORTON 1 | 11 | CONTROLS PM | 2002-08-12 07:30 | 2002-08-16 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17638 | LIB | MORTON 1 | 12 | CONTROLS PM | 2002-08-19 07:30 | 2002-08-23 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17622 | LIB | MORTON 1 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 18 | 96.8 | Annual ESD. |  |  | 0 | P
17626 | LIB | MORTON 6 | 1 | MP 2 | 2002-05-13 07:30 | 2002-05-24 16:00 | 11.4 | 4 | 45.5 | MP2 8 000 hour inspect. |  |  | 0 | P
17642 | LIB | MORTON 6 | 1 | CONTROLS PM | 2002-10-07 07:30 | 2002-10-09 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17612 | LIB | MORTON 6 | 2 | OIL FILTER CHANGE | 2002-01-15 07:30 | 2002-01-15 16:00 | 0.4 | 0 | 0 | Oil Filter change. |  |  | 0 | P
17628 | LIB | MORTON 6 | 2 | MP2 | 2002-05-28 07:30 | 2002-06-07 16:00 | 10.4 | 4 | 41.5 | MP2 8 000 hr inspection |  |  | 0 | P
17643 | LIB | MORTON 6 | 2 | CONTROLS PM | 2002-10-14 07:30 | 2002-10-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17623 | LIB | MORTON 6 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 18 | 96.8 | Annual ESD. |  |  | 0 | P
18069 | LIB | STEVENS 1 | 1 | MAINTENANCE | 2002-02-05 07:30 | 2002-02-06 16:00 | 1.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
17765 | LIB | STEVENS 1 | 1 | PMS | 2002-02-05 08:00 | 2002-02-06 16:00 | 1.3 | 0 | 0 | Pm scheduled work. |  |  | 0 | P
18071 | LIB | STEVENS 1 | 2 | MAINTENANCE | 2002-03-05 07:30 | 2002-03-06 16:00 | 1.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
17766 | LIB | STEVENS 1 | 2 | PMS | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 | 0 | 0 | PM scheduled work. |  |  | 0 | P
18070 | LIB | STEVENS 1 | 4 | MAINTENANCE | 2002-02-20 07:30 | 2002-02-20 16:00 | 0.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
18067 | LIB | STEVENS 1 | 5 | MAINTENANCE | 2002-01-09 07:30 | 2002-01-09 16:00 | 0.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
18072 | LIB | STEVENS 1 | 6 | MAINTENANCE | 2002-03-19 07:30 | 2002-03-20 16:00 | 1.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
17767 | LIB | STEVENS 1 | 6 | PMS | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | PM scheduled work. |  |  | 0 | P
18068 | LIB | STEVENS 1 | 7 | MAINTENANCE | 2002-01-23 07:30 | 2002-01-23 16:00 | 0.4 | 0 | 0 | Service unit and MP2 tasks. |  |  | 0 | P
18073 | LIB | STEVENS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 | 0 | 0 | Annual ESD. |  |  | 0 | P
17801 | LIB | STEVENS 2 | 3 | MP2 | 2002-01-17 08:00 | 2002-01-17 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17802 | LIB | STEVENS 2 | 3 | MP2 | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17771 | LIB | STEVENS 2 | 3 | SERVICE | 2002-03-14 08:00 | 2002-03-14 16:00 | 0.3 | 0 | 0 | Service Unit 1324 HP |  |  | 0 | P
17803 | LIB | STEVENS 2 | 3 | MP2 | 2002-04-02 08:00 | 2002-04-02 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17804 | LIB | STEVENS 2 | 3 | MP2 | 2002-05-07 08:00 | 2002-05-07 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17805 | LIB | STEVENS 2 | 3 | MP2 | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17806 | LIB | STEVENS 2 | 3 | MP2 | 2002-07-24 08:00 | 2002-07-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17807 | LIB | STEVENS 2 | 3 | MP2 | 2002-08-14 08:00 | 2002-08-14 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17772 | LIB | STEVENS 2 | 3 | SERVICE | 2002-09-03 08:00 | 2002-09-03 16:00 | 0.3 | 0 | 0 | Service unit 1324 HP |  |  | 0 | P
17808 | LIB | STEVENS 2 | 3 | MP2 | 2002-10-08 08:00 | 2002-10-08 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17809 | LIB | STEVENS 2 | 3 | MP2 | 2002-11-13 08:00 | 2002-11-13 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1324 HP |  |  | 0 | P
17773 | LIB | STEVENS 2 | 3 | SERVICE | 2002-12-04 08:00 | 2002-12-04 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1324 HP |  |  | 0 | P
18241 | LIB | STEVENS 2 | 6 | REPLACE POWER CYLINDER | 2002-01-02 08:00 | 2002-01-04 16:00 | 2.3 | 0 | 0 | Unit #6 has a power cylinder leaking water into the crankcase. Will have to replace the power cylinder. | 2002-01-02 08:00 |  | 0 | U
17810 | LIB | STEVENS 2 | 6 | MP2 | 2002-01-23 08:00 | 2002-01-23 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17811 | LIB | STEVENS 2 | 6 | MP2 | 2002-02-07 08:00 | 2002-02-07 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17774 | LIB | STEVENS 2 | 6 | SERVICE | 2002-03-06 08:00 | 2002-03-06 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM 1234 HP |  |  | 0 | P
17812 | LIB | STEVENS 2 | 6 | MP2 | 2002-04-03 08:00 | 2002-04-03 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17813 | LIB | STEVENS 2 | 6 | MP2 | 2002-05-08 08:00 | 2002-05-08 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17814 | LIB | STEVENS 2 | 6 | MP2 | 2002-06-06 08:00 | 2002-06-06 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17815 | LIB | STEVENS 2 | 6 | MP2 | 2002-07-25 08:00 | 2002-07-25 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17775 | LIB | STEVENS 2 | 6 | SERVICE | 2002-08-13 08:00 | 2002-08-13 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17816 | LIB | STEVENS 2 | 6 | MP2 | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17817 | LIB | STEVENS 2 | 6 | MP2 | 2002-10-09 08:00 | 2002-10-09 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17776 | LIB | STEVENS 2 | 6 | SERVICE | 2002-11-14 08:00 | 2002-11-14 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17818 | LIB | STEVENS 2 | 6 | MP2 | 2002-12-03 08:00 | 2002-12-03 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17819 | LIB | STEVENS 2 | 7 | MP2 | 2002-01-24 08:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17830 | LIB | STEVENS 2 | 7 | CHECK VALVES | 2002-01-28 08:00 | 2002-01-28 16:00 | 0.3 | 0 | 0 | Repairing check valve leaks. |  |  | 0 | P
17777 | LIB | STEVENS 2 | 7 | SERVICE | 2002-02-05 08:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17820 | LIB | STEVENS 2 | 7 | MP2 | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17778 | LIB | STEVENS 2 | 7 | SERVICE | 2002-04-09 08:00 | 2002-04-09 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17821 | LIB | STEVENS 2 | 7 | MP2 | 2002-05-09 08:00 | 2002-05-09 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17779 | LIB | STEVENS 2 | 7 | SERVICE | 2002-06-11 08:00 | 2002-06-11 16:00 | 0.3 | 0 | 0 | Service unit. 1234 HP |  |  | 0 | P
17780 | LIB | STEVENS 2 | 7 | SERVICE | 2002-07-23 08:00 | 2002-07-23 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1234 HP |  |  | 0 | P
17822 | LIB | STEVENS 2 | 7 | MP2 | 2002-08-15 08:00 | 2002-08-15 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17781 | LIB | STEVENS 2 | 7 | SERVICE | 2002-09-17 08:00 | 2002-09-17 16:00 | 0.3 | 0 | 0 | Service unit 586 HP |  |  | 0 | P
17823 | LIB | STEVENS 2 | 7 | MP2 | 2002-10-10 08:00 | 2002-10-10 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17782 | LIB | STEVENS 2 | 7 | SERVICE | 2002-11-12 08:00 | 2002-11-12 16:00 | 0.3 | 0 | 0 | Service unit. 586 HP |  |  | 0 | P
17825 | LIB | STEVENS 2 | 7 | MP2 | 2002-12-17 08:00 | 2002-12-17 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 586 HP |  |  | 0 | P
17783 | LIB | STEVENS 2 | 8 | SERVICE | 2002-01-08 08:00 | 2002-01-08 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17828 | LIB | STEVENS 2 | 8 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17784 | LIB | STEVENS 2 | 8 | SERVICE | 2002-03-05 08:00 | 2002-03-05 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17829 | LIB | STEVENS 2 | 8 | MP2 | 2002-04-04 08:00 | 2002-04-04 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17831 | LIB | STEVENS 2 | 8 | MP2 | 2002-05-21 08:00 | 2002-05-21 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17785 | LIB | STEVENS 2 | 8 | SERVICE | 2002-06-04 08:00 | 2002-06-04 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17786 | LIB | STEVENS 2 | 8 | SERVICE | 2002-07-02 08:00 | 2002-07-02 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17832 | LIB | STEVENS 2 | 8 | MP2 | 2002-08-20 08:00 | 2002-08-20 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17787 | LIB | STEVENS 2 | 8 | SERVICE | 2002-09-15 08:00 | 2002-09-15 16:00 | 0.3 | 0 | 0 | Service unit. 764 HP |  |  | 0 | P
17833 | LIB | STEVENS 2 | 8 | MP2 | 2002-10-22 08:00 | 2002-10-22 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17834 | LIB | STEVENS 2 | 8 | MP2 | 2002-11-19 08:00 | 2002-11-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 764 HP |  |  | 0 | P
17788 | LIB | STEVENS 2 | 8 | SERVICE | 2002-12-05 08:00 | 2002-12-05 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 764 HP |  |  | 0 | P
17789 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-01-09 08:00 | 2002-01-15 16:00 | 6.3 | 0 | 0 | Service Unit & MP2 Tasks. 375 hp |  |  | 0 | P
17790 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-02-11 08:00 | 2002-02-13 16:00 | 2.3 | 0 | 0 | Service Unit & MP2 Tasks. 375 HP |  |  | 0 | P
17791 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-03-07 08:00 | 2002-03-13 16:00 | 6.3 | 0 | 0 | Service units plus panel S/D & PM. 375 HP |  |  | 0 | P
17792 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-04-10 08:00 | 2002-04-16 16:00 | 6.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17793 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-05-13 08:00 | 2002-05-15 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17794 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-06-17 08:00 | 2002-06-19 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17795 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-07-09 08:00 | 2002-07-11 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17796 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-08-06 08:00 | 2002-08-08 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17797 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-09-09 08:00 | 2002-09-11 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17798 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-10-15 08:00 | 2002-10-17 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17799 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-11-05 08:00 | 2002-11-07 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17800 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2002-12-10 08:00 | 2002-12-12 16:00 | 2.3 | 0 | 0 | Service units. 375 HP |  |  | 0 | P
17842 | LIB | STEVENS 2 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 0 | 0 | Annual ESD |  |  | 0 | P
17852 | LIB | STEVENS 3 | 1 | MP2 | 2002-01-23 08:00 | 2002-01-23 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17843 | LIB | STEVENS 3 | 1 | SERVICE | 2002-02-05 08:00 | 2002-02-06 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1064 HP |  |  | 0 | P
17853 | LIB | STEVENS 3 | 1 | MP2 | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17854 | LIB | STEVENS 3 | 1 | MP2 | 2002-04-23 08:00 | 2002-04-23 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17855 | LIB | STEVENS 3 | 1 | MP2 | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17844 | LIB | STEVENS 3 | 1 | SERVICE | 2002-06-04 08:00 | 2002-06-05 16:00 | 1.3 | 0 | 0 | Service & MP2 Tasks. 1064 HP |  |  | 0 | P
17856 | LIB | STEVENS 3 | 1 | MP2 | 2002-07-30 08:00 | 2002-07-30 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17857 | LIB | STEVENS 3 | 1 | MP2 | 2002-08-20 08:00 | 2002-08-20 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17858 | LIB | STEVENS 3 | 1 | MP2 | 2002-09-24 08:00 | 2002-09-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17845 | LIB | STEVENS 3 | 1 | SERVICE | 2002-10-08 08:00 | 2002-10-09 16:00 | 1.3 | 0 | 0 | Service & MP2 Tasks. 1064 HP |  |  | 0 | P
17859 | LIB | STEVENS 3 | 1 | MP2 | 2002-11-20 08:00 | 2002-11-20 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17860 | LIB | STEVENS 3 | 1 | MP2 | 2002-12-17 08:00 | 2002-12-17 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1064 HP |  |  | 0 | P
17861 | LIB | STEVENS 3 | 3 | MP2 | 2002-01-29 08:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17862 | LIB | STEVENS 3 | 3 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17846 | LIB | STEVENS 3 | 3 | SERVICE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1100 HP |  |  | 0 | P
17863 | LIB | STEVENS 3 | 3 | MP2 | 2002-04-24 08:00 | 2002-04-24 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17864 | LIB | STEVENS 3 | 3 | MP2 | 2002-05-28 08:00 | 2002-05-28 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17865 | LIB | STEVENS 3 | 3 | MP2 | 2002-06-19 08:00 | 2002-06-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17847 | LIB | STEVENS 3 | 3 | SERVICE | 2002-07-23 08:00 | 2002-07-24 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1100 HP |  |  | 0 | P
17866 | LIB | STEVENS 3 | 3 | MP2 | 2002-08-27 08:00 | 2002-08-27 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17867 | LIB | STEVENS 3 | 3 | MP2 | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17868 | LIB | STEVENS 3 | 3 | MP2 | 2002-10-29 08:00 | 2002-10-29 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17848 | LIB | STEVENS 3 | 3 | SERVICE | 2002-11-12 08:00 | 2002-11-13 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1100 HP |  |  | 0 | P
17869 | LIB | STEVENS 3 | 3 | MP2 | 2002-12-04 08:00 | 2002-12-04 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1100 HP |  |  | 0 | P
17870 | LIB | STEVENS 3 | 4 | MP2 | 2002-01-22 08:00 | 2002-01-22 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17871 | LIB | STEVENS 3 | 4 | MP2 | 2002-02-19 08:00 | 2002-02-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17849 | LIB | STEVENS 3 | 4 | SERVICE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1600 HP |  |  | 0 | P
17872 | LIB | STEVENS 3 | 4 | MP2 | 2002-04-16 08:00 | 2002-04-16 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17873 | LIB | STEVENS 3 | 4 | MP2 | 2002-05-29 08:00 | 2002-05-29 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17874 | LIB | STEVENS 3 | 4 | MP2 | 2002-06-12 08:00 | 2002-06-12 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17850 | LIB | STEVENS 3 | 4 | SERVICE | 2002-07-16 08:00 | 2002-07-17 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1600 HP |  |  | 0 | P
17875 | LIB | STEVENS 3 | 4 | MP2 | 2002-08-28 08:00 | 2002-08-28 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17876 | LIB | STEVENS 3 | 4 | MP2 | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17851 | LIB | STEVENS 3 | 4 | SERVICE | 2002-10-15 08:00 | 2002-10-16 16:00 | 1.3 | 0 | 0 | Service unit MP2 Tasks. 1600 HP |  |  | 0 | P
17877 | LIB | STEVENS 3 | 4 | MP2 | 2002-11-19 08:00 | 2002-11-19 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17878 | LIB | STEVENS 3 | 4 | MP2 | 2002-12-11 08:00 | 2002-12-11 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1600 HP |  |  | 0 | P
17879 | LIB | STEVENS 4 | 1 | SERVICE | 2002-01-09 08:00 | 2002-01-10 16:00 | 1.3 | 7 | 9.3 | Service unit & MP 2. |  |  | 0 | P
17896 | LIB | STEVENS 4 | 1 | MP2 | 2002-02-13 08:00 | 2002-02-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17897 | LIB | STEVENS 4 | 1 | MP2 | 2002-03-20 08:00 | 2002-03-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17898 | LIB | STEVENS 4 | 1 | MP2 | 2002-04-17 08:00 | 2002-04-17 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17880 | LIB | STEVENS 4 | 1 | SERVICE | 2002-05-09 08:00 | 2002-05-10 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17899 | LIB | STEVENS 4 | 1 | MP2 | 2002-06-19 08:00 | 2002-06-19 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17900 | LIB | STEVENS 4 | 1 | MP2 | 2002-07-17 08:00 | 2002-07-17 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17901 | LIB | STEVENS 4 | 1 | MP2 | 2002-08-14 08:00 | 2002-08-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17881 | LIB | STEVENS 4 | 1 | SERVICE | 2002-09-11 08:00 | 2002-09-12 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17902 | LIB | STEVENS 4 | 1 | MP2 | 2002-10-16 08:00 | 2002-10-16 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17882 | LIB | STEVENS 4 | 1 | SERVICE | 2002-11-05 08:00 | 2002-11-06 16:00 | 1.3 | 0 | 0 | Panel S/D & PM MP 2. |  |  | 0 | P
17903 | LIB | STEVENS 4 | 1 | MP2 | 2002-12-11 08:00 | 2002-12-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17904 | LIB | STEVENS 4 | 2 | MP2 | 2002-01-15 08:00 | 2002-01-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17905 | LIB | STEVENS 4 | 2 | MP2 | 2002-02-21 08:00 | 2002-02-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17883 | LIB | STEVENS 4 | 2 | SERVICE | 2002-03-13 08:00 | 2002-03-14 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17906 | LIB | STEVENS 4 | 2 | MP2 | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17907 | LIB | STEVENS 4 | 2 | MP2 | 2002-05-23 08:00 | 2002-05-23 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17908 | LIB | STEVENS 4 | 2 | MP2 | 2002-06-20 08:00 | 2002-06-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17884 | LIB | STEVENS 4 | 2 | SERVICE | 2002-07-10 08:00 | 2002-07-11 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17909 | LIB | STEVENS 4 | 2 | MP2 | 2002-08-15 08:00 | 2002-08-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17910 | LIB | STEVENS 4 | 2 | MP2 | 2002-09-26 08:00 | 2002-09-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17911 | LIB | STEVENS 4 | 2 | MP2 | 2002-10-17 08:00 | 2002-10-17 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17885 | LIB | STEVENS 4 | 2 | SERVICE | 2002-11-13 08:00 | 2002-11-14 16:00 | 1.3 | 0 | 0 | Service unit panel S/D & MP 2. |  |  | 0 | P
17912 | LIB | STEVENS 4 | 2 | MP2 | 2002-12-12 08:00 | 2002-12-12 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17913 | LIB | STEVENS 4 | 3 | MP2 | 2002-01-15 08:00 | 2002-01-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17886 | LIB | STEVENS 4 | 3 | SERVICE | 2002-02-20 08:00 | 2002-02-20 16:00 | 0.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17914 | LIB | STEVENS 4 | 3 | MP2 | 2002-03-22 08:00 | 2002-03-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17915 | LIB | STEVENS 4 | 3 | MP2 | 2002-04-19 08:00 | 2002-04-19 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17916 | LIB | STEVENS 4 | 3 | MP2 | 2002-05-21 08:00 | 2002-05-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17887 | LIB | STEVENS 4 | 3 | SERVICE | 2002-06-12 08:00 | 2002-06-12 16:00 | 0.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17917 | LIB | STEVENS 4 | 3 | MP2 | 2002-07-19 08:00 | 2002-07-19 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17918 | LIB | STEVENS 4 | 3 | MP2 | 2002-08-16 08:00 | 2002-08-16 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17919 | LIB | STEVENS 4 | 3 | MP2 | 2002-09-27 08:00 | 2002-09-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17888 | LIB | STEVENS 4 | 3 | SERVICE | 2002-10-09 08:00 | 2002-10-09 16:00 | 0.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17889 | LIB | STEVENS 4 | 3 | SERVICE | 2002-11-06 08:00 | 2002-11-06 16:00 | 0.3 | 0 | 0 | Panel S/D & MP 2. |  |  | 0 | P
17920 | LIB | STEVENS 4 | 3 | MP2 | 2002-12-10 08:00 | 2002-12-10 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17890 | LIB | STEVENS 4 | 4 | SERVICE | 2002-01-16 08:00 | 2002-01-17 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17921 | LIB | STEVENS 4 | 4 | MP2 | 2002-02-18 08:00 | 2002-02-18 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17922 | LIB | STEVENS 4 | 4 | MP2 | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17923 | LIB | STEVENS 4 | 4 | MP2 | 2002-04-22 08:00 | 2002-04-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17891 | LIB | STEVENS 4 | 4 | SERVICE | 2002-05-15 08:00 | 2002-05-16 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17892 | LIB | STEVENS 4 | 4 | OVERHAUL | 2002-06-01 08:00 | 2002-07-01 16:00 | 30.3 | 0 | 0 | Comp. & engine overhaul. |  |  | 0 | P
17924 | LIB | STEVENS 4 | 4 | MP2 | 2002-06-25 08:00 | 2002-06-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17925 | LIB | STEVENS 4 | 4 | MP2 | 2002-07-16 08:00 | 2002-07-16 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17926 | LIB | STEVENS 4 | 4 | MP2 | 2002-08-13 08:00 | 2002-08-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17893 | LIB | STEVENS 4 | 4 | SERVICE | 2002-09-18 08:00 | 2002-09-19 16:00 | 1.3 | 0 | 0 | Service unit & MP 2. |  |  | 0 | P
17927 | LIB | STEVENS 4 | 4 | MP2 | 2002-10-15 08:00 | 2002-10-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17894 | LIB | STEVENS 4 | 4 | SERVICE | 2002-11-15 08:00 | 2002-11-15 16:00 | 0.3 | 0 | 0 | Panel S/D & MP 2. |  |  | 0 | P
17928 | LIB | STEVENS 4 | 4 | MP2 | 2002-12-09 08:00 | 2002-12-09 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. |  |  | 0 | P
17895 | LIB | STEVENS 4 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 0 | 0 | Annual ESD. |  |  | 0 | P
17762 | LIB | STEVENS 6 | 1 | PMS | 2002-01-08 08:00 | 2002-01-09 16:00 | 1.3 | 0 | 0 | PM Scheduled work. |  |  | 0 | P
17763 | LIB | STEVENS 6 | 3 | PMS | 2002-01-22 08:00 | 2002-01-23 16:00 | 1.3 | 0 | 0 | PM scheduled work. |  |  | 0 | P
17764 | LIB | STEVENS 6 | 4 | PMS | 2002-01-29 08:00 | 2002-01-30 16:00 | 1.3 | 0 | 0 | PM scheduled work. |  |  | 0 | P
18062 | LIB | STEVENS 7 | 1 | MP2 | 2002-03-05 09:00 | 2002-03-07 16:00 | 2.3 | 4 | 9.2 | MP2 Tasks. |  |  | 0 | P
18061 | LIB | STEVENS 7 | 2 | MP2 | 2002-02-05 09:00 | 2002-02-07 16:00 | 2.3 | 0 | 0 | MP2 Tasks. |  |  | 0 | P
18060 | LIB | STEVENS 7 | 4 | MP2 | 2002-01-15 09:00 | 2002-01-17 16:00 | 2.3 | 0 | 0 | MP2 Tasks. |  |  | 0 | P
17983 | LIB | SUBLETTE | 13 | MP2 | 2002-01-09 08:00 | 2002-01-09 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17984 | LIB | SUBLETTE | 13 | MP2 | 2002-01-29 08:00 | 2002-01-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17985 | LIB | SUBLETTE | 13 | MP2 | 2002-02-13 08:00 | 2002-02-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17986 | LIB | SUBLETTE | 13 | MP2 | 2002-02-27 08:00 | 2002-02-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17987 | LIB | SUBLETTE | 13 | MP2 | 2002-03-13 08:00 | 2002-03-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17988 | LIB | SUBLETTE | 13 | MP2 | 2002-03-27 08:00 | 2002-03-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17935 | LIB | SUBLETTE | 14 | MP2 | 2002-01-02 08:00 | 2002-01-02 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17936 | LIB | SUBLETTE | 14 | MP2 | 2002-01-23 08:00 | 2002-01-23 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17937 | LIB | SUBLETTE | 14 | MP2 | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17938 | LIB | SUBLETTE | 14 | MP2 | 2002-02-20 08:00 | 2002-02-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17939 | LIB | SUBLETTE | 14 | MP2 | 2002-03-07 08:00 | 2002-03-07 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17940 | LIB | SUBLETTE | 14 | MP2 | 2002-03-20 08:00 | 2002-03-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17941 | LIB | SUBLETTE | 19 | MP2 | 2002-01-11 08:00 | 2002-01-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17942 | LIB | SUBLETTE | 19 | MP2 | 2002-01-31 08:00 | 2002-01-31 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17943 | LIB | SUBLETTE | 19 | MP2 | 2002-02-11 08:00 | 2002-02-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17944 | LIB | SUBLETTE | 19 | MP2 | 2002-02-25 08:00 | 2002-02-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17945 | LIB | SUBLETTE | 19 | MP2 | 2002-03-04 08:00 | 2002-03-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17946 | LIB | SUBLETTE | 19 | MP2 | 2002-03-25 08:00 | 2002-03-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17947 | LIB | SUBLETTE | 20 | MP2 | 2002-01-07 08:00 | 2002-01-07 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17948 | LIB | SUBLETTE | 20 | MP2 | 2002-01-25 08:00 | 2002-01-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17949 | LIB | SUBLETTE | 20 | MP2 | 2002-02-05 08:00 | 2002-02-05 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17950 | LIB | SUBLETTE | 20 | MP2 | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17951 | LIB | SUBLETTE | 20 | MP2 | 2002-03-15 08:00 | 2002-03-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17952 | LIB | SUBLETTE | 20 | MP2 | 2002-03-29 08:00 | 2002-03-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17953 | LIB | SUBLETTE | 21 | MP2 | 2002-01-10 08:00 | 2002-01-10 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17954 | LIB | SUBLETTE | 21 | MP2 | 2002-01-28 08:00 | 2002-01-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17955 | LIB | SUBLETTE | 21 | MP2 | 2002-02-04 08:00 | 2002-02-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17956 | LIB | SUBLETTE | 21 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17957 | LIB | SUBLETTE | 21 | MP2 | 2002-03-11 08:00 | 2002-03-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17958 | LIB | SUBLETTE | 21 | MP2 | 2002-03-28 08:00 | 2002-03-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17959 | LIB | SUBLETTE | 22 | MP2 | 2002-01-04 08:00 | 2002-01-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17960 | LIB | SUBLETTE | 22 | MP2 | 2002-01-24 08:00 | 2002-01-24 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17961 | LIB | SUBLETTE | 22 | MP2 | 2002-02-01 08:00 | 2002-02-01 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17962 | LIB | SUBLETTE | 22 | MP2 | 2002-02-15 08:00 | 2002-02-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17963 | LIB | SUBLETTE | 22 | MP2 | 2002-03-01 08:00 | 2002-03-01 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17964 | LIB | SUBLETTE | 22 | MP2 | 2002-03-22 08:00 | 2002-03-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17965 | LIB | SUBLETTE | 23 | MP2 | 2002-01-08 08:00 | 2002-01-08 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17966 | LIB | SUBLETTE | 23 | MP2 | 2002-01-21 08:00 | 2002-01-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17967 | LIB | SUBLETTE | 23 | MP2 | 2002-02-07 08:00 | 2002-02-07 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17968 | LIB | SUBLETTE | 23 | MP2 | 2002-02-22 08:00 | 2002-02-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17969 | LIB | SUBLETTE | 23 | MP2 | 2002-03-05 08:00 | 2002-03-05 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17970 | LIB | SUBLETTE | 23 | MP2 | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17971 | LIB | SUBLETTE | 24 | MP2 | 2002-01-14 08:00 | 2002-01-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17972 | LIB | SUBLETTE | 24 | MP2 | 2002-01-30 08:00 | 2002-01-30 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17973 | LIB | SUBLETTE | 24 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17974 | LIB | SUBLETTE | 24 | MP2 | 2002-02-25 08:00 | 2002-02-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17975 | LIB | SUBLETTE | 24 | MP2 | 2002-03-08 08:00 | 2002-03-08 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17976 | LIB | SUBLETTE | 24 | MP2 | 2002-03-21 08:00 | 2002-03-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17544 | LIB | SUBLETTE | 26 | POWER TURBINE | 2001-09-20 12:00 | 2002-01-31 16:00 | 133.2 | 0 | 0 | Overhaul on the unit. They need to replace the power turbine. Will put on other units to cover loss in volumes. Some of the gas will be sent towards Holcomb. | 2001-09-20 12:00 |  | 0 | U
17977 | LIB | SUBLETTE | 26 | MP2 | 2002-01-07 08:00 | 2002-01-07 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17978 | LIB | SUBLETTE | 26 | MP2 | 2002-01-30 08:00 | 2002-01-30 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17979 | LIB | SUBLETTE | 26 | MP2 | 2002-02-11 08:00 | 2002-02-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17980 | LIB | SUBLETTE | 26 | MP2 | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17981 | LIB | SUBLETTE | 26 | MP2 | 2002-03-04 08:00 | 2002-03-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17982 | LIB | SUBLETTE | 26 | MP2 | 2002-03-25 08:00 | 2002-03-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17929 | LIB | SUBLETTE | 27 | MP2 | 2002-01-15 08:00 | 2002-01-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17930 | LIB | SUBLETTE | 27 | MP2 | 2002-01-28 08:00 | 2002-01-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17931 | LIB | SUBLETTE | 27 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17932 | LIB | SUBLETTE | 27 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17933 | LIB | SUBLETTE | 27 | MP2 | 2002-03-15 08:00 | 2002-03-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17934 | LIB | SUBLETTE | 27 | MP2 | 2002-03-29 08:00 | 2002-03-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
16441 | LIB | TATE | 1 | OVERHAUL | 2002-10-01 08:00 | 2002-12-01 16:00 | 61.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
16442 | LIB | TATE | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-10-01 16:00 | 61.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
17754 | LIB | TATE | 10 | INSPECTION | 2002-12-02 08:00 | 2002-12-13 16:00 | 11.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17755 | LIB | TATE | 11 | INSPECTION | 2002-12-16 08:00 | 2002-12-20 16:00 | 4.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17757 | LIB | TATE | ALL | ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 | 14 | 4.7 | Annual ESD test. |  |  | 0 | P
17668 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-10 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17669 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-08-27 08:00 | 2002-08-27 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17670 | LIB | TEXAS 1 | 2 | INSPEC TION | 2002-10-21 08:00 | 2002-10-25 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17671 | LIB | TEXAS 1 | 3 | INSPECTION | 2002-02-18 08:00 | 2002-02-22 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17627 | LIB | TEXAS 1 | 3 | CONTROLS PM | 2002-05-14 07:30 | 2002-05-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17672 | LIB | TEXAS 1 | 3 | ENGINE SERVICE | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 | 0 | 0 | Engine service |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17624 | LIB | TEXAS 1 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 10 | 53.8 | Annual ESD. |  |  | 0 | P
17629 | LIB | TEXAS 2 | 1 | CONTROLS PM | 2002-06-10 07:30 | 2002-06-12 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17631 | LIB | TEXAS 2 | 2 | CONTROLS PM | 2002-06-18 07:30 | 2002-06-20 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17633 | LIB | TEXAS 2 | 3 | CONTROLS PM | 2002-07-08 07:30 | 2002-07-10 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17635 | LIB | TEXAS 2 | 4 | CONTROLS PM | 2002-07-15 07:30 | 2002-07-17 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17636 | LIB | TEXAS 2 | 5 | CONTROLS PM | 2002-08-05 07:30 | 2002-08-07 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17677 | LIB | TEXAS 2 | 6 | INSPECTION | 2002-07-22 08:00 | 2002-07-26 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17678 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17673 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-13 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17674 | LIB | TEXAS 2 | 7 | INSPECTION | 2002-06-24 08:00 | 2002-06-28 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17675 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-07-30 08:00 | 2002-07-30 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17625 | LIB | TEXAS 2 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 15 | 80.6 | Annual ESD. |  |  | 0 | P