## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 6, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 18:00 | 1.4 |  | OPS |  | 100 | 141.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
2 | 17150 | MID | SEMINOLE | 1 | OVERHAUL | 2002-09-02 08:00 | 2002-09-30 16:00 | 28.3 |  | OPS |  | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 | P | N | N
3 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
4 | 18383 | MID | WT-2 | 201 | OVERHAUL | 2002-09-15 08:00 | 2002-10-20 16:00 | 35.3 |  | OPS |  | 0 | 0 | Compressor OH. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 6, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 18:00 | 1.4 |  | OPS |  | 100 | 141.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
2 | 17150 | MID | SEMINOLE | 1 | OVERHAUL | 2002-09-02 08:00 | 2002-09-30 16:00 | 28.3 |  | OPS |  | 0 | 0 | Complete disassembly and overhaul of gas producer and power turbine. |  |  |  | 0 | P | N | N
3 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
4 | 18383 | MID | WT-2 | 201 | OVERHAUL | 2002-09-15 08:00 | 2002-10-20 16:00 | 35.3 |  | OPS |  | 0 | 0 | Compressor OH. |  |  |  | 0 | P | N | N