## 020702Bu
PLANNED AND UNPLANNED OUTAGE AFFECTING THE BUSHTON UNIVERSE.
2002-02-07
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
18362 | AMA | BEAVER 12 | 3 | UNIT OVERHAUL | 2002-03-04 07:30 | 2002-03-30 16:00 | 26.4 | 0 | 0 | Overhaul Engine & Compressors. |  |  | 0 | P
18376 | AMA | BEAVER 2 | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 | 0 | 0 | Major engine (Mike White OH). |  |  | 0 | P
18380 | AMA | BEAVER 6 | 1 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 | 0 | 0 | Major Engine & compressor. |  |  | 0 | P
18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 | 5 | 0.6 | 1500 hour inspection. |  |  | 0 | P
18374 | AMA | BEAVER 7 | 1 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 | 0 | 0 | Major overhaul. |  |  | 0 | P
18384 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-10-15 08:00 | 2002-10-30 16:00 | 15.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18386 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-30 16:00 | 29.3 | 0 | 0 | Major Compressor. |  |  | 0 | P
18365 | AMA | BEAVER PLANT | 9 | OVERHAUL | 2002-03-01 08:00 | 2002-03-30 16:00 | 29.3 | 0 | 0 | Major engine & compressors. |  |  | 0 | P
18367 | AMA | BEAVER PLANT | 12 | OVERHAUL | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 | 0 | 0 | Major enigne & compressors. |  |  | 0 | P
18369 | AMA | BEAVER PLANT | 14 | OVERHAUL | 2002-05-01 08:00 | 2002-06-01 16:00 | 31.3 | 0 | 0 | Major engine and compressors. |  |  | 0 | P
18412 | AMA | BEAVER PLANT | 18 | WATER PUMP | 2002-02-06 15:00 | 2002-02-15 16:00 | 9 | 0 | 0 | Water pump gears. | 2002-02-06 15:00 |  | 0 | U
18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 | 3 | 0.9 | 1500 hour inspection. |  |  | 0 | P
18385 | AMA | ELLIS 1 | 1 | OVERHAUL | 2002-10-15 08:00 | 2002-11-15 16:00 | 31.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 | 3 | 0.3 | 1500 hour inspection. |  |  | 0 | P
18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 | 7 | 0.9 | 1500 hour inspection. |  |  | 0 | P
18377 | AMA | ELLIS 2 | 2 | OVERHAUL | 2002-07-15 08:00 | 2002-07-30 16:00 | 15.3 | 0 | 0 | Major compressor. |  |  | 0 | P
18378 | AMA | WOODWARD 1 | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-08-30 16:00 | 29.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18381 | AMA | WOODWARD 2 | 4 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18382 | AMA | WOODWARD 3 | 4 | OVERHAUL | 2002-09-15 08:00 | 2002-09-30 16:00 | 15.3 | 0 | 0 | Major Compressor. |  |  | 0 | P
18299 | BEA | BUSHTON | 24 | WRIST PEN | 2002-02-04 07:00 | 2002-02-08 15:30 | 4.3 | 0 | 0 | Replace piston Wrist pen remove power rod piston and head. | 2002-02-04 07:00 |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-09-02 07:00 | 2002-10-04 15:30 | 32.3 | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Flow affect will depends the needs on the pipeline). Unit pumps about 75 mmcfd. |  |  | 0 | P
18346 | LIB | BEAVER 1 | 1 | ROD BEARINGS | 2002-01-24 08:00 | 2002-02-08 16:00 | 15.3 | 1 | 15.3 | Need to change comppressor rod bearings. Waiting for parts to come in. | 2002-01-24 08:00 |  | 0 | U
18402 | LIB | BURDETT | 2 | BORESCOPE & MAINTENANCE | 2002-05-20 07:30 | 2002-05-31 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18403 | LIB | BURDETT | 3 | BORESCOPE & MAINTENANCE | 2002-06-10 07:30 | 2002-06-21 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18404 | LIB | BURDETT | 4 | BORESCOPE & MAINTENANCE | 2002-07-01 07:30 | 2002-07-12 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18405 | LIB | BURDETT | 5 | BORESCOPE & MAINTENANCE | 2002-07-22 07:30 | 2002-08-02 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18406 | LIB | BURDETT | 6 | BORESCOPE & MAINTENANCE | 2002-08-12 07:30 | 2002-08-30 16:00 | 18.4 | 0 | 0 | Possible overhaul- ECS other wise Borescope & minor maintenance. |  |  | 0 | P
18408 | LIB | BURDETT | ALL | ANNUAL ESD | 2002-05-14 07:00 | 2002-05-16 16:00 | 2.4 | 0 | 0 | Annual ESD will shut down during the same time as Holcomb's ESD. |  |  | 0 | P
18407 | LIB | BURDETT | ALL | RELIEF VALVE TESTING | 2002-06-17 07:30 | 2002-06-21 16:00 | 4.4 | 0 | 0 | Will take one unit down at a time to do the testing. |  |  | 0 | P
18409 | LIB | BURDETT | ALL | JACKET WATER PROJECT | 2002-07-01 08:00 | 2002-07-01 16:00 | 0.3 | 0 | 0 | There is no firm date for this outage yet if at all. |  |  | 0 | P
18012 | LIB | FINNEY 2 | 1 | MAINTENANCE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18368 | LIB | FINNEY 2 | 1 | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 | 0 | 0 | Inframe engine & compressor OH. |  |  | 0 | P
18013 | LIB | FINNEY 2 | 2 | MAINTENANCE | 2002-03-07 08:00 | 2002-03-08 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18005 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18014 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18006 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-02-14 09:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18016 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-03-18 08:00 | 2002-03-18 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18007 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-02-19 09:00 | 2002-02-19 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18017 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18008 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-02-21 09:00 | 2002-02-21 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18018 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-03-21 08:00 | 2002-03-22 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18009 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-02-26 09:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18019 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-03-26 08:00 | 2002-03-27 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18010 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-02-28 09:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18020 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-03-28 08:00 | 2002-03-29 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18364 | LIB | FINNEY 3 | 1 | ENGINE EXCHANGE | 2002-04-01 08:00 | 2002-04-15 16:00 | 14.3 | 0 | 0 | Engine exchange. |  |  | 0 | P
18047 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-12-06 08:00 | 2002-12-06 16:00 | 0.3 | 0 | 0 | Scheduled maintenance - work orders & DET list. |  |  | 0 | P
18015 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-03-14 09:00 | 2002-03-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17698 | LIB | FINNEY 4 | 1 | BEARING SENSOR | 2001-10-05 14:00 | 2002-06-30 16:30 | 268.1 | 0 | 0 | Lost main bearing sensor. Pulled doors off to check sensor and found metal in crankcase. Drained oil and located problem. Unit will have to be re-worked. | 2001-10-05 14:00 |  | 0 | U
18011 | LIB | FINNEY 4 | 1 | MAINTENANCE | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18400 | LIB | FINNEY 4 | 3 | OVERHAUL | 2002-03-11 08:00 | 2002-04-05 16:30 | 25.3 | 3 | 76 | The unit will pulled out and overhauled. (Unit #2 will be down also due to no demand form unit #3). |  |  | 0 | P
18363 | LIB | FINNEY 4 | 4 | OVERHAUL | 2002-04-15 08:00 | 2002-05-10 16:30 | 25.3 | 3 | 76 | Unit will be pulled out and overhauled. (Unit Exchange if possible). |  |  | 0 | P
17838 | LIB | HOLCOMB | 2 | ANNUAL MAINTENANCE | 2002-02-13 08:00 | 2002-02-14 16:00 | 1.3 | 6 | 8 | Annual maintenance. (This unit pumps Holcomb South). |  |  | 0 | P
18366 | LIB | HOLCOMB | 6 | OVERHAUL | 2002-03-01 08:00 | 2002-04-01 16:00 | 31.3 | 0 | 0 | Inframe engine. |  |  | 0 | P
17836 | LIB | HOLCOMB | 10 | REPLACE PISTONS & RINGS | 2002-05-01 08:00 | 2002-05-31 16:00 | 30.3 | 0 | 0 | Replace pistons and rings overhaul 2 & 3 compressors. |  |  | 0 | P
17839 | LIB | HOLCOMB | ESD | ANNUAL ESD | 2002-05-14 08:00 | 2002-05-16 16:00 | 2.3 | 135 | 315 | Annual ESD and maintenance. |  |  | 0 | P
17840 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD | 2002-05-14 08:00 | 2002-05-16 16:00 | 2.3 | 0 | 0 | Outage coordinated with Holcomb's Annual ESD. |  |  | 0 | P
18353 | LIB | HUGOTON | 10 | MP2 & MAINTENANCE | 2002-01-07 08:00 | 2002-02-15 14:00 | 39.3 | 0 | 0 | MP2 & and other maintenance. They have a spare unit so there is no flow affect. | 2002-01-07 08:00 |  | 0 | P
18314 | LIB | HUGOTON | 16 | SERVICE & MAINTENANCE | 2002-10-08 08:00 | 2002-10-08 16:00 | 0.3 | 12 | 4 | Service and maintenance. |  |  | 0 | P
18102 | LIB | HUGOTON | 17 | SERVICE | 2002-10-15 08:00 | 2002-10-15 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 1800 HP |  |  | 0 | P
18089 | LIB | HUGOTON | ALL | ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 100 | 233.3 | Planned ESD. |  |  | 0 | P
17634 | LIB | MORTON 1 | 3 | MP2 | 2002-07-08 07:30 | 2002-07-26 16:00 | 18.4 | 0 | 0 | MP2 8 000 hour inspection. |  |  | 0 | P
17644 | LIB | MORTON 1 | 3 | CONTROLS PM | 2002-12-02 07:30 | 2002-12-06 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17622 | LIB | MORTON 1 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 18 | 96.8 | Annual ESD. |  |  | 0 | P
17626 | LIB | MORTON 6 | 1 | MP 2 | 2002-05-13 07:30 | 2002-05-24 16:00 | 11.4 | 4 | 45.5 | MP2 8 000 hour inspect. |  |  | 0 | P
17628 | LIB | MORTON 6 | 2 | MP2 | 2002-05-28 07:30 | 2002-06-07 16:00 | 10.4 | 4 | 41.5 | MP2 8 000 hr inspection |  |  | 0 | P
17643 | LIB | MORTON 6 | 2 | CONTROLS PM | 2002-10-14 07:30 | 2002-10-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17623 | LIB | MORTON 6 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 18 | 96.8 | Annual ESD. |  |  | 0 | P
18312 | LIB | MULLINVILLE | 19 | REPLACE ROD BEARING | 2002-01-16 14:00 | 2002-02-08 16:00 | 23.1 | 0 | 0 | Will remove bearing and inspect crank shaft. | 2002-01-16 14:00 |  | 0 | U
18373 | LIB | MULLINVILLE | 20 | TURBOCHARGER | 2002-05-15 08:00 | 2002-05-28 16:00 | 13.3 | 0 | 0 | Rebuild Turbocharger. |  |  | 0 | P
18343 | LIB | MULLINVILLE | 23 | WARRENTY WORK | 2002-01-29 08:00 | 2002-02-06 16:00 | 5.3 | 0 | 0 | Exline is doing some warrenty work on the ignition system. | 2002-01-29 08:00 |  | 0 | U
18370 | LIB | MULLINVILLE | 8 AUX. | OVERHAUL | 2002-05-01 08:00 | 2002-05-03 16:00 | 2.3 | 0 | 0 | TEO |  |  | 0 | P
18375 | LIB | STEVENS 1 | 4 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 | 0 | 0 | Major compressor and all five cylinders. |  |  | 0 | P
18073 | LIB | STEVENS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 | 0 | 0 | Annual ESD. |  |  | 0 | P
17773 | LIB | STEVENS 2 | 3 | SERVICE | 2002-12-04 08:00 | 2002-12-04 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1324 HP |  |  | 0 | P
17774 | LIB | STEVENS 2 | 6 | SERVICE | 2002-03-06 08:00 | 2002-03-06 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM 1234 HP |  |  | 0 | P
17817 | LIB | STEVENS 2 | 6 | MP2 | 2002-10-09 08:00 | 2002-10-09 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17780 | LIB | STEVENS 2 | 7 | SERVICE | 2002-07-23 08:00 | 2002-07-23 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1234 HP |  |  | 0 | P
18379 | LIB | STEVENS 2 | 8 | OVERHAUL | 2002-08-10 08:00 | 2002-08-30 16:00 | 20.3 | 0 | 0 | Compressor overhaul. |  |  | 0 | P
17788 | LIB | STEVENS 2 | 8 | SERVICE | 2002-12-05 08:00 | 2002-12-05 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 764 HP |  |  | 0 | P
17842 | LIB | STEVENS 2 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 0 | 0 | Annual ESD |  |  | 0 | P
17846 | LIB | STEVENS 3 | 3 | SERVICE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1100 HP |  |  | 0 | P
17882 | LIB | STEVENS 4 | 1 | SERVICE | 2002-11-05 08:00 | 2002-11-06 16:00 | 1.3 | 0 | 0 | Panel S/D & PM MP 2. |  |  | 0 | P
17885 | LIB | STEVENS 4 | 2 | SERVICE | 2002-11-13 08:00 | 2002-11-14 16:00 | 1.3 | 0 | 0 | Service unit panel S/D & MP 2. |  |  | 0 | P
17889 | LIB | STEVENS 4 | 3 | SERVICE | 2002-11-06 08:00 | 2002-11-06 16:00 | 0.3 | 0 | 0 | Panel S/D & MP 2. |  |  | 0 | P
17892 | LIB | STEVENS 4 | 4 | OVERHAUL | 2002-06-01 08:00 | 2002-07-01 16:00 | 30.3 | 0 | 0 | Comp. & engine overhaul. |  |  | 0 | P
17895 | LIB | STEVENS 4 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 0 | 0 | Annual ESD. |  |  | 0 | P
18062 | LIB | STEVENS 7 | 1 | MP2 | 2002-03-05 09:00 | 2002-03-07 16:00 | 2.3 | 4 | 9.2 | MP2 Tasks. |  |  | 0 | P
17985 | LIB | SUBLETTE | 13 | MP2 | 2002-02-13 08:00 | 2002-02-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17986 | LIB | SUBLETTE | 13 | MP2 | 2002-02-27 08:00 | 2002-02-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17987 | LIB | SUBLETTE | 13 | MP2 | 2002-03-13 08:00 | 2002-03-13 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17988 | LIB | SUBLETTE | 13 | MP2 | 2002-03-27 08:00 | 2002-03-27 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17938 | LIB | SUBLETTE | 14 | MP2 | 2002-02-20 08:00 | 2002-02-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17939 | LIB | SUBLETTE | 14 | MP2 | 2002-03-07 08:00 | 2002-03-07 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17940 | LIB | SUBLETTE | 14 | MP2 | 2002-03-20 08:00 | 2002-03-20 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17943 | LIB | SUBLETTE | 19 | MP2 | 2002-02-11 08:00 | 2002-02-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17944 | LIB | SUBLETTE | 19 | MP2 | 2002-02-25 08:00 | 2002-02-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17945 | LIB | SUBLETTE | 19 | MP2 | 2002-03-04 08:00 | 2002-03-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17946 | LIB | SUBLETTE | 19 | MP2 | 2002-03-25 08:00 | 2002-03-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17950 | LIB | SUBLETTE | 20 | MP2 | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17951 | LIB | SUBLETTE | 20 | MP2 | 2002-03-15 08:00 | 2002-03-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17952 | LIB | SUBLETTE | 20 | MP2 | 2002-03-29 08:00 | 2002-03-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17956 | LIB | SUBLETTE | 21 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17957 | LIB | SUBLETTE | 21 | MP2 | 2002-03-11 08:00 | 2002-03-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17958 | LIB | SUBLETTE | 21 | MP2 | 2002-03-28 08:00 | 2002-03-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17962 | LIB | SUBLETTE | 22 | MP2 | 2002-02-15 08:00 | 2002-02-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17963 | LIB | SUBLETTE | 22 | MP2 | 2002-03-01 08:00 | 2002-03-01 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17964 | LIB | SUBLETTE | 22 | MP2 | 2002-03-22 08:00 | 2002-03-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17968 | LIB | SUBLETTE | 23 | MP2 | 2002-02-22 08:00 | 2002-02-22 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17969 | LIB | SUBLETTE | 23 | MP2 | 2002-03-05 08:00 | 2002-03-05 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17970 | LIB | SUBLETTE | 23 | MP2 | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17973 | LIB | SUBLETTE | 24 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17974 | LIB | SUBLETTE | 24 | MP2 | 2002-02-25 08:00 | 2002-02-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17975 | LIB | SUBLETTE | 24 | MP2 | 2002-03-08 08:00 | 2002-03-08 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17976 | LIB | SUBLETTE | 24 | MP2 | 2002-03-21 08:00 | 2002-03-21 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17979 | LIB | SUBLETTE | 26 | MP2 | 2002-02-11 08:00 | 2002-02-11 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17980 | LIB | SUBLETTE | 26 | MP2 | 2002-02-28 08:00 | 2002-02-28 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17981 | LIB | SUBLETTE | 26 | MP2 | 2002-03-04 08:00 | 2002-03-04 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17982 | LIB | SUBLETTE | 26 | MP2 | 2002-03-25 08:00 | 2002-03-25 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17931 | LIB | SUBLETTE | 27 | MP2 | 2002-02-14 08:00 | 2002-02-14 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17932 | LIB | SUBLETTE | 27 | MP2 | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17933 | LIB | SUBLETTE | 27 | MP2 | 2002-03-15 08:00 | 2002-03-15 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17934 | LIB | SUBLETTE | 27 | MP2 | 2002-03-29 08:00 | 2002-03-29 16:00 | 0.3 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17754 | LIB | TATE | 10 | INSPECTION | 2002-12-02 08:00 | 2002-12-13 16:00 | 11.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17755 | LIB | TATE | 11 | INSPECTION | 2002-12-16 08:00 | 2002-12-20 16:00 | 4.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17757 | LIB | TATE | ALL | ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 | 14 | 4.7 | Annual ESD test. |  |  | 0 | P
18392 | LIB | TEXAS 1 | 2 | POWER CYLINDER HEAD | 2002-02-04 08:00 | 2002-02-06 14:00 | 2.3 | 0 | 0 | Replace a power cylinder head on unit #2 (#1R & #2R Head) |  |  | 0 | U
17668 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-10 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17669 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-08-27 08:00 | 2002-08-27 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17670 | LIB | TEXAS 1 | 2 | INSPEC TION | 2002-10-21 08:00 | 2002-10-25 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17671 | LIB | TEXAS 1 | 3 | INSPECTION | 2002-02-18 08:00 | 2002-02-22 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17627 | LIB | TEXAS 1 | 3 | CONTROLS PM | 2002-05-14 07:30 | 2002-05-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17672 | LIB | TEXAS 1 | 3 | ENGINE SERVICE | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 | 0 | 0 | Engine service |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17624 | LIB | TEXAS 1 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 10 | 53.8 | Annual ESD. |  |  | 0 | P
17629 | LIB | TEXAS 2 | 1 | CONTROLS PM | 2002-06-10 07:30 | 2002-06-12 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17631 | LIB | TEXAS 2 | 2 | CONTROLS PM | 2002-06-18 07:30 | 2002-06-20 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17633 | LIB | TEXAS 2 | 3 | CONTROLS PM | 2002-07-08 07:30 | 2002-07-10 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17635 | LIB | TEXAS 2 | 4 | CONTROLS PM | 2002-07-15 07:30 | 2002-07-17 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17636 | LIB | TEXAS 2 | 5 | CONTROLS PM | 2002-08-05 07:30 | 2002-08-07 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17677 | LIB | TEXAS 2 | 6 | INSPECTION | 2002-07-22 08:00 | 2002-07-26 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17678 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-13 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17674 | LIB | TEXAS 2 | 7 | INSPECTION | 2002-06-24 08:00 | 2002-06-28 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17675 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-07-30 08:00 | 2002-07-30 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17625 | LIB | TEXAS 2 | ALL | ANNUAL ESD | 2002-05-06 07:30 | 2002-05-11 16:00 | 5.4 | 15 | 80.6 | Annual ESD. |  |  | 0 | P