## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 12, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18362 | AMA | BEAVER 12 | 3 | UNIT OVERHAUL | 2002-03-26 13:00 | 2002-04-26 16:00 | 31.1 |  | OPS |  | 0 | 0 | Overhaul Engine & Compressors. |  |  |  | 0 | P | N | N
2 | 18376 | AMA | BEAVER 2 | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major engine (Mike White OH). |  |  |  | 0 | P | N | N
3 | 18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hour inspection. |  |  |  | 0 | P | N | N
4 | 18380 | AMA | BEAVER 6 | 1 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine & compressor. |  |  |  | 0 | P | N | N
5 | 18374 | AMA | BEAVER 7 | 1 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major overhaul. |  |  |  | 0 | P | N | N
6 | 18384 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-10-15 08:00 | 2002-10-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
7 | 18386 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N
8 | 18412 | AMA | BEAVER PLANT | 18 | WATER PUMP | 2002-02-06 15:00 | 2002-02-15 16:00 | 9 |  | OPS |  | 0 | 0 | Water pump gears. |  | 2002-02-06 15:00 |  | 0 | U | N | N
9 | 18365 | AMA | BEAVER PLANT | 9 | OVERHAUL | 2002-03-01 08:00 | 2002-03-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major engine & compressors. |  |  |  | 0 | P | N | N
10 | 18367 | AMA | BEAVER PLANT | 12 | OVERHAUL | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major enigne & compressors. |  |  |  | 0 | P | N | N
11 | 18369 | AMA | BEAVER PLANT | 14 | OVERHAUL | 2002-05-01 08:00 | 2002-06-01 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major engine and compressors. |  |  |  | 0 | P | N | N
12 | 18262 | AMA | CANADIAN | 1 & 3 | REFLIEF VALVE TEST | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual relief valve test. Station will be shut down. |  |  |  | 0 | P | N | N
13 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
14 | 18338 | AMA | CLAUDE | 1 | ANNUAL ESD | 2002-05-14 09:00 | 2002-05-14 18:00 | 0.4 |  | OPS |  | 0 | 0 | Conducting annual ESD. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
15 | 18340 | AMA | CLAUDE | 1 | SAFETY DEVICES | 2002-10-08 09:00 | 2002-10-09 08:00 | 1 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
16 | 18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
17 | 18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 |  | OPS |  | 3 | 0.3 | 1500 hour inspection. |  |  |  | 0 | P | N | N
18 | 18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 |  | OPS |  | 7 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
19 | 18385 | AMA | ELLIS 1 | 1 | OVERHAUL | 2002-10-15 08:00 | 2002-11-15 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
20 | 18377 | AMA | ELLIS 2 | 2 | OVERHAUL | 2002-07-15 08:00 | 2002-07-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major compressor. |  |  |  | 0 | P | N | N
21 | 18261 | AMA | HEMPHILL 2 | ANNUAL ESD | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
22 | 18260 | AMA | HEMPHILL 3 | ANNUAL ESD | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
23 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
24 | 18331 | AMA | P3 | ALL | SURGE CONTROL TIE-IN | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | We will need to remove some material that we are going to reuse and test it before we can make our tie-ins. (They will be able to by-pass the station to make some deliveries). |  |  |  | 0 | P | N | N
25 | 18337 | AMA | P3 | ALL | ANNUAL ESD | 2002-04-17 08:00 | 2002-04-17 18:00 | 0.4 |  | OPS |  | 150 | 62.5 | Conducting annual ESD at the P3 station. |  |  |  | 0 | P | N | N
26 | 18332 | AMA | P3 | 1 | SAFETY DEVICES | 2002-04-23 08:00 | 2002-04-24 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
27 | 18371 | AMA | P3 | 1 | OVERHAUL | 2002-05-01 08:00 | 2002-05-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Exchange GP PT & AGB. |  |  |  | 0 | P | N | N
28 | 18333 | AMA | P3 | 2 | SAFETY DEVICES | 2002-05-08 08:00 | 2002-05-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
29 | 18334 | AMA | P3 | 3 | SAFETY DEVICES | 2002-05-22 08:00 | 2002-05-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
30 | 18336 | AMA | P3 | 5 | SAFETY DEVICES | 2002-06-18 08:00 | 2002-06-20 18:00 | 2.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
31 | 18335 | AMA | P3 | 4 | SAFETY DEVICES | 2002-08-22 08:00 | 2002-08-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
32 | 18339 | AMA | PAMPA | 1 | ESD & SAFETY DEVICES | 2002-04-08 08:00 | 2002-04-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Conducting annual ESD test and calibrating safety devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
33 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
34 | 18453 | AMA | ROGER MILLS | 3 | OIL COOLER | 2002-02-11 13:00 | 2002-02-19 16:00 | 8.1 |  | OPS |  | 0 | 0 | Remove engine oil cooler and send in for repair. |  | 2002-02-11 13:00 |  | 0 | P | N | N
35 | 18455 | AMA | ROGER MILLS | ALL | RELIEF VALVE TEST | 2002-04-09 07:30 | 2002-04-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual relief valve testing. |  |  |  | 0 | P | N | N
36 | 18454 | AMA | ROGER MILLS | ALL | ANNUAL ESD | 2002-07-22 08:00 | 2002-07-22 12:00 | 0.2 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
37 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
38 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N
39 | 18387 | AMA | SUNRAY | 6 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
40 | 18388 | AMA | SUNRAY | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
41 | 18389 | AMA | SUNRAY | 5 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | Engine both side & compressor. |  |  |  | 0 | P | N | N
42 | 18378 | AMA | WOODWARD 1 | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-08-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
43 | 18381 | AMA | WOODWARD 2 | 4 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
44 | 18382 | AMA | WOODWARD 3 | 4 | OVERHAUL | 2002-09-15 08:00 | 2002-09-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 12, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18362 | AMA | BEAVER 12 | 3 | UNIT OVERHAUL | 2002-03-26 13:00 | 2002-04-26 16:00 | 31.1 |  | OPS |  | 0 | 0 | Overhaul Engine & Compressors. |  |  |  | 0 | P | N | N
2 | 18376 | AMA | BEAVER 2 | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major engine (Mike White OH). |  |  |  | 0 | P | N | N
3 | 18245 | AMA | BEAVER 6 | 2 | 1500 HR. INSPECTION | 2002-02-20 10:00 | 2002-02-20 13:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hour inspection. |  |  |  | 0 | P | N | N
4 | 18380 | AMA | BEAVER 6 | 1 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine & compressor. |  |  |  | 0 | P | N | N
5 | 18374 | AMA | BEAVER 7 | 1 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major overhaul. |  |  |  | 0 | P | N | N
6 | 18384 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-10-15 08:00 | 2002-10-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
7 | 18386 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N
8 | 18412 | AMA | BEAVER PLANT | 18 | WATER PUMP | 2002-02-06 15:00 | 2002-02-15 16:00 | 9 |  | OPS |  | 0 | 0 | Water pump gears. |  | 2002-02-06 15:00 |  | 0 | U | N | N
9 | 18365 | AMA | BEAVER PLANT | 9 | OVERHAUL | 2002-03-01 08:00 | 2002-03-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major engine & compressors. |  |  |  | 0 | P | N | N
10 | 18367 | AMA | BEAVER PLANT | 12 | OVERHAUL | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major enigne & compressors. |  |  |  | 0 | P | N | N
11 | 18369 | AMA | BEAVER PLANT | 14 | OVERHAUL | 2002-05-01 08:00 | 2002-06-01 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major engine and compressors. |  |  |  | 0 | P | N | N
12 | 18262 | AMA | CANADIAN | 1 & 3 | REFLIEF VALVE TEST | 2002-03-12 08:00 | 2002-03-12 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual relief valve test. Station will be shut down. |  |  |  | 0 | P | N | N
13 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
14 | 18338 | AMA | CLAUDE | 1 | ANNUAL ESD | 2002-05-14 09:00 | 2002-05-14 18:00 | 0.4 |  | OPS |  | 0 | 0 | Conducting annual ESD. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
15 | 18340 | AMA | CLAUDE | 1 | SAFETY DEVICES | 2002-10-08 09:00 | 2002-10-09 08:00 | 1 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
16 | 18247 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-02-12 09:00 | 2002-02-12 16:00 | 0.3 |  | OPS |  | 3 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
17 | 18248 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-02-13 09:00 | 2002-02-13 11:00 | 0.1 |  | OPS |  | 3 | 0.3 | 1500 hour inspection. |  |  |  | 0 | P | N | N
18 | 18249 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTION | 2002-02-14 09:00 | 2002-02-14 12:00 | 0.1 |  | OPS |  | 7 | 0.9 | 1500 hour inspection. |  |  |  | 0 | P | N | N
19 | 18385 | AMA | ELLIS 1 | 1 | OVERHAUL | 2002-10-15 08:00 | 2002-11-15 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
20 | 18377 | AMA | ELLIS 2 | 2 | OVERHAUL | 2002-07-15 08:00 | 2002-07-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major compressor. |  |  |  | 0 | P | N | N
21 | 18261 | AMA | HEMPHILL 2 | ANNUAL ESD | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
22 | 18260 | AMA | HEMPHILL 3 | ANNUAL ESD | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
23 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
24 | 18331 | AMA | P3 | ALL | SURGE CONTROL TIE-IN | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | We will need to remove some material that we are going to reuse and test it before we can make our tie-ins. (They will be able to by-pass the station to make some deliveries). |  |  |  | 0 | P | N | N
25 | 18337 | AMA | P3 | ALL | ANNUAL ESD | 2002-04-17 08:00 | 2002-04-17 18:00 | 0.4 |  | OPS |  | 150 | 62.5 | Conducting annual ESD at the P3 station. |  |  |  | 0 | P | N | N
26 | 18332 | AMA | P3 | 1 | SAFETY DEVICES | 2002-04-23 08:00 | 2002-04-24 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
27 | 18371 | AMA | P3 | 1 | OVERHAUL | 2002-05-01 08:00 | 2002-05-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Exchange GP PT & AGB. |  |  |  | 0 | P | N | N
28 | 18333 | AMA | P3 | 2 | SAFETY DEVICES | 2002-05-08 08:00 | 2002-05-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
29 | 18334 | AMA | P3 | 3 | SAFETY DEVICES | 2002-05-22 08:00 | 2002-05-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
30 | 18336 | AMA | P3 | 5 | SAFETY DEVICES | 2002-06-18 08:00 | 2002-06-20 18:00 | 2.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
31 | 18335 | AMA | P3 | 4 | SAFETY DEVICES | 2002-08-22 08:00 | 2002-08-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
32 | 18339 | AMA | PAMPA | 1 | ESD & SAFETY DEVICES | 2002-04-08 08:00 | 2002-04-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Conducting annual ESD test and calibrating safety devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
33 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
34 | 18453 | AMA | ROGER MILLS | 3 | OIL COOLER | 2002-02-11 13:00 | 2002-02-19 16:00 | 8.1 |  | OPS |  | 0 | 0 | Remove engine oil cooler and send in for repair. |  | 2002-02-11 13:00 |  | 0 | P | N | N
35 | 18455 | AMA | ROGER MILLS | ALL | RELIEF VALVE TEST | 2002-04-09 07:30 | 2002-04-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual relief valve testing. |  |  |  | 0 | P | N | N
36 | 18454 | AMA | ROGER MILLS | ALL | ANNUAL ESD | 2002-07-22 08:00 | 2002-07-22 12:00 | 0.2 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
37 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
38 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N
39 | 18387 | AMA | SUNRAY | 6 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
40 | 18388 | AMA | SUNRAY | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
41 | 18389 | AMA | SUNRAY | 5 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | Engine both side & compressor. |  |  |  | 0 | P | N | N
42 | 18378 | AMA | WOODWARD 1 | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-08-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
43 | 18381 | AMA | WOODWARD 2 | 4 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
44 | 18382 | AMA | WOODWARD 3 | 4 | OVERHAUL | 2002-09-15 08:00 | 2002-09-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N