## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 12, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
3 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-09-02 07:00 | 2002-10-04 15:30 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Flow affect will depends the needs on the pipeline). Unit pumps about 75 mmcfd. |  |  |  | 0 | P | N | N
4 | 18411 | BEA | PALMYRA | 23 | POWER PISTON | 2002-02-11 07:30 | 2002-02-12 16:00 | 1.4 |  | OPS |  | 0 | 0 | Pulling #3 power piston for inspection and installing a recondition power cylinder head. (We will check with Gas Control before starting on Monday morning). |  |  |  | 0 | P | N | N
5 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-21 16:00 | 15.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
7 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N
9 | 18324 | BEA | TESCOTT | ALL | MOVE ESD STATION | 2002-03-15 08:00 | 2002-03-15 13:00 | 0.2 |  | OPS |  | 0 | 0 | We need to remove the ESD station with the new gate installation. We estimate this will take 4 to 6 hours. (Will have to work with Gas Control to schedule this outage). |  |  |  | 0 | U | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 12, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
3 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL | 2002-09-02 07:00 | 2002-10-04 15:30 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Flow affect will depends the needs on the pipeline). Unit pumps about 75 mmcfd. |  |  |  | 0 | P | N | N
4 | 18411 | BEA | PALMYRA | 23 | POWER PISTON | 2002-02-11 07:30 | 2002-02-12 16:00 | 1.4 |  | OPS |  | 0 | 0 | Pulling #3 power piston for inspection and installing a recondition power cylinder head. (We will check with Gas Control before starting on Monday morning). |  |  |  | 0 | P | N | N
5 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-21 16:00 | 15.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
7 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N
9 | 18324 | BEA | TESCOTT | ALL | MOVE ESD STATION | 2002-03-15 08:00 | 2002-03-15 13:00 | 0.2 |  | OPS |  | 0 | 0 | We need to remove the ESD station with the new gate installation. We estimate this will take 4 to 6 hours. (Will have to work with Gas Control to schedule this outage). |  |  |  | 0 | U | N | N