## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
DesMoines Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 21, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17521 | DES | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 | P | N | N
2 | 17518 | DES | BELLEVILLE | 1 | ANNUAL PM | 2002-09-09 09:00 | 2002-09-13 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
3 | 17517 | DES | BELLEVILLE | 2 | ANNUAL PM | 2002-09-16 09:00 | 2002-09-20 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
4 | 17516 | DES | BELLEVILLE | 3 | ANNUAL PM | 2002-09-23 09:00 | 2002-09-27 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
5 | 18497 | DES | EARLVILLE | 1 | WATER WASH | 2002-04-17 06:00 | 2002-04-17 16:00 | 0.4 |  | OPS |  | 0 | 0 | Water wash turbine and change air filters. |  |  |  | 0 | P | N | N
6 | 18498 | DES | EARLVILLE | 1 | ESD & P.M. CONTROLS | 2002-07-09 07:00 | 2002-07-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual ESD test P.M. all control and end devices change ESD relief valves change oil filters change fuel filters water wash turbine program modification by Solar service bulletin work and motor control center P.M.'s. |  |  |  | 0 | P | N | N
7 | 17161 | DES | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 | P | N | N
8 | 17520 | DES | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 | P | N | N
9 | 17519 | DES | GALENA | 1 | ANNUAL PM | 2002-10-07 08:00 | 2002-10-11 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
10 | 17515 | DES | GALENA | 2 | ANNUAL PM | 2002-10-14 08:00 | 2002-10-18 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
11 | 18397 | DES | HUBBARD | 1 | ANNUAL ESD & SUBSTATION MAINTENANCE | 2002-06-17 09:00 | 2002-06-21 13:00 | 4.2 |  | OPS |  | 0 | 0 | Annual ESD will blow the station down Electrical Substation & High yard testing. All other station compliance testing. The station can be available after the second day 6/19/02. The unit could be made available at the end of each day. |  |  |  | 0 | P | N | N
12 | 18287 | DES | OGDEN | 16 | P.M. | 2002-02-25 08:00 | 2002-03-25 16:00 | 28.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
13 | 18286 | DES | OGDEN | 15 | P.M. | 2002-03-11 08:00 | 2002-03-22 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
14 | 18285 | DES | OGDEN | 14 | P.M. | 2002-03-25 08:00 | 2002-04-05 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
15 | 18284 | DES | OGDEN | 13 | P.M. | 2002-04-08 08:00 | 2002-04-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
16 | 18290 | DES | OGDEN | 16 | MCS & CONTROLS | 2002-04-22 08:00 | 2002-04-26 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
17 | 17164 | DES | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
18 | 18289 | DES | OGDEN | 18 | P.M | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
19 | 18291 | DES | OGDEN | 14 | MCS & CONTROLS | 2002-05-20 08:00 | 2002-05-24 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
20 | 18292 | DES | OGDEN | PLANT 3 | BSD | 2002-05-29 08:00 | 2002-05-29 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
21 | 17163 | DES | OGDEN | 14 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
22 | 18293 | DES | OGDEN | PLANT 2 | BSD | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
23 | 18451 | DES | OGDEN | HWY 141 DM A | DESMOINES A LINE | 2002-06-05 08:00 | 2002-06-08 16:00 | 3.3 |  | 453 |  | 0 | 0 | Hwy 141 DM A Relocate- Relocate and install approx. 1500 feet of 16" pipe of the DesMoines A line at Hwy 141 in Polk Co. Iowa. Remove approx. 1200 feet of 16" pipe. |  |  |  | 0 | P | N | N
24 | 17165 | DES | OGDEN | 16 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
25 | 18278 | DES | OGDEN | 7 | P.M. | 2002-07-29 08:00 | 2002-08-02 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive maintenance. |  |  |  | 0 | P | N | N
26 | 18279 | DES | OGDEN | 8 | P.M. | 2002-08-05 08:00 | 2002-08-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
27 | 18280 | DES | OGDEN | 9 | P.M. | 2002-08-12 08:00 | 2002-08-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
28 | 18281 | DES | OGDEN | 10 | P.M. | 2002-08-19 08:00 | 2002-08-23 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
29 | 18282 | DES | OGDEN | 11 | P.M. | 2002-08-26 08:00 | 2002-08-30 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
30 | 18283 | DES | OGDEN | 12 | P.M. | 2002-09-03 08:00 | 2002-09-06 16:00 | 3.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
31 | 18288 | DES | OGDEN | 17 | P.M. | 2002-09-16 08:00 | 2002-09-27 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
32 | 17229 | DES | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 | P | N | N
33 | 18449 | DES | PLATTEVILLE | HWY 151 | REPLACE 8" SAVANNA BL | 2002-04-26 08:00 | 2002-04-26 16:00 | 0.3 |  | 453 |  | 0 | 0 | Hwy 151 Dubuque Co- Replace and lower approx. 450 feet of 8" pipe of the Savanna BL at Hwy 151 in Dubuque Co. Iowa. |  |  |  | 0 | P | N | N
34 | 18372 | DES | PORTLAND 2101 | 3 | OVERHAUL | 2002-05-06 08:00 | 2002-06-14 16:00 | 39.3 |  | OPS |  | 0 | 0 | Top end overhaul. |  |  |  | 0 | P | N | N
35 | 18322 | DES | REDFIELD | 3 | MAINTENANCE | 2002-06-03 07:30 | 2002-06-14 16:00 | 11.4 |  | OPS |  | 0 | 0 | #3 will have some compressor maintenance done to it. |  |  |  | 0 | P | N | N
36 | 18323 | DES | REDFIELD | ESD | ANNUAL ESD | 2002-06-24 07:30 | 2002-06-28 16:00 | 4.4 |  | OPS |  | 0 | 0 | Will have our planned ESD. After shut in some time in June. |  |  |  | 0 | P | N | N
37 | 17171 | DES | REDFIELD | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Cooper GMWA-8based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
38 | 18424 | DES | WATERLOO | 6 | PACKING LEAK & COMPRESSOR RINGS | 2002-02-11 07:00 | 2002-02-27 15:30 | 16.3 |  | OPS |  | 0 | 0 | Repair packing leak on compressor on unit #6 replace packing and oil scraper packing put in new gasket for packing. Pulled compressors apart and found broken some broken rings. |  | 2002-02-11 07:00 |  | 0 | P | N | N
39 | 18499 | DES | WATERLOO | ALL | ESD | 2002-08-06 07:00 | 2002-08-07 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual ESD test rebuild ESD regulators test ESD relief valves Motor Control center wiring clean-up install ESD system quick fill assembly replace unit #6 suction and discharge lead-line valves (Valve replacement pending funding). |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
DesMoines Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 21, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17521 | DES | BELLEVILLE | 1 2 3 | ESD TEST | 2002-05-07 10:00 | 2002-05-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 3300 HP |  |  |  | 0 | P | N | N
2 | 17518 | DES | BELLEVILLE | 1 | ANNUAL PM | 2002-09-09 09:00 | 2002-09-13 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
3 | 17517 | DES | BELLEVILLE | 2 | ANNUAL PM | 2002-09-16 09:00 | 2002-09-20 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
4 | 17516 | DES | BELLEVILLE | 3 | ANNUAL PM | 2002-09-23 09:00 | 2002-09-27 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 1100 HP |  |  |  | 0 | P | N | N
5 | 18497 | DES | EARLVILLE | 1 | WATER WASH | 2002-04-17 06:00 | 2002-04-17 16:00 | 0.4 |  | OPS |  | 0 | 0 | Water wash turbine and change air filters. |  |  |  | 0 | P | N | N
6 | 18498 | DES | EARLVILLE | 1 | ESD & P.M. CONTROLS | 2002-07-09 07:00 | 2002-07-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual ESD test P.M. all control and end devices change ESD relief valves change oil filters change fuel filters water wash turbine program modification by Solar service bulletin work and motor control center P.M.'s. |  |  |  | 0 | P | N | N
7 | 17161 | DES | GALENA | 1 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Solar Centaur Turbine exchange based on analysis and run hours. |  |  |  | 0 | P | N | N
8 | 17520 | DES | GALENA | 1 2 | ESD TEST | 2002-05-14 09:00 | 2002-05-14 11:00 | 0.1 |  | OPS |  | 0 | 0 | ESD test. 8000 HP |  |  |  | 0 | P | N | N
9 | 17519 | DES | GALENA | 1 | ANNUAL PM | 2002-10-07 08:00 | 2002-10-11 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
10 | 17515 | DES | GALENA | 2 | ANNUAL PM | 2002-10-14 08:00 | 2002-10-18 16:00 | 4.3 |  | OPS |  | 0 | 0 | Annual PM. 4000 HP |  |  |  | 0 | P | N | N
11 | 18397 | DES | HUBBARD | 1 | ANNUAL ESD & SUBSTATION MAINTENANCE | 2002-06-17 09:00 | 2002-06-21 13:00 | 4.2 |  | OPS |  | 0 | 0 | Annual ESD will blow the station down Electrical Substation & High yard testing. All other station compliance testing. The station can be available after the second day 6/19/02. The unit could be made available at the end of each day. |  |  |  | 0 | P | N | N
12 | 18287 | DES | OGDEN | 16 | P.M. | 2002-02-25 08:00 | 2002-03-25 16:00 | 28.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
13 | 18286 | DES | OGDEN | 15 | P.M. | 2002-03-11 08:00 | 2002-03-22 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
14 | 18285 | DES | OGDEN | 14 | P.M. | 2002-03-25 08:00 | 2002-04-05 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
15 | 18284 | DES | OGDEN | 13 | P.M. | 2002-04-08 08:00 | 2002-04-19 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
16 | 18290 | DES | OGDEN | 16 | MCS & CONTROLS | 2002-04-22 08:00 | 2002-04-26 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
17 | 17164 | DES | OGDEN | 15 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
18 | 18289 | DES | OGDEN | 18 | P.M | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
19 | 18291 | DES | OGDEN | 14 | MCS & CONTROLS | 2002-05-20 08:00 | 2002-05-24 16:00 | 4.3 |  | OPS |  | 0 | 0 | MCS and Controls work on engines. |  |  |  | 0 | P | N | N
20 | 18292 | DES | OGDEN | PLANT 3 | BSD | 2002-05-29 08:00 | 2002-05-29 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
21 | 17163 | DES | OGDEN | 14 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
22 | 18293 | DES | OGDEN | PLANT 2 | BSD | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 |  | OPS |  | 0 | 0 | Scheduled BSD. |  |  |  | 0 | P | N | N
23 | 18451 | DES | OGDEN | HWY 141 DM A | DESMOINES A LINE | 2002-06-05 08:00 | 2002-06-08 16:00 | 3.3 |  | 453 |  | 0 | 0 | Hwy 141 DM A Relocate- Relocate and install approx. 1500 feet of 16" pipe of the DesMoines A line at Hwy 141 in Polk Co. Iowa. Remove approx. 1200 feet of 16" pipe. |  |  |  | 0 | P | N | N
24 | 17165 | DES | OGDEN | 16 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Dresser Clark TLA-6 based on preventative maintenance data analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
25 | 18278 | DES | OGDEN | 7 | P.M. | 2002-07-29 08:00 | 2002-08-02 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive maintenance. |  |  |  | 0 | P | N | N
26 | 18279 | DES | OGDEN | 8 | P.M. | 2002-08-05 08:00 | 2002-08-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
27 | 18280 | DES | OGDEN | 9 | P.M. | 2002-08-12 08:00 | 2002-08-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
28 | 18281 | DES | OGDEN | 10 | P.M. | 2002-08-19 08:00 | 2002-08-23 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
29 | 18282 | DES | OGDEN | 11 | P.M. | 2002-08-26 08:00 | 2002-08-30 16:00 | 4.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
30 | 18283 | DES | OGDEN | 12 | P.M. | 2002-09-03 08:00 | 2002-09-06 16:00 | 3.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
31 | 18288 | DES | OGDEN | 17 | P.M. | 2002-09-16 08:00 | 2002-09-27 16:00 | 11.3 |  | OPS |  | 0 | 0 | Preventive Maintenance. |  |  |  | 0 | P | N | N
32 | 17229 | DES | OTTAWA | N MANHATTAN | N MANHATTAN CV | 2002-04-17 08:00 | 2002-04-21 16:00 | 4.3 |  | 453 | C.014802 | 0 | 0 | North Manhattan CV replacement. Remove existing control valve and install a new quieter valve. |  |  |  | 0 | P | N | N
33 | 18449 | DES | PLATTEVILLE | HWY 151 | REPLACE 8" SAVANNA BL | 2002-04-26 08:00 | 2002-04-26 16:00 | 0.3 |  | 453 |  | 0 | 0 | Hwy 151 Dubuque Co- Replace and lower approx. 450 feet of 8" pipe of the Savanna BL at Hwy 151 in Dubuque Co. Iowa. |  |  |  | 0 | P | N | N
34 | 18372 | DES | PORTLAND 2101 | 3 | OVERHAUL | 2002-05-06 08:00 | 2002-06-14 16:00 | 39.3 |  | OPS |  | 0 | 0 | Top end overhaul. |  |  |  | 0 | P | N | N
35 | 18322 | DES | REDFIELD | 3 | MAINTENANCE | 2002-06-03 07:30 | 2002-06-14 16:00 | 11.4 |  | OPS |  | 0 | 0 | #3 will have some compressor maintenance done to it. |  |  |  | 0 | P | N | N
36 | 18323 | DES | REDFIELD | ESD | ANNUAL ESD | 2002-06-24 07:30 | 2002-06-28 16:00 | 4.4 |  | OPS |  | 0 | 0 | Will have our planned ESD. After shut in some time in June. |  |  |  | 0 | P | N | N
37 | 17171 | DES | REDFIELD | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Cooper GMWA-8based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
38 | 18424 | DES | WATERLOO | 6 | PACKING LEAK & COMPRESSOR RINGS | 2002-02-11 07:00 | 2002-02-27 15:30 | 16.3 |  | OPS |  | 0 | 0 | Repair packing leak on compressor on unit #6 replace packing and oil scraper packing put in new gasket for packing. Pulled compressors apart and found broken some broken rings. |  | 2002-02-11 07:00 |  | 0 | P | N | N
39 | 18499 | DES | WATERLOO | ALL | ESD | 2002-08-06 07:00 | 2002-08-07 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual ESD test rebuild ESD regulators test ESD relief valves Motor Control center wiring clean-up install ESD system quick fill assembly replace unit #6 suction and discharge lead-line valves (Valve replacement pending funding). |  |  |  | 0 | P | N | N