## 022502a
PLANNED AND UNPLANNED OUTAGES AFFECTING THE BUSHTON UNIVERSE.
2002-02-25
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
17698 | LIB | FINNEY 4 | 1 | BEARING SENSOR | 2001-10-05 14:00 | 2002-06-30 16:30 | 268.1 | 0 | 0 | Lost main bearing sensor. Pulled doors off to check sensor and found metal in crankcase. Drained oil and located problem. Unit will have to be re-worked. | 2001-10-05 14:00 |  | 0 | U
18461 | AMA | BEAVER 12 | 1 | SUCTION SCRUBBER | 2001-12-29 12:00 | 2002-03-22 16:00 | 83.2 | 0 | 0 | Have suction scrubber rebuilt. | 2001-12-29 12:00 |  | 0 | U
18353 | LIB | HUGOTON | 10 | MP2 & MAINTENANCE | 2002-01-07 08:00 | 2002-03-15 14:00 | 67.3 | 0 | 0 | MP2 & and other maintenance. They have a spare unit so there is no flow affect. | 2002-01-07 08:00 |  | 0 | P
18312 | LIB | MULLINVILLE | 19 | REPLACE ROD BEARING | 2002-01-16 14:00 | 2002-02-28 16:00 | 43.1 | 0 | 0 | Will remove bearing and inspect crank shaft. | 2002-01-16 14:00 |  | 0 | U
18412 | AMA | BEAVER PLANT | 18 | WATER PUMP | 2002-02-06 15:00 | 2002-02-27 16:00 | 21 | 0 | 0 | Water pump gears. | 2002-02-06 15:00 |  | 0 | U
17974 | LIB | SUBLETTE | 24 | MP2 | 2002-02-25 08:00 | 2002-02-26 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP | 2002-02-25 08:00 |  | 0 | P
18458 | LIB | HUGOTON | 16 | WARRENTY WORK | 2002-02-26 08:00 | 2002-02-26 16:00 | 0.3 | 0 | 0 | Cooper is doing warrenty work on the blower. |  |  | 0 | P
17986 | LIB | SUBLETTE | 13 | MP2 | 2002-02-27 08:00 | 2002-02-28 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17963 | LIB | SUBLETTE | 22 | MP2 | 2002-03-01 08:00 | 2002-03-02 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
18365 | AMA | BEAVER PLANT | 9 | OVERHAUL | 2002-03-01 08:00 | 2002-03-30 16:00 | 29.3 | 0 | 0 | Major engine & compressors. |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-04 16:00 | 0.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17945 | LIB | SUBLETTE | 19 | MP2 | 2002-03-04 08:00 | 2002-03-05 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17981 | LIB | SUBLETTE | 26 | MP2 | 2002-03-04 08:00 | 2002-03-05 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
18506 | BEA | BUSHTON | 31 | EXHAUST HEADER | 2002-03-05 07:00 | 2002-03-07 15:30 | 2.3 | 0 | 0 | Replace section of exhaust header. |  |  | 0 | P
17969 | LIB | SUBLETTE | 23 | MP2 | 2002-03-05 08:00 | 2002-03-06 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
18468 | LIB | CLARK 1 | 1 | BORESCOPE | 2002-03-05 08:00 | 2002-03-06 16:00 | 1.3 | 2 | 2.7 | Borescope the power cylinder. |  |  | 0 | P
18012 | LIB | FINNEY 2 | 1 | MAINTENANCE | 2002-03-05 08:00 | 2002-03-07 16:00 | 2.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18062 | LIB | STEVENS 7 | 1 | MP2 | 2002-03-05 09:00 | 2002-03-07 16:00 | 2.3 | 4 | 9.2 | MP2 Tasks. |  |  | 0 | P
17774 | LIB | STEVENS 2 | 6 | SERVICE | 2002-03-06 08:00 | 2002-03-06 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM 1234 HP |  |  | 0 | P
17939 | LIB | SUBLETTE | 14 | MP2 | 2002-03-07 08:00 | 2002-03-08 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
18013 | LIB | FINNEY 2 | 2 | MAINTENANCE | 2002-03-07 08:00 | 2002-03-08 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17975 | LIB | SUBLETTE | 24 | MP2 | 2002-03-08 08:00 | 2002-03-09 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-11 16:00 | 0.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17957 | LIB | SUBLETTE | 21 | MP2 | 2002-03-11 08:00 | 2002-03-12 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
18456 | LIB | HOLCOMB | 1 | CAM BOX | 2002-03-11 08:00 | 2002-03-12 16:00 | 1.3 | 0 | 0 | Working on the Cam Box. |  |  | 0 | P
18400 | LIB | FINNEY 4 | 3 | OVERHAUL | 2002-03-11 08:00 | 2002-04-05 16:30 | 25.3 | 3 | 76 | The unit will pulled out and overhauled. (Unit #2 will be down also due to no demand form unit #3). |  |  | 0 | P
18466 | LIB | BEAVER 1 | 3 | BORESCOPE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Borescope power cylinder. |  |  | 0 | P
18014 | LIB | FINNEY 2 | 3 | MAINTENANCE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17846 | LIB | STEVENS 3 | 3 | SERVICE | 2002-03-12 08:00 | 2002-03-13 16:00 | 1.3 | 0 | 0 | Service unit plus panel S/D & PM MP2 Tasks. 1100 HP |  |  | 0 | P
17987 | LIB | SUBLETTE | 13 | MP2 | 2002-03-13 08:00 | 2002-03-14 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
18446 | LIB | STEVENS 4 | 2 | SERVICE | 2002-03-13 08:00 | 2002-03-14 16:00 | 1.3 | 3.5 | 4.7 | Service and MP2 tasks. |  |  | 0 | P
18015 | LIB | FINNEY 3 | 3 | MAINTENANCE | 2002-03-14 09:00 | 2002-03-14 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17951 | LIB | SUBLETTE | 20 | MP2 | 2002-03-15 08:00 | 2002-03-16 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17933 | LIB | SUBLETTE | 27 | MP2 | 2002-03-15 08:00 | 2002-03-16 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
18504 | AMA | PERRYTON BARLOW | 1 2 3 | TEST RELIEF VALVES | 2002-03-18 08:00 | 2002-03-18 16:00 | 0.3 | 7 | 2.3 | Relief valve testing. |  |  | 0 | P
18016 | LIB | FINNEY 2 | 5 | MAINTENANCE | 2002-03-18 08:00 | 2002-03-18 16:00 | 0.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18505 | AMA | NORTHRUP | 1 2 | RELIEF VALVE TEST | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 15 | 5 | Testing the the relief valves. |  |  | 0 | P
18017 | LIB | FINNEY 2 | 6 | MAINTENANCE | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18436 | LIB | STEVENS 4 | 1 | MP2 | 2002-03-20 08:00 | 2002-03-20 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
17940 | LIB | SUBLETTE | 14 | MP2 | 2002-03-20 08:00 | 2002-03-21 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17976 | LIB | SUBLETTE | 24 | MP2 | 2002-03-21 08:00 | 2002-03-22 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
18018 | LIB | FINNEY 2 | 7 | MAINTENANCE | 2002-03-21 08:00 | 2002-03-22 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17964 | LIB | SUBLETTE | 22 | MP2 | 2002-03-22 08:00 | 2002-03-23 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17946 | LIB | SUBLETTE | 19 | MP2 | 2002-03-25 08:00 | 2002-03-26 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17982 | LIB | SUBLETTE | 26 | MP2 | 2002-03-25 08:00 | 2002-03-26 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
17970 | LIB | SUBLETTE | 23 | MP2 | 2002-03-26 08:00 | 2002-03-27 08:00 | 1 | 9 | 9 | MP 2 Tasks. 1400 HP |  |  | 0 | P
18019 | LIB | FINNEY 2 | 8 | MAINTENANCE | 2002-03-26 08:00 | 2002-03-27 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
18362 | AMA | BEAVER 12 | 3 | UNIT OVERHAUL | 2002-03-26 13:00 | 2002-04-26 16:00 | 31.1 | 0 | 0 | Overhaul Engine & Compressors. |  |  | 0 | P
17988 | LIB | SUBLETTE | 13 | MP2 | 2002-03-27 08:00 | 2002-03-28 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17958 | LIB | SUBLETTE | 21 | MP2 | 2002-03-28 08:00 | 2002-03-29 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
18020 | LIB | FINNEY 2 | 9 | MAINTENANCE | 2002-03-28 08:00 | 2002-03-29 16:00 | 1.3 | 0 | 0 | Scheduled maintenance: work orders & DET list. |  |  | 0 | P
17952 | LIB | SUBLETTE | 20 | MP2 | 2002-03-29 08:00 | 2002-03-30 08:00 | 1 | 0 | 0 | MP 2 Tasks. 2000 HP |  |  | 0 | P
17934 | LIB | SUBLETTE | 27 | MP2 | 2002-03-29 08:00 | 2002-03-30 08:00 | 1 | 0 | 0 | MP 2 Tasks. 6000 HP |  |  | 0 | P
18364 | LIB | FINNEY 3 | 1 | ENGINE EXCHANGE | 2002-04-01 08:00 | 2002-04-15 16:00 | 14.3 | 0 | 0 | Engine exchange. |  |  | 0 | P
18367 | AMA | BEAVER PLANT | 12 | OVERHAUL | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 | 0 | 0 | Major enigne & compressors. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-08 16:00 | 0.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
18368 | LIB | FINNEY 2 | 1 | OVERHAUL | 2002-04-15 08:00 | 2002-04-30 16:00 | 15.3 | 0 | 0 | Inframe engine & compressor OH. |  |  | 0 | P
18363 | LIB | FINNEY 4 | 4 | OVERHAUL | 2002-04-15 08:00 | 2002-05-10 16:30 | 25.3 | 3 | 76 | Unit will be pulled out and overhauled. (Unit Exchange if possible). |  |  | 0 | P
18437 | LIB | STEVENS 4 | 1 | MP2 | 2002-04-17 08:00 | 2002-04-17 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
18447 | LIB | STEVENS 4 | 2 | MP2 | 2002-04-18 08:00 | 2002-04-18 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18401 | LIB | BURDETT | 1 | BORESCOPE & MINOR MAINTENANCE | 2002-04-29 07:30 | 2002-05-10 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
18370 | LIB | MULLINVILLE | 8 AUX. | OVERHAUL | 2002-05-01 08:00 | 2002-05-03 16:00 | 2.3 | 0 | 0 | TEO |  |  | 0 | P
17836 | LIB | HOLCOMB | 10 | REPLACE PISTONS & RINGS | 2002-05-01 08:00 | 2002-05-31 16:00 | 30.3 | 0 | 0 | Replace pistons and rings overhaul 2 & 3 compressors. |  |  | 0 | P
18369 | AMA | BEAVER PLANT | 14 | OVERHAUL | 2002-05-01 08:00 | 2002-06-01 16:00 | 31.3 | 0 | 0 | Major engine and compressors. |  |  | 0 | P
18511 | LIB | FINNEY 1 2 3 4 | ALL | ANNUAL ESD | 2002-05-02 07:30 | 2002-05-02 16:00 | 0.4 | 0 | 0 | Annual ESD's for the Finney Co. Stations. 1 2 3 and 4. |  |  | 0 | P
18408 | LIB | BURDETT | ALL | ANNUAL ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 0 | 0 | Annual ESD will shut down during the same time as Holcomb's ESD. |  |  | 0 | P
17839 | LIB | HOLCOMB | ESD | ANNUAL ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 135 | 22.5 | Annual ESD and maintenance. |  |  | 0 | P
17840 | LIB | HOLCOMB | HOLCOMB SOUTH | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 8 | 1.3 | Outage coordinated with Holcomb's Annual ESD. |  |  | 0 | P
17757 | LIB | TATE | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 | 14 | 2.3 | Annual ESD test. |  |  | 0 | P
18073 | LIB | STEVENS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | 30 | 3.8 | Annual ESD. |  |  | 0 | P
18493 | LIB | STEVENS 3 | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 10:30 | 0.1 | 6 | 0.8 | Annual ESD. |  |  | 0 | P
17622 | LIB | MORTON 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | 18 | 4.5 | Annual ESD. |  |  | 0 | P
17623 | LIB | MORTON 6 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-07 13:00 | 0.3 | 8 | 2 | Annual ESD. |  |  | 0 | P
17624 | LIB | TEXAS 1 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | 10 | 12.9 | Annual ESD. |  |  | 0 | P
17625 | LIB | TEXAS 2 | ALL | ANNUAL ESD | 2002-05-07 07:30 | 2002-05-08 14:00 | 1.3 | 15 | 19.4 | Annual ESD. |  |  | 0 | P
18089 | LIB | HUGOTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-09 16:00 | 2.4 | 80 | 190 | Planned ESD. (Actual completion time depends on contractors). |  |  | 0 | P
17842 | LIB | STEVENS 2 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | 19 | 1.6 | Annual ESD |  |  | 0 | P
18472 | LIB | STEVENS 7 | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 10:30 | 0.1 | 30 | 2.5 | Annual ESD. |  |  | 0 | P
18473 | LIB | SUBLETTE | ALL | ESD | 2002-05-07 08:00 | 2002-05-07 14:00 | 0.3 | 0 | 0 | Annual ESD. (Flow affects are in Hugoton's outage). |  |  | 0 | P
17895 | LIB | STEVENS 4 | ALL | ANNUAL ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 18 | 42 | Annual ESD. (Station will be back up when Hugoton comes back on). |  |  | 0 | P
18471 | LIB | STEVENS 6 | ALL | ESD | 2002-05-07 08:00 | 2002-05-09 16:00 | 2.3 | 18 | 42 | Annual ESD. (The station will be back on line when the Hugoton plant comes back on). |  |  | 0 | P
18459 | AMA | ELLIS 1 | ALL | ANNUAL ESD | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 | 21 | 1.8 | Annual ESD. Will blind flange and not blow the station down. |  |  | 0 | P
18460 | AMA | BEAVER 6 | ALL | ANNUAL ESD | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 | 10.5 | 0.9 | Annual ESD. Will blind flange and not blow the station down. |  |  | 0 | P
18438 | LIB | STEVENS 4 | 1 | SERVICE | 2002-05-09 08:00 | 2002-05-10 20:00 | 1.5 | 3.5 | 5.3 | Service and MP2 tasks. |  |  | 0 | P
17626 | LIB | MORTON 6 | 1 | MP 2 | 2002-05-13 07:30 | 2002-05-15 16:00 | 2.4 | 4 | 9.5 | MP2 8 000 hour inspect. |  |  | 0 | P
18467 | LIB | CLARK 1 | ALL | ESD | 2002-05-13 08:00 | 2002-05-13 16:00 | 0.3 | 6.5 | 2.2 | Annual ESD. |  |  | 0 | P
17627 | LIB | TEXAS 1 | 3 | CONTROLS PM | 2002-05-14 07:30 | 2002-05-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
18494 | LIB | MULLINVILLE | ALL | ESD | 2002-05-14 08:00 | 2002-05-16 16:00 | 2.3 | 100 | 233.3 | Annual ESD. |  |  | 0 | P
18469 | LIB | CLARK 2 | ALL | ESD | 2002-05-15 08:00 | 2002-05-15 16:00 | 0.3 | 6 | 2 | Annual ESD. |  |  | 0 | P
18513 | AMA | ELLIS 2 | ALL | ESD | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
18465 | LIB | BEAVER 1 | ALL | ESD | 2002-05-16 08:00 | 2002-05-16 16:00 | 0.3 | 14 | 4.7 | Annual ESD. |  |  | 0 | P
18402 | LIB | BURDETT | 2 | BORESCOPE & MAINTENANCE | 2002-05-20 07:30 | 2002-05-31 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18448 | LIB | STEVENS 4 | 2 | MP2 | 2002-05-23 08:00 | 2002-05-23 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
17628 | LIB | MORTON 6 | 2 | MP2 | 2002-05-28 07:30 | 2002-05-30 16:00 | 2.4 | 4 | 9.5 | MP2 8 000 hr inspection |  |  | 0 | P
17892 | LIB | STEVENS 4 | 4 | OVERHAUL | 2002-06-01 08:00 | 2002-07-01 16:00 | 30.3 | 0 | 0 | Comp. & engine overhaul. |  |  | 0 | P
17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17672 | LIB | TEXAS 1 | 3 | ENGINE SERVICE | 2002-06-05 08:00 | 2002-06-05 16:00 | 0.3 | 0 | 0 | Engine service |  |  | 0 | P
17629 | LIB | TEXAS 2 | 1 | CONTROLS PM | 2002-06-10 07:30 | 2002-06-10 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
18403 | LIB | BURDETT | 3 | BORESCOPE & MAINTENANCE | 2002-06-10 07:30 | 2002-06-21 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18514 | AMA | WOODWARD 1 | ALL | ESD | 2002-06-12 09:00 | 2002-06-12 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
18374 | AMA | BEAVER 7 | 1 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 | 0 | 0 | Major overhaul. |  |  | 0 | P
18375 | LIB | STEVENS 1 | 4 | OVERHAUL | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 | 0 | 0 | Major compressor and all five cylinders. |  |  | 0 | P
18407 | LIB | BURDETT | ALL | RELIEF VALVE TESTING | 2002-06-17 07:30 | 2002-06-21 16:00 | 4.4 | 0 | 0 | Will take one unit down at a time to do the testing. |  |  | 0 | P
17631 | LIB | TEXAS 2 | 2 | CONTROLS PM | 2002-06-18 07:30 | 2002-06-18 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
18439 | LIB | STEVENS 4 | 1 | MP2 | 2002-06-19 08:00 | 2002-06-19 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18516 | AMA | WOODWARD 3 | ALL | ESD | 2002-06-19 09:00 | 2002-06-19 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
18430 | LIB | STEVENS 4 | 2 | MP2 | 2002-06-20 08:00 | 2002-06-20 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
17674 | LIB | TEXAS 2 | 7 | INSPECTION | 2002-06-24 08:00 | 2002-06-24 16:00 | 0.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
18404 | LIB | BURDETT | 4 | BORESCOPE & MAINTENANCE | 2002-07-01 07:30 | 2002-07-12 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
18409 | LIB | BURDETT | ALL | JACKET WATER PROJECT | 2002-07-01 08:00 | 2002-07-01 16:00 | 0.3 | 0 | 0 | There is no firm date for this outage yet if at all. |  |  | 0 | P
17633 | LIB | TEXAS 2 | 3 | CONTROLS PM | 2002-07-08 07:30 | 2002-07-08 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
17634 | LIB | MORTON 1 | 3 | MP2 | 2002-07-08 07:30 | 2002-07-26 16:00 | 18.4 | 0 | 0 | MP2 8 000 hour inspection. |  |  | 0 | P
18376 | AMA | BEAVER 2 | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 | 0 | 0 | Major engine (Mike White OH). |  |  | 0 | P
18431 | LIB | STEVENS 4 | 2 | SERVICE | 2002-07-10 08:00 | 2002-07-11 16:00 | 1.3 | 3 | 4 | Service & MP2. |  |  | 0 | P
17635 | LIB | TEXAS 2 | 4 | CONTROLS PM | 2002-07-15 07:30 | 2002-07-15 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
18377 | AMA | ELLIS 2 | 2 | OVERHAUL | 2002-07-15 08:00 | 2002-07-30 16:00 | 15.3 | 0 | 0 | Major compressor. |  |  | 0 | P
18440 | LIB | STEVENS 4 | 1 | MP2 | 2002-07-17 08:00 | 2002-07-17 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18515 | AMA | WOODWARD 2 | ALL | ESD | 2002-07-17 09:00 | 2002-07-17 11:00 | 0.1 | 0 | 0 | Annual ESD. |  |  | 0 | P
18405 | LIB | BURDETT | 5 | BORESCOPE & MAINTENANCE | 2002-07-22 07:30 | 2002-08-02 16:00 | 11.4 | 0 | 0 | Borescope and minor maintenance. |  |  | 0 | P
17677 | LIB | TEXAS 2 | 6 | INSPECTION | 2002-07-22 08:00 | 2002-07-22 16:00 | 0.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17780 | LIB | STEVENS 2 | 7 | SERVICE | 2002-07-23 08:00 | 2002-07-23 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1234 HP |  |  | 0 | P
17675 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-07-30 08:00 | 2002-07-30 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
18378 | AMA | WOODWARD 1 | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-08-30 16:00 | 29.3 | 0 | 0 | Major Engine. |  |  | 0 | P
17636 | LIB | TEXAS 2 | 5 | CONTROLS PM | 2002-08-05 07:30 | 2002-08-05 16:00 | 0.4 | 0 | 0 | Controls PM |  |  | 0 | P
18379 | LIB | STEVENS 2 | 8 | OVERHAUL | 2002-08-10 08:00 | 2002-08-30 16:00 | 20.3 | 0 | 0 | Compressor overhaul. |  |  | 0 | P
18406 | LIB | BURDETT | 6 | BORESCOPE & MAINTENANCE | 2002-08-12 07:30 | 2002-08-30 16:00 | 18.4 | 0 | 0 | Possible overhaul- ECS other wise Borescope & minor maintenance. |  |  | 0 | P
18441 | LIB | STEVENS 4 | 1 | MP2 | 2002-08-14 08:00 | 2002-08-14 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18432 | LIB | STEVENS 4 | 2 | MP2 | 2002-08-15 08:00 | 2002-08-15 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
17669 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-08-27 08:00 | 2002-08-27 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
18380 | AMA | BEAVER 6 | 1 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 | 0 | 0 | Major Engine & compressor. |  |  | 0 | P
18381 | AMA | WOODWARD 2 | 4 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18442 | LIB | STEVENS 4 | 1 | SERVICE | 2002-09-11 08:00 | 2002-09-12 16:00 | 1.3 | 3.5 | 4.7 | Service and MP2 tasks. |  |  | 0 | P
18382 | AMA | WOODWARD 3 | 4 | OVERHAUL | 2002-09-15 08:00 | 2002-09-30 16:00 | 15.3 | 0 | 0 | Major Compressor. |  |  | 0 | P
17678 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-09-18 08:00 | 2002-09-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
18433 | LIB | STEVENS 4 | 2 | MP2 | 2002-09-26 08:00 | 2002-09-26 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
18314 | LIB | HUGOTON | 16 | SERVICE & MAINTENANCE | 2002-10-08 08:00 | 2002-10-08 16:00 | 0.3 | 0 | 0 | Service and maintenance. |  |  | 0 | P
17817 | LIB | STEVENS 2 | 6 | MP2 | 2002-10-09 08:00 | 2002-10-09 16:00 | 0.3 | 0 | 0 | MP2 Tasks. 1234 HP |  |  | 0 | P
17643 | LIB | MORTON 6 | 2 | CONTROLS PM | 2002-10-14 07:30 | 2002-10-16 16:00 | 2.4 | 0 | 0 | Controls PM |  |  | 0 | P
18102 | LIB | HUGOTON | 17 | SERVICE | 2002-10-15 08:00 | 2002-10-15 14:00 | 0.3 | 0 | 0 | Service and maintenance. 1800 HP |  |  | 0 | P
18384 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-10-15 08:00 | 2002-10-30 16:00 | 15.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18385 | AMA | ELLIS 1 | 1 | OVERHAUL | 2002-10-15 08:00 | 2002-11-15 16:00 | 31.3 | 0 | 0 | Major Engine. |  |  | 0 | P
18443 | LIB | STEVENS 4 | 1 | MP2 | 2002-10-16 08:00 | 2002-10-16 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18434 | LIB | STEVENS 4 | 2 | MP2 | 2002-10-17 08:00 | 2002-10-17 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
17670 | LIB | TEXAS 1 | 2 | INSPEC TION | 2002-10-21 08:00 | 2002-10-25 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
18386 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-30 16:00 | 29.3 | 0 | 0 | Major Compressor. |  |  | 0 | P
17882 | LIB | STEVENS 4 | 1 | SERVICE | 2002-11-05 08:00 | 2002-11-06 16:00 | 1.3 | 0 | 0 | Panel S/D & PM MP 2. |  |  | 0 | P
17889 | LIB | STEVENS 4 | 3 | SERVICE | 2002-11-06 08:00 | 2002-11-06 20:00 | 0.5 | 0 | 0 | Panel S/D & MP 2. |  |  | 0 | P
17885 | LIB | STEVENS 4 | 2 | SERVICE | 2002-11-13 08:00 | 2002-11-14 16:00 | 1.3 | 0 | 0 | Service unit panel S/D & MP 2. |  |  | 0 | P
17644 | LIB | MORTON 1 | 3 | CONTROLS PM | 2002-12-02 07:30 | 2002-12-06 16:00 | 4.4 | 0 | 0 | Controls PM |  |  | 0 | P
17754 | LIB | TATE | 10 | INSPECTION | 2002-12-02 08:00 | 2002-12-13 16:00 | 11.3 | 0 | 0 | Unit inspection. |  |  | 0 | P
17773 | LIB | STEVENS 2 | 3 | SERVICE | 2002-12-04 08:00 | 2002-12-04 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 1324 HP |  |  | 0 | P
17788 | LIB | STEVENS 2 | 8 | SERVICE | 2002-12-05 08:00 | 2002-12-05 16:00 | 0.3 | 0 | 0 | Service unit plus panel board S/D & PM. 764 HP |  |  | 0 | P
18047 | LIB | FINNEY 3 | 1 | MAINTENANCE | 2002-12-06 08:00 | 2002-12-06 16:00 | 0.3 | 0 | 0 | Scheduled maintenance - work orders & DET list. |  |  | 0 | P
18444 | LIB | STEVENS 4 | 1 | MP2 | 2002-12-11 08:00 | 2002-12-11 20:00 | 0.5 | 3.5 | 1.8 | MP2 tasks. |  |  | 0 | P
18435 | LIB | STEVENS 4 | 2 | MP2 | 2002-12-12 08:00 | 2002-12-12 20:00 | 0.5 | 3 | 1.5 | MP2 tasks. |  |  | 0 | P
17755 | LIB | TATE | 11 | INSPECTION | 2002-12-16 08:00 | 2002-12-20 16:00 | 4.3 | 0 | 0 | Unit inspection. |  |  | 0 | P