## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 26, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 18:00 | 1.4 |  | OPS |  | 100 | 141.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
2 | 18510 | MID | SPRAYBERRY | 9 | BEARING INSPECTION | 2002-03-18 08:00 | 2002-04-15 16:00 | 28.3 |  | OPS |  | 0 | 0 | Check main bearings rod bearings and compressor bearings. |  |  |  | 0 | P | N | N
3 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
4 | 18483 | MID | WT-2 | ALL | SCRUBBER WORK | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 |  | OPS |  | 300 | 400 | Replacing a 12" valve on #1 scrubber and repair the internal piping to #1 scrubber. |  |  |  | 0 | P | N | N
5 | 18383 | MID | WT-2 | 201 | OVERHAUL | 2002-09-15 08:00 | 2002-10-20 16:00 | 35.3 |  | OPS |  | 0 | 0 | Compressor OH. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 26, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 18:00 | 1.4 |  | OPS |  | 100 | 141.7 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. |  |  |  | 0 | P | N | N
2 | 18510 | MID | SPRAYBERRY | 9 | BEARING INSPECTION | 2002-03-18 08:00 | 2002-04-15 16:00 | 28.3 |  | OPS |  | 0 | 0 | Check main bearings rod bearings and compressor bearings. |  |  |  | 0 | P | N | N
3 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 280 | 93.3 | Annual ESD and maintenance. |  |  |  | 0 | P | N | N
4 | 18483 | MID | WT-2 | ALL | SCRUBBER WORK | 2002-03-19 08:00 | 2002-03-20 16:00 | 1.3 |  | OPS |  | 300 | 400 | Replacing a 12" valve on #1 scrubber and repair the internal piping to #1 scrubber. |  |  |  | 0 | P | N | N
5 | 18383 | MID | WT-2 | 201 | OVERHAUL | 2002-09-15 08:00 | 2002-10-20 16:00 | 35.3 |  | OPS |  | 0 | 0 | Compressor OH. |  |  |  | 0 | P | N | N