## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Minneapolis Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 26, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18399 | MIN | ALEXANDRIA | 1 | ANNUAL ESD | 2002-06-21 11:00 | 2002-06-21 14:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. There should be no flow affect this time of year. |  |  |  | 0 | P | N | N
2 | 18361 | MIN | CARLTON | ALL | ANNUAL ESD | 2002-06-11 08:00 | 2002-06-11 15:30 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
3 | 17153 | MIN | CARLTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Cooper 12-V250 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
4 | 18298 | MIN | CHATFIELD | ALL | ESD | 2002-11-08 08:00 | 2002-11-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
5 | 18296 | MIN | FAIRBAULT | ALL | ESD | 2002-10-09 08:00 | 2002-10-09 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
6 | 17157 | MIN | FARMINGTON | 4 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT606 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
7 | 17156 | MIN | FARMINGTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS48 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 18190 | MIN | GARNER | LNG | REFRIGERANT COMPRESSOR | 2001-12-04 08:00 | 2002-04-30 16:00 | 147.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is being shipped to York International for repairs. York is estimating an 8 week turnaround if there are no problems. |  | 2001-12-04 08:00 |  | 0 | U | N | N
9 | 18273 | MIN | HUGO | 1 | ANNUAL ESD | 2002-07-18 12:30 | 2002-07-19 14:30 | 1.1 |  | OPS |  | 0 | 0 | Annual ESD training and testing station ESD system will be tested with blowoff caps on. Need to perform routine maintenance on the 19" and will be ready for service at 14:30. |  |  |  | 0 | P | N | N
10 | 18297 | MIN | LACRESCENT | ALL | ESD | 2002-11-07 08:00 | 2002-11-07 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
11 | 18518 | MIN | NORTH BRANCH | BUFFALO B/L | BUFFALO 4 BLOCK VALVE RELOCATE | 2002-04-22 08:00 | 2002-04-22 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67101BYB01.1 on the 4" Buffalo B/L at M.P. 6.812 and install new block valve setting. The pressure will reduced to 500-550 psig to allow proper seating of the stopples. |  |  |  | 0 | P | N | N
12 | 18519 | MIN | NORTH BRANCH | BUFFALO 6 BLOCK | BUFFALO 6 BLOCK VALVE RELOCATE | 2002-04-23 08:00 | 2002-04-23 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67102BYB011.1 on the 6" B/L at M.P. 6.818 and install new 6" spool piece. Reduce pressure to 500-550 psig to allow proper seating of stopples. |  |  |  | 0 | P | N | N
13 | 18274 | MIN | NORTH BRANCH | ALL | ANNUAL ESD | 2002-07-18 08:00 | 2002-07-25 12:00 | 7.2 |  | OPS |  | 0 | 0 | Annual ESD Training and Testing O-Rring replacement on check valves on compressor units General maintenance leak repairs etc. (Neighboring Stations may be need to carry the load while North Branch is down). |  |  |  | 0 | P | N | N
14 | 18295 | MIN | OWATONNA | ALL | ESD TEST | 2002-10-08 08:00 | 2002-10-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
15 | 18398 | MIN | PIERZ | 1 | ANNUAL ESD | 2002-08-23 11:00 | 2002-08-23 14:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. This unit is not critical this time of year. There will be no flow affect. |  |  |  | 0 | P | N | N
16 | 18462 | MIN | VENTURA | ALL | ANNUAL ESD | 2002-06-06 08:00 | 2002-06-06 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
17 | 18269 | MIN | WRENSHALL | SUCTION VALVES | REPLACE SUCTON VALVES | 2002-06-01 08:00 | 2002-08-15 16:00 | 75.3 |  | OPS |  | 0 | 0 | Replace suction valves on all LNG pumps and check valve on g-601b lng PUMP. Will not be able to Vaporize for about 10 weeks do to warming lines and replacing suction valves. |  |  |  | 0 | P | N | N
18 | 18270 | MIN | WRENSHALL | ESD | ESD TEST | 2002-06-05 07:00 | 2002-06-05 10:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. Will affect LNG plant only. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Minneapolis Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 26, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18399 | MIN | ALEXANDRIA | 1 | ANNUAL ESD | 2002-06-21 11:00 | 2002-06-21 14:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. There should be no flow affect this time of year. |  |  |  | 0 | P | N | N
2 | 18361 | MIN | CARLTON | ALL | ANNUAL ESD | 2002-06-11 08:00 | 2002-06-11 15:30 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
3 | 17153 | MIN | CARLTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Cooper 12-V250 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
4 | 18298 | MIN | CHATFIELD | ALL | ESD | 2002-11-08 08:00 | 2002-11-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
5 | 18296 | MIN | FAIRBAULT | ALL | ESD | 2002-10-09 08:00 | 2002-10-09 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
6 | 17157 | MIN | FARMINGTON | 4 | OVERHAUL | 2002-06-03 08:00 | 2002-06-28 16:00 | 25.3 |  | OPS |  | 0 | 0 | Top end overhaul on an Ingersoll Rand KVT606 based on analysis and run time hours. Unit will have heads removed inspected and rebuilt to OEM standards. |  |  |  | 0 | P | N | N
7 | 17156 | MIN | FARMINGTON | 2 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS48 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
8 | 18190 | MIN | GARNER | LNG | REFRIGERANT COMPRESSOR | 2001-12-04 08:00 | 2002-04-30 16:00 | 147.3 |  | OPS |  | 0 | 0 | Refrigerant compressor is being shipped to York International for repairs. York is estimating an 8 week turnaround if there are no problems. |  | 2001-12-04 08:00 |  | 0 | U | N | N
9 | 18273 | MIN | HUGO | 1 | ANNUAL ESD | 2002-07-18 12:30 | 2002-07-19 14:30 | 1.1 |  | OPS |  | 0 | 0 | Annual ESD training and testing station ESD system will be tested with blowoff caps on. Need to perform routine maintenance on the 19" and will be ready for service at 14:30. |  |  |  | 0 | P | N | N
10 | 18297 | MIN | LACRESCENT | ALL | ESD | 2002-11-07 08:00 | 2002-11-07 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
11 | 18518 | MIN | NORTH BRANCH | BUFFALO B/L | BUFFALO 4 BLOCK VALVE RELOCATE | 2002-04-22 08:00 | 2002-04-22 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67101BYB01.1 on the 4" Buffalo B/L at M.P. 6.812 and install new block valve setting. The pressure will reduced to 500-550 psig to allow proper seating of the stopples. |  |  |  | 0 | P | N | N
12 | 18519 | MIN | NORTH BRANCH | BUFFALO 6 BLOCK | BUFFALO 6 BLOCK VALVE RELOCATE | 2002-04-23 08:00 | 2002-04-23 16:00 | 0.3 |  | OPS |  | 0 | 0 | Remove existing block valve setting 67102BYB011.1 on the 6" B/L at M.P. 6.818 and install new 6" spool piece. Reduce pressure to 500-550 psig to allow proper seating of stopples. |  |  |  | 0 | P | N | N
13 | 18274 | MIN | NORTH BRANCH | ALL | ANNUAL ESD | 2002-07-18 08:00 | 2002-07-25 12:00 | 7.2 |  | OPS |  | 0 | 0 | Annual ESD Training and Testing O-Rring replacement on check valves on compressor units General maintenance leak repairs etc. (Neighboring Stations may be need to carry the load while North Branch is down). |  |  |  | 0 | P | N | N
14 | 18295 | MIN | OWATONNA | ALL | ESD TEST | 2002-10-08 08:00 | 2002-10-08 12:00 | 0.2 |  | OPS |  | 0 | 0 | ESD testing. |  |  |  | 0 | P | N | N
15 | 18398 | MIN | PIERZ | 1 | ANNUAL ESD | 2002-08-23 11:00 | 2002-08-23 14:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. This unit is not critical this time of year. There will be no flow affect. |  |  |  | 0 | P | N | N
16 | 18462 | MIN | VENTURA | ALL | ANNUAL ESD | 2002-06-06 08:00 | 2002-06-06 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
17 | 18269 | MIN | WRENSHALL | SUCTION VALVES | REPLACE SUCTON VALVES | 2002-06-01 08:00 | 2002-08-15 16:00 | 75.3 |  | OPS |  | 0 | 0 | Replace suction valves on all LNG pumps and check valve on g-601b lng PUMP. Will not be able to Vaporize for about 10 weeks do to warming lines and replacing suction valves. |  |  |  | 0 | P | N | N
18 | 18270 | MIN | WRENSHALL | ESD | ESD TEST | 2002-06-05 07:00 | 2002-06-05 10:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD test. Will affect LNG plant only. |  |  |  | 0 | P | N | N