## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Dakota Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 28, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17159 | DAK | FT BUFORD | 3 | OVERHAUL | 2002-04-01 08:00 | 2002-04-26 16:00 | 25.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 17160 | DAK | FT BUFORD | 4 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
3 | 18485 | DAK | SOUTH SIOUX CITY | TEKAMAH | INSTALL ERCOFORM | 2002-07-08 08:00 | 2002-07-19 17:00 | 11.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats and construct flexible concrete revetments exposed line in the dry wash. (Tekamah B/L reduce pressure 50%). |  |  |  | 0 | P | N | N
4 | 18487 | DAK | SOUTH SIOUX CITY | HOOP/SSC A LINE | INSTALL ERCOFORM | 2002-07-22 08:00 | 2002-07-26 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC A line reduce pressure 50% or 250#). M.P. 9.5 |  |  |  | 0 | P | N | N
5 | 18486 | DAK | SOUTH SIOUX CITY | HOOP/SSC B LINE | INSTALL ERCOFORM | 2002-07-29 08:00 | 2002-08-02 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC B line M570B reduce pressure 80% or 500#). M.P. 9.6 |  |  |  | 0 | P | N | N
6 | 18489 | DAK | SOUTH SIOUX CITY | HOOP/SSC C LINE | INSTALL ERCOFORM | 2002-08-05 08:00 | 2002-08-09 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC C line M570C reduce pressure 80% or 778#). M.P. 9.6 |  |  |  | 0 | P | N | N
7 | 18463 | DAK | SOUTH SIOUX CITY | WAYNE A&J | INSTALL ERCOFORM MATS | 2002-08-12 08:00 | 2002-08-16 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. Reduce operation pressure 50%. (Wayne A&J NEB57001&57002) M.P. 16 |  |  |  | 0 | P | N | N
8 | 18490 | DAK | SOUTH SIOUX CITY | SSC/PAUL B LINE | INSTALL ERCOFORM | 2002-08-19 08:00 | 2002-08-23 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (SSC/PAUL B line IAM560B) M.P. 5.21 reduce pressure to 80% or 640#. |  |  |  | 0 | P | N | N
9 | 18488 | DAK | SOUTH SIOUX CITY | SSC/PAUL B LINE | INSTALL ERCOFORM | 2002-08-26 08:00 | 2002-08-30 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (SSC/PAUL B line IAM560B reduce pressure 80% or 640#). M.P. 17.23 |  |  |  | 0 | P | N | N
10 | 18491 | DAK | SOUTH SIOUX CITY | HOOP/SSC A LINE | INSTALL ERCOFORM | 2002-09-02 08:00 | 2002-09-06 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC A line NEM570A) M.P. 43.88 reduce pressure to 50% or 250#). |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Dakota Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted February 28, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17159 | DAK | FT BUFORD | 3 | OVERHAUL | 2002-04-01 08:00 | 2002-04-26 16:00 | 25.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
2 | 17160 | DAK | FT BUFORD | 4 | OVERHAUL | 2002-05-06 08:00 | 2002-05-17 16:00 | 11.3 |  | OPS |  | 0 | 0 | Superior 8GTLA engine exchange based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
3 | 18485 | DAK | SOUTH SIOUX CITY | TEKAMAH | INSTALL ERCOFORM | 2002-07-08 08:00 | 2002-07-19 17:00 | 11.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats and construct flexible concrete revetments exposed line in the dry wash. (Tekamah B/L reduce pressure 50%). |  |  |  | 0 | P | N | N
4 | 18487 | DAK | SOUTH SIOUX CITY | HOOP/SSC A LINE | INSTALL ERCOFORM | 2002-07-22 08:00 | 2002-07-26 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC A line reduce pressure 50% or 250#). M.P. 9.5 |  |  |  | 0 | P | N | N
5 | 18486 | DAK | SOUTH SIOUX CITY | HOOP/SSC B LINE | INSTALL ERCOFORM | 2002-07-29 08:00 | 2002-08-02 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC B line M570B reduce pressure 80% or 500#). M.P. 9.6 |  |  |  | 0 | P | N | N
6 | 18489 | DAK | SOUTH SIOUX CITY | HOOP/SSC C LINE | INSTALL ERCOFORM | 2002-08-05 08:00 | 2002-08-09 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC C line M570C reduce pressure 80% or 778#). M.P. 9.6 |  |  |  | 0 | P | N | N
7 | 18463 | DAK | SOUTH SIOUX CITY | WAYNE A&J | INSTALL ERCOFORM MATS | 2002-08-12 08:00 | 2002-08-16 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. Reduce operation pressure 50%. (Wayne A&J NEB57001&57002) M.P. 16 |  |  |  | 0 | P | N | N
8 | 18490 | DAK | SOUTH SIOUX CITY | SSC/PAUL B LINE | INSTALL ERCOFORM | 2002-08-19 08:00 | 2002-08-23 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (SSC/PAUL B line IAM560B) M.P. 5.21 reduce pressure to 80% or 640#. |  |  |  | 0 | P | N | N
9 | 18488 | DAK | SOUTH SIOUX CITY | SSC/PAUL B LINE | INSTALL ERCOFORM | 2002-08-26 08:00 | 2002-08-30 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (SSC/PAUL B line IAM560B reduce pressure 80% or 640#). M.P. 17.23 |  |  |  | 0 | P | N | N
10 | 18491 | DAK | SOUTH SIOUX CITY | HOOP/SSC A LINE | INSTALL ERCOFORM | 2002-09-02 08:00 | 2002-09-06 17:00 | 4.4 |  | OPS |  | 0 | 0 | Install Ercoform articulating grout mats over exposed line in small creek. (Hoop/SSC A line NEM570A) M.P. 43.88 reduce pressure to 50% or 250#). |  |  |  | 0 | P | N | N