## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 14, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17145 | ALB | ATOKA 1 | 737 | OVERHAUL | 2002-09-02 08:00 | 2002-09-20 16:00 | 18.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
2 | 17146 | ALB | ATOKA 1 | 761 | OVERHAUL | 2002-09-09 08:00 | 2002-09-13 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 | P | N | N
3 | 17142 | ALB | ATOKA 1 | 719 | OVERHAUL | 2002-09-16 08:00 | 2002-09-20 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
4 | 18591 | ALB | ATOKA 2 | 760 | UNIT MAINTENANCE | 2002-03-13 08:00 | 2002-03-13 12:00 | 0.2 |  | OPS |  | 0 | 0 | They have some unit maintenance they need to do on the unit. |  |  |  | 0 | U | N | N
5 | 18581 | ALB | ATOKA 3 | 762 | REPAIR EXHAUST MANIFOLD | 2002-03-12 06:00 | 2002-03-12 18:00 | 0.5 |  | OPS |  | 0 | 0 | Need repair exhaust manifold. Installing new exhaust flange and re-torque heads on unit 762. Shouldn't affect flow for the day. |  |  |  | 0 | P | N | N
6 | 18354 | ALB | BISTI | 1 | ESD & STATION TURN AROUND | 2002-04-11 07:00 | 2002-04-12 07:00 | 1 |  | OPS |  | 150 | 150 | ESD & Station turn around. Unit down for an estimated 24 hours for unit maintenance Sub station & PCR building maintenance also valve maintenance. |  |  |  | 0 | P | N | N
7 | 18355 | ALB | BLOOMFIELD | ALL | ESD & STATION TURN AROUND | 2002-04-08 09:00 | 2002-04-11 09:00 | 3 |  | OPS |  | 225 | 675 | ESD and Station turn around.(3 day outage) 1st Day- ESD test relief valves safety devices valve maint. water wash #3. 2nd Day- Unit 1 & 2 down for maintenance water wash and safety devices. 3rd Day- Do maintenance on #4 also Sub-station maintenance. |  |  |  | 0 | P | N | N
8 | 18390 | ALB | GALLOP | 1 | ESD & SUBSTATION MAINTENACE | 2002-04-11 09:00 | 2002-04-13 09:00 | 2 |  | OPS |  | 150 | 300 | Annual ESD test change unit filters Inspect VFD & change module test safety devices Install new seal gas pre-filter and Electrical substation maintenance. |  |  |  | 0 | P | N | N
9 | 18545 | ALB | IGNACIO TO BLANCO | QUESTAR I/C | QUESTAR TIE-IN | 2002-04-02 09:00 | 2002-04-03 09:00 | 1 |  | OPS |  | 205 | 205 | Pipeline outage from Ignacio to Blanco to tie-in Questar I/C. |  |  |  | 0 | P | N | N
10 | 18360 | ALB | LAPLATA | ALL | ANNUAL TURN AROUND & FUEL VALVE CHANGE | 2002-04-02 09:00 | 2002-04-06 09:00 | 4 |  | OPS |  | 500 | 2000 | Annual turn around and fuel valve change out. ESD Safety Devices Water Wash Filters Valves and over all maintenance on both units. |  |  |  | 0 | P | N | N
11 | 18503 | ALB | LOOPLINE | 5 TO 4 | 8 EXCAVATIONS | 2002-04-08 08:00 | 2002-04-10 16:00 | 2.3 |  | OPS |  | 0 | 0 | 8 excavations on the loopline 5-4. |  |  |  | 0 | P | N | N
12 | 18501 | ALB | MAINLINE | 8 TO 7 | 2-4 PITS & 3 DENTS | 2002-04-02 08:00 | 2002-04-05 16:00 | 3.3 |  | OPS |  | 0 | 0 | 2 to 4 pits and 3 dents that have to be looked at. 8-7. (Verification digs) |  |  |  | 0 | P | N | N
13 | 18502 | ALB | MAINLINE | 5 TO 4 | 5 EXCAVATIONS | 2002-04-08 08:00 | 2002-04-10 16:00 | 2.3 |  | OPS |  | 0 | 0 | 5 excavations on the mainline 5-4. |  |  |  | 0 | P | N | N
14 | 18500 | ALB | MAINLINE | 7 TO 6 | 16 EXCAVATIONS | 2002-04-13 08:00 | 2002-04-20 16:00 | 7.3 |  | OPS |  | 0 | 0 | 16 pits to be fixed on the mainline section 7-6. |  |  |  | 0 | P | N | N
15 | 17195 | ALB | STATION 1 | 101 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
16 | 17196 | ALB | STATION 1 | 102 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
17 | 17197 | ALB | STATION 1 | 103 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
18 | 17198 | ALB | STATION 2 | 201 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
19 | 17199 | ALB | STATION 2 | 202 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
20 | 17200 | ALB | STATION 2 | 203 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
21 | 17095 | ALB | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-04-03 08:00 | 2002-04-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (Flow affect is captured in the outage on | 401). |  |  | 0 | P | N | N
22 | 17096 | ALB | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-04-07 16:00 | 2002-04-11 16:00 | 4 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (Flow affect is captured in the outage o | n 401). |  |  | 0 | P | N | N
23 | 17201 | ALB | STATION 3 | 301 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
24 | 17202 | ALB | STATION 3 | 302 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
25 | 17203 | ALB | STATION 3 | 303 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
26 | 17128 | ALB | STATION 4 | 401 | OVERHAUL | 2002-04-01 09:00 | 2002-04-13 09:00 | 12 |  | OPS |  | 150 | 1800 | ESD the staton for our annual test. Start unit 402 and 403 back up. 401 will have all main bearing 2 pistons and liners changed both aftercoolers all fuel valves lifters spark plugs fin fan motors compressor valves compressor rods and pistons. |  |  |  | 0 | P | N | N
27 | 17129 | ALB | STATION 4 | 402 | OVERHAUL | 2002-04-13 09:00 | 2002-04-24 09:00 | 11 |  | OPS |  | 150 | 1650 | Change 2 piston and cylinders both aftercoolers all fuel valves lifters spark plugs finfan motors compressor valves compressor rods and pistons packing and pocket loaders calibrate and check all safety devices. |  |  |  | 0 | P | N | N
28 | 17130 | ALB | STATION 4 | 403 | OVERHAUL | 2002-04-24 09:00 | 2002-05-05 09:00 | 11 |  | OPS |  | 150 | 1650 | Change 2 piston and cylinders both aftercoolers all fuel valves lifters spark plugs finfan motors compressor valves compressor rods and pistons packing and pocket loaders calibrate and check all safety devices. |  |  |  | 0 | P | N | N
29 | 18317 | ALB | STATION 4 | 421 | OVERHAUL | 2002-05-04 08:00 | 2002-05-07 16:00 | 3.3 |  | OPS |  | 0 | 0 | Overhaul. |  |  |  | 0 | P | N | N
30 | 18318 | ALB | STATION 4 | 422 | OVERHAUL | 2002-05-08 08:00 | 2002-05-10 16:00 | 2.3 |  | OPS |  | 0 | 0 | Overhaul. |  |  |  | 0 | P | N | N
31 | 17131 | ALB | STATION 5 | 501 PHFU | OVERHAUL | 2002-05-01 08:00 | 2002-05-25 16:00 | 24.3 |  | OPS |  | 0 | 0 | Contractor will remove and replace both left and right bank upper blocks. Block replacement will result in a complete upper end overhaul. |  |  |  | 0 | P | N | N
32 | 17132 | ALB | STATION 5 | 502 | OVERHAUL | 2002-11-01 08:00 | 2002-11-11 16:00 | 10.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold system and replace with new exhaust manifold system. Also replace turbocharger and turbo coolers with the spare turbo and coolers at the station. |  |  |  | 0 | P | N | N
33 | 18311 | ALB | STATION 6 | 602 PHFU | REMOVE UNLOADERS & TURBO COOLER | 2002-01-16 08:00 | 2002-05-31 16:00 | 135.3 |  | OPS |  | 0 | 0 | Remove unloaders from all compressors and 1 turbo-cooler to be sent in and rebuild to use at Station 4 during their outage. When Station 4 is complete rebuilt equipment will be re-installed at Station 6 602. (This unit has been in PHFU). |  | 2002-01-16 08:00 |  | 0 | P | N | N
34 | 17133 | ALB | STATION 6 | 601 | VALVE OVERHAUL | 2002-09-02 08:00 | 2002-09-04 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
35 | 17134 | ALB | STATION 6 | 602 PHFU | VALVE OVERHAUL | 2002-09-05 08:00 | 2002-09-08 16:00 | 3.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
36 | 17135 | ALB | STATION 6 | 603 | VALVE OVERHAUL | 2002-09-09 08:00 | 2002-09-11 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
37 | 17138 | ALB | STATION 7 | 721 | OVERHAUL | 2002-03-11 08:00 | 2002-04-06 16:00 | 26.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete upper and lower end overhaul. Contractor will remove generator and it will be sent in for complete restoration. |  | 2002-03-11 08:00 |  | 0 | P | N | N
38 | 17136 | ALB | STATION 7 | 701 PHFU | OVERHAUL | 2002-10-28 08:00 | 2002-11-09 16:00 | 12.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold and replace with new exhaust manifold system. Both intake manifolds will also be replaced. Intake manifolds will be supplied by Enron. Unit main frame bolts will be checked by ultrasound. Bolts will be rep | laced if cracked or broken. |  |  | 0 | P | N | N
39 | 17137 | ALB | STATION 7 | 702 PHFU | OVERHAUL | 2002-11-10 08:00 | 2002-11-13 16:00 | 3.3 |  | OPS |  | 0 | 0 | Contractor will remove left and right intake manifolds and send them to Coopers shop in Odessa for repairs. Upon completion contractor will reinstall. |  |  |  | 0 | P | N | N
40 | 17139 | ALB | STATION 8 | 801 | OVERHAUL | 2002-06-01 08:00 | 2002-06-25 16:00 | 24.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. The accessory drive chain and sprocket will replaced due to wear. Contractor will perform a complete overhaul including pulling #3 doghous | e to replace gasket. All valves will be sent in for reconditioning. |  |  | 0 | P | N | N
41 | 17140 | ALB | STATION 8 | 802 | OVERHAUL | 2002-10-01 08:00 | 2002-10-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. Contractor will perform a complete overhaul and valves will be sent in for reconditioning. |  |  |  | 0 | P | N | N
42 | 18492 | ALB | TRANSCOLORADO | I/C | CHANGE TURBINE METER | 2002-03-19 08:00 | 2002-03-19 10:00 | 0.1 |  | OPS |  | 0 | 0 | Change out the 12" turbine meter and inspect the tube. We should be able to make up the volumes for the day. |  |  |  | 0 | P | N | N
43 | 17721 | ALB | WT-1 | 102 | BEARING REPLACEMENT | 2002-10-02 08:00 | 2002-10-15 16:00 | 13.3 |  | OPS |  | 0 | 0 | Main bearing and seal replacement. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Albuquerque Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 14, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17145 | ALB | ATOKA 1 | 737 | OVERHAUL | 2002-09-02 08:00 | 2002-09-20 16:00 | 18.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
2 | 17146 | ALB | ATOKA 1 | 761 | OVERHAUL | 2002-09-09 08:00 | 2002-09-13 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul. Replace rings packing R&R all compressor valves inspect cylinders for wear and check rod and main bearings. |  |  |  | 0 | P | N | N
3 | 17142 | ALB | ATOKA 1 | 719 | OVERHAUL | 2002-09-16 08:00 | 2002-09-20 16:00 | 4.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete compressor overhaul replace rings packing R&R all valves inspect cylinders for wear and check rod and main bearings. (Flow affect is zero but suction comes up some). |  |  |  | 0 | P | N | N
4 | 18591 | ALB | ATOKA 2 | 760 | UNIT MAINTENANCE | 2002-03-13 08:00 | 2002-03-13 12:00 | 0.2 |  | OPS |  | 0 | 0 | They have some unit maintenance they need to do on the unit. |  |  |  | 0 | U | N | N
5 | 18581 | ALB | ATOKA 3 | 762 | REPAIR EXHAUST MANIFOLD | 2002-03-12 06:00 | 2002-03-12 18:00 | 0.5 |  | OPS |  | 0 | 0 | Need repair exhaust manifold. Installing new exhaust flange and re-torque heads on unit 762. Shouldn't affect flow for the day. |  |  |  | 0 | P | N | N
6 | 18354 | ALB | BISTI | 1 | ESD & STATION TURN AROUND | 2002-04-11 07:00 | 2002-04-12 07:00 | 1 |  | OPS |  | 150 | 150 | ESD & Station turn around. Unit down for an estimated 24 hours for unit maintenance Sub station & PCR building maintenance also valve maintenance. |  |  |  | 0 | P | N | N
7 | 18355 | ALB | BLOOMFIELD | ALL | ESD & STATION TURN AROUND | 2002-04-08 09:00 | 2002-04-11 09:00 | 3 |  | OPS |  | 225 | 675 | ESD and Station turn around.(3 day outage) 1st Day- ESD test relief valves safety devices valve maint. water wash #3. 2nd Day- Unit 1 & 2 down for maintenance water wash and safety devices. 3rd Day- Do maintenance on #4 also Sub-station maintenance. |  |  |  | 0 | P | N | N
8 | 17148 | ALB | CRAWFORD | 751 | OVERHAUL | 2002-03-05 09:00 | 2002-03-11 09:00 | 6 |  | OPS |  | 0 | 0 | Complete UX turbine exchange. Contractor will remove old turbine and install and align new reconditioned turbine. (The flow affect is 30 mmcf from capacity on 3/6 gas day). Capacity is around 60 mmcf. |  | 2002-03-05 09:00 |  | 0 | P | N | N
9 | 18243 | ALB | CRAWFORD | CONTROL VALVE | INSTALL CONTROL VALVE | 2002-03-05 09:00 | 2002-03-11 09:00 | 6 |  | OPS |  | 30 | 180 | Installing two elbows in the 16" line in order to put in the flow control valve for existing Duke I/C inside the Crawford compressor station. (The station would need to be down for this work). |  | 2002-03-05 09:00 |  | 0 | P | N | N
10 | 18390 | ALB | GALLOP | 1 | ESD & SUBSTATION MAINTENACE | 2002-04-11 09:00 | 2002-04-13 09:00 | 2 |  | OPS |  | 150 | 300 | Annual ESD test change unit filters Inspect VFD & change module test safety devices Install new seal gas pre-filter and Electrical substation maintenance. |  |  |  | 0 | P | N | N
11 | 18545 | ALB | IGNACIO TO BLANCO | QUESTAR I/C | QUESTAR TIE-IN | 2002-04-02 09:00 | 2002-04-03 09:00 | 1 |  | OPS |  | 205 | 205 | Pipeline outage from Ignacio to Blanco to tie-in Questar I/C. |  |  |  | 0 | P | N | N
12 | 18360 | ALB | LAPLATA | ALL | ANNUAL TURN AROUND & FUEL VALVE CHANGE | 2002-04-02 09:00 | 2002-04-06 09:00 | 4 |  | OPS |  | 500 | 2000 | Annual turn around and fuel valve change out. ESD Safety Devices Water Wash Filters Valves and over all maintenance on both units. |  |  |  | 0 | P | N | N
13 | 18503 | ALB | LOOPLINE | 5 TO 4 | 8 EXCAVATIONS | 2002-04-08 08:00 | 2002-04-10 16:00 | 2.3 |  | OPS |  | 0 | 0 | 8 excavations on the loopline 5-4. |  |  |  | 0 | P | N | N
14 | 18501 | ALB | MAINLINE | 8 TO 7 | 2-4 PITS & 3 DENTS | 2002-04-02 08:00 | 2002-04-05 16:00 | 3.3 |  | OPS |  | 0 | 0 | 2 to 4 pits and 3 dents that have to be looked at. 8-7. (Verification digs) |  |  |  | 0 | P | N | N
15 | 18502 | ALB | MAINLINE | 5 TO 4 | 5 EXCAVATIONS | 2002-04-08 08:00 | 2002-04-10 16:00 | 2.3 |  | OPS |  | 0 | 0 | 5 excavations on the mainline 5-4. |  |  |  | 0 | P | N | N
16 | 18500 | ALB | MAINLINE | 7 TO 6 | 16 EXCAVATIONS | 2002-04-13 08:00 | 2002-04-20 16:00 | 7.3 |  | OPS |  | 0 | 0 | 16 pits to be fixed on the mainline section 7-6. |  |  |  | 0 | P | N | N
17 | 17195 | ALB | STATION 1 | 101 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
18 | 17196 | ALB | STATION 1 | 102 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
19 | 17197 | ALB | STATION 1 | 103 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
20 | 17198 | ALB | STATION 2 | 201 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
21 | 17199 | ALB | STATION 2 | 202 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
22 | 17200 | ALB | STATION 2 | 203 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
23 | 17095 | ALB | STATION 3 | MAINLINE | RED ROCK TIE-IN | 2002-04-03 08:00 | 2002-04-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (Flow affect is captured in the outage on | 401). |  |  | 0 | P | N | N
24 | 17096 | ALB | STATION 3 | LOOP LINE | RED ROCK TIE-IN | 2002-04-07 16:00 | 2002-04-11 16:00 | 4 |  | OPS |  | 0 | 0 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. (Flow affect is captured in the outage o | n 401). |  |  | 0 | P | N | N
25 | 17201 | ALB | STATION 3 | 301 | SAFETY DEVICES | 2002-07-03 08:00 | 2002-07-07 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
26 | 17202 | ALB | STATION 3 | 302 | SAFETY DEVICES | 2002-07-10 08:00 | 2002-07-14 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
27 | 17203 | ALB | STATION 3 | 303 | SAFETY DEVICES | 2002-07-17 08:00 | 2002-07-21 16:00 | 4.3 |  | OPS |  | 0 | 0 | Safety devices and maintenance. |  |  |  | 0 | P | N | N
28 | 18304 | ALB | STATION 4 | 403 | BEARING INSPECTION | 2002-03-10 16:00 | 2002-03-12 16:00 | 2 |  | OPS |  | 120 | 240 | Perform bearing and power cylinder inspection |  |  |  | 0 | P | N | N
29 | 17128 | ALB | STATION 4 | 401 | OVERHAUL | 2002-04-01 09:00 | 2002-04-13 09:00 | 12 |  | OPS |  | 150 | 1800 | ESD the staton for our annual test. Start unit 402 and 403 back up. 401 will have all main bearing 2 pistons and liners changed both aftercoolers all fuel valves lifters spark plugs fin fan motors compressor valves compressor rods and pistons. |  |  |  | 0 | P | N | N
30 | 17129 | ALB | STATION 4 | 402 | OVERHAUL | 2002-04-13 09:00 | 2002-04-24 09:00 | 11 |  | OPS |  | 150 | 1650 | Change 2 piston and cylinders both aftercoolers all fuel valves lifters spark plugs finfan motors compressor valves compressor rods and pistons packing and pocket loaders calibrate and check all safety devices. |  |  |  | 0 | P | N | N
31 | 17130 | ALB | STATION 4 | 403 | OVERHAUL | 2002-04-24 09:00 | 2002-05-05 09:00 | 11 |  | OPS |  | 150 | 1650 | Change 2 piston and cylinders both aftercoolers all fuel valves lifters spark plugs finfan motors compressor valves compressor rods and pistons packing and pocket loaders calibrate and check all safety devices. |  |  |  | 0 | P | N | N
32 | 18317 | ALB | STATION 4 | 421 | OVERHAUL | 2002-05-04 08:00 | 2002-05-07 16:00 | 3.3 |  | OPS |  | 0 | 0 | Overhaul. |  |  |  | 0 | P | N | N
33 | 18318 | ALB | STATION 4 | 422 | OVERHAUL | 2002-05-08 08:00 | 2002-05-10 16:00 | 2.3 |  | OPS |  | 0 | 0 | Overhaul. |  |  |  | 0 | P | N | N
34 | 17131 | ALB | STATION 5 | 501 PHFU | OVERHAUL | 2002-05-01 08:00 | 2002-05-25 16:00 | 24.3 |  | OPS |  | 0 | 0 | Contractor will remove and replace both left and right bank upper blocks. Block replacement will result in a complete upper end overhaul. |  |  |  | 0 | P | N | N
35 | 17132 | ALB | STATION 5 | 502 | OVERHAUL | 2002-11-01 08:00 | 2002-11-11 16:00 | 10.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold system and replace with new exhaust manifold system. Also replace turbocharger and turbo coolers with the spare turbo and coolers at the station. |  |  |  | 0 | P | N | N
36 | 18311 | ALB | STATION 6 | 602 PHFU | REMOVE UNLOADERS & TURBO COOLER | 2002-01-16 08:00 | 2002-05-31 16:00 | 135.3 |  | OPS |  | 0 | 0 | Remove unloaders from all compressors and 1 turbo-cooler to be sent in and rebuild to use at Station 4 during their outage. When Station 4 is complete rebuilt equipment will be re-installed at Station 6 602. (This unit has been in PHFU). |  | 2002-01-16 08:00 |  | 0 | P | N | N
37 | 17133 | ALB | STATION 6 | 601 | VALVE OVERHAUL | 2002-09-02 08:00 | 2002-09-04 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
38 | 17134 | ALB | STATION 6 | 602 PHFU | VALVE OVERHAUL | 2002-09-05 08:00 | 2002-09-08 16:00 | 3.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
39 | 17135 | ALB | STATION 6 | 603 | VALVE OVERHAUL | 2002-09-09 08:00 | 2002-09-11 16:00 | 2.3 |  | OPS |  | 0 | 0 | Contractor will remove all compressor valves and install all new reconditioned valves. Compressor valves will be sent to VMS for R&R. Upon return valve will be i nstalled in the next unit. |  |  |  | 0 | P | N | N
40 | 17138 | ALB | STATION 7 | 721 | OVERHAUL | 2002-03-11 08:00 | 2002-04-06 16:00 | 26.3 |  | OPS |  | 0 | 0 | Contractor will perform a complete upper and lower end overhaul. Contractor will remove generator and it will be sent in for complete restoration. |  | 2002-03-11 08:00 |  | 0 | P | N | N
41 | 17136 | ALB | STATION 7 | 701 PHFU | OVERHAUL | 2002-10-28 08:00 | 2002-11-09 16:00 | 12.3 |  | OPS |  | 0 | 0 | Contractor will remove the old exhaust manifold and replace with new exhaust manifold system. Both intake manifolds will also be replaced. Intake manifolds will be supplied by Enron. Unit main frame bolts will be checked by ultrasound. Bolts will be rep | laced if cracked or broken. |  |  | 0 | P | N | N
42 | 17137 | ALB | STATION 7 | 702 PHFU | OVERHAUL | 2002-11-10 08:00 | 2002-11-13 16:00 | 3.3 |  | OPS |  | 0 | 0 | Contractor will remove left and right intake manifolds and send them to Coopers shop in Odessa for repairs. Upon completion contractor will reinstall. |  |  |  | 0 | P | N | N
43 | 17139 | ALB | STATION 8 | 801 | OVERHAUL | 2002-06-01 08:00 | 2002-06-25 16:00 | 24.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. The accessory drive chain and sprocket will replaced due to wear. Contractor will perform a complete overhaul including pulling #3 doghous | e to replace gasket. All valves will be sent in for reconditioning. |  |  | 0 | P | N | N
44 | 17140 | ALB | STATION 8 | 802 | OVERHAUL | 2002-10-01 08:00 | 2002-10-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | Contractor will perform a partial upper end overhaul. Six pistons and liners will be removed and replaced as needed. Contractor will perform a complete overhaul and valves will be sent in for reconditioning. |  |  |  | 0 | P | N | N
45 | 18492 | ALB | TRANSCOLORADO | I/C | CHANGE TURBINE METER | 2002-03-19 08:00 | 2002-03-19 10:00 | 0.1 |  | OPS |  | 0 | 0 | Change out the 12" turbine meter and inspect the tube. We should be able to make up the volumes for the day. |  |  |  | 0 | P | N | N
46 | 17721 | ALB | WT-1 | 102 | BEARING REPLACEMENT | 2002-10-02 08:00 | 2002-10-15 16:00 | 13.3 |  | OPS |  | 0 | 0 | Main bearing and seal replacement. |  |  |  | 0 | P | N | N