## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 19, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18461 | AMA | BEAVER 12 | 1 | SUCTION SCRUBBER | 2001-12-29 12:00 | 2002-03-22 16:00 | 83.2 |  | OPS |  | 0 | 0 | Have suction scrubber rebuilt. |  | 2001-12-29 12:00 |  | 0 | U | N | N
2 | 18362 | AMA | BEAVER 12 | 3 | OVERHAUL (ON HOLD) | 2002-03-26 13:00 | 2002-04-26 16:00 | 31.1 |  | OPS |  | 0 | 0 | Overhaul Engine & Compressors. |  |  |  | 0 | P | N | N
3 | 18528 | AMA | BEAVER 2 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 |  | OPS |  | 5 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18376 | AMA | BEAVER 2 | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major engine (Mike White OH). |  |  |  | 0 | P | N | N
5 | 18460 | AMA | BEAVER 6 | ALL | ANNUAL ESD | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
6 | 18380 | AMA | BEAVER 6 | 1 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine & compressor. |  |  |  | 0 | P | N | N
7 | 18589 | AMA | BEAVER 7 | 1 | COMPRESSOR CYLINDER | 2002-03-10 07:00 | 2002-03-22 16:00 | 12.4 |  | OPS |  | 3 | 37.1 | Unit down with a knock in the #1 compressor. Not sure what they have unitl they tear into it. |  | 2002-03-10 07:00 |  | 0 | U | N | N
8 | 18374 | AMA | BEAVER 7 | 1 | OVERHAUL (ON HOLD) | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major overhaul. |  |  |  | 0 | P | N | N
9 | 18384 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-10-15 08:00 | 2002-10-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
10 | 18386 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N
11 | 18367 | AMA | BEAVER PLANT | 12 | OVERHAUL (ON HOLD) | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major enigne & compressors. (Subject to Dynegy approval). |  |  |  | 0 | P | N | N
12 | 18369 | AMA | BEAVER PLANT | 14 | OVERHAUL | 2002-05-01 08:00 | 2002-06-01 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major engine and compressors. |  |  |  | 0 | P | N | N
13 | 18522 | AMA | BEAVER PLANT | ESD | ESD | 2002-05-02 08:00 | 2002-05-02 16:00 | 0.3 |  | OPS |  | 350 | 116.7 | Annual ESD. (7 to 8 hours). |  |  |  | 0 | P | N | N
14 | 18583 | AMA | BEAVER PLANT | B LINE ORIFICE | REMOVE ORIFICE PLATE | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 0 | 0 | They believe the orifice plate is bent on the B line measurement at Beaver. They need to remove it when Beaver has their ESD. Actual time table for the work is estimated. It could be more or less. Flow affect is Spearman volumes. Estimated(68 mmfcd). |  |  |  | 0 | P | N | N
15 | 18365 | AMA | BEAVER PLANT | 9 | OVERHAUL | 2002-07-29 08:00 | 2002-08-30 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major engine & compressors. |  |  |  | 0 | P | N | N
16 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
17 | 18607 | AMA | CANADIAN RIVER STA. | 1&3 | POWER CYLINDER LINERS | 2002-03-18 12:30 | 2002-03-27 16:00 | 9.2 |  | OPS |  | 5 | 45.8 | Four power cylinder liners leaking. Will remove all eight liners and replace gaskets. |  | 2002-03-18 12:30 |  | 0 | U | N | N
18 | 18338 | AMA | CLAUDE | 1 | ANNUAL ESD | 2002-05-14 09:00 | 2002-05-14 18:00 | 0.4 |  | OPS |  | 0 | 0 | Conducting annual ESD. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
19 | 18340 | AMA | CLAUDE | 1 | SAFETY DEVICES | 2002-10-08 09:00 | 2002-10-09 08:00 | 1 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
20 | 18555 | AMA | ELLIS 1 | 2 | 1500 HR. INSPECTION | 2002-03-21 09:00 | 2002-03-21 12:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hr Inspection. |  |  |  | 0 | U | N | N
21 | 18554 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-04-15 09:00 | 2002-04-15 11:00 | 0.1 |  | OPS |  | 2 | 0.2 | 1500 hr. Inspection. |  |  |  | 0 | U | N | N
22 | 18553 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTON | 2002-04-17 09:00 | 2002-04-17 12:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hr. Inspection. |  |  |  | 0 | U | N | N
23 | 18552 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-04-19 09:00 | 2002-04-19 11:00 | 0.1 |  | OPS |  | 2 | 0.2 | 1500 hr. inspection. |  |  |  | 0 | U | N | N
24 | 18459 | AMA | ELLIS 1 | ALL | ANNUAL ESD | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
25 | 18385 | AMA | ELLIS 1 | 1 | OVERHAUL | 2002-10-15 08:00 | 2002-11-15 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
26 | 18513 | AMA | ELLIS 2 | ALL | ESD | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
27 | 18377 | AMA | ELLIS 2 | 2 | OVERHAUL | 2002-07-15 08:00 | 2002-07-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major compressor. |  |  |  | 0 | P | N | N
28 | 18588 | AMA | ELLIS 3 | 6 | 1500 HR. INSPECTION | 2002-04-07 09:00 | 2002-04-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | 1500 hour inspection. |  |  |  | 0 | P | N | N
29 | 18261 | AMA | HEMPHILL 2 | ALL | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
30 | 18260 | AMA | HEMPHILL 3 | ALL | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
31 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
32 | 18593 | AMA | HUTCH 1 | 1 2 | RELIEF VALVE TESTING | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 |  | OPS |  | 0 | 0 | Testing the relief valves. |  |  |  | 0 | P | N | N
33 | 18505 | AMA | NORTHRUP | 1 2 | RELIEF VALVE TEST | 2002-03-19 08:00 | 2002-03-19 11:00 | 0.1 |  | OPS |  | 15 | 1.9 | Testing the the relief valves. |  |  |  | 0 | P | N | N
34 | 18524 | AMA | NORTHRUP | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 10 | 5 | Annual ESD. |  |  |  | 0 | P | N | N
35 | 18331 | AMA | P3 | ALL | SURGE CONTROL TIE-IN & ESD | 2002-03-26 08:00 | 2002-03-27 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | Annual ESD. We will need to remove some material that we are going to reuse and test it before we can make our tie-ins. (They will be able to by-pass the station to make some deliveries). |  |  |  | 0 | P | N | N
36 | 18332 | AMA | P3 | 1 | SAFETY DEVICES | 2002-04-23 08:00 | 2002-04-24 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
37 | 18371 | AMA | P3 | 1 | OVERHAUL | 2002-05-01 08:00 | 2002-05-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Exchange GP PT & AGB. |  |  |  | 0 | P | N | N
38 | 18333 | AMA | P3 | 2 | SAFETY DEVICES | 2002-05-08 08:00 | 2002-05-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
39 | 18334 | AMA | P3 | 3 | SAFETY DEVICES | 2002-05-22 08:00 | 2002-05-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
40 | 18336 | AMA | P3 | 5 | SAFETY DEVICES | 2002-06-18 08:00 | 2002-06-20 18:00 | 2.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
41 | 18335 | AMA | P3 | 4 | SAFETY DEVICES | 2002-08-22 08:00 | 2002-08-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
42 | 18339 | AMA | PAMPA | 1 | ESD & SAFETY DEVICES | 2002-04-08 08:00 | 2002-04-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Conducting annual ESD test and calibrating safety devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
43 | 18525 | AMA | PERRYTON BARLOW | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 7 | 3.5 | Annual ESD. |  |  |  | 0 | P | N | N
44 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
45 | 18455 | AMA | ROGER MILLS | ALL | RELIEF VALVE TEST | 2002-04-09 07:30 | 2002-04-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual relief valve testing. |  |  |  | 0 | P | N | N
46 | 18454 | AMA | ROGER MILLS | ALL | ANNUAL ESD | 2002-07-22 08:00 | 2002-07-22 12:00 | 0.2 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
47 | 18592 | AMA | SPEARMAN | ALL | RELIEF VALVE TESTING | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 |  | OPS |  | 0 | 0 | Testing the relief valves. |  |  |  | 0 | P | N | N
48 | 18523 | AMA | SPEARMAN | ESD & A LINE | ESD & A LINE LEAKS | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 68 | 90.7 | Annual ESD. Need to repair several A Line leaks. |  |  |  | 0 | P | N | N
49 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
50 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N
51 | 18526 | AMA | SUNRAY | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 144 | 72 | Annual ESD. |  |  |  | 0 | P | N | N
52 | 18387 | AMA | SUNRAY | 6 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
53 | 18388 | AMA | SUNRAY | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
54 | 18389 | AMA | SUNRAY | 5 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | Engine both side & compressor. |  |  |  | 0 | P | N | N
55 | 18514 | AMA | WOODWARD 1 | ALL | ESD | 2002-06-12 09:00 | 2002-06-12 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
56 | 18378 | AMA | WOODWARD 1 | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-08-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
57 | 18515 | AMA | WOODWARD 2 | ALL | ESD | 2002-07-17 09:00 | 2002-07-17 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
58 | 18381 | AMA | WOODWARD 2 | 4 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
59 | 18516 | AMA | WOODWARD 3 | ALL | ESD | 2002-06-19 09:00 | 2002-06-19 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
60 | 18382 | AMA | WOODWARD 3 | 4 | OVERHAUL | 2002-09-15 08:00 | 2002-09-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - August 1, 2001 Through December 31, 2002
Amarillo Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 19, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18461 | AMA | BEAVER 12 | 1 | SUCTION SCRUBBER | 2001-12-29 12:00 | 2002-03-22 16:00 | 83.2 |  | OPS |  | 0 | 0 | Have suction scrubber rebuilt. |  | 2001-12-29 12:00 |  | 0 | U | N | N
2 | 18362 | AMA | BEAVER 12 | 3 | OVERHAUL (ON HOLD) | 2002-03-26 13:00 | 2002-04-26 16:00 | 31.1 |  | OPS |  | 0 | 0 | Overhaul Engine & Compressors. |  |  |  | 0 | P | N | N
3 | 18528 | AMA | BEAVER 2 | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 12:00 | 0.2 |  | OPS |  | 5 | 0.8 | Annual ESD. |  |  |  | 0 | P | N | N
4 | 18376 | AMA | BEAVER 2 | 5 | OVERHAUL | 2002-07-08 08:00 | 2002-08-09 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major engine (Mike White OH). |  |  |  | 0 | P | N | N
5 | 18460 | AMA | BEAVER 6 | ALL | ANNUAL ESD | 2002-05-08 10:00 | 2002-05-08 12:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
6 | 18380 | AMA | BEAVER 6 | 1 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine & compressor. |  |  |  | 0 | P | N | N
7 | 18589 | AMA | BEAVER 7 | 1 | COMPRESSOR CYLINDER | 2002-03-10 07:00 | 2002-03-22 16:00 | 12.4 |  | OPS |  | 3 | 37.1 | Unit down with a knock in the #1 compressor. Not sure what they have unitl they tear into it. |  | 2002-03-10 07:00 |  | 0 | U | N | N
8 | 18374 | AMA | BEAVER 7 | 1 | OVERHAUL (ON HOLD) | 2002-06-15 08:00 | 2002-06-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major overhaul. |  |  |  | 0 | P | N | N
9 | 18384 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-10-15 08:00 | 2002-10-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
10 | 18386 | AMA | BEAVER 7 | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N
11 | 18367 | AMA | BEAVER PLANT | 12 | OVERHAUL (ON HOLD) | 2002-04-01 08:00 | 2002-04-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major enigne & compressors. (Subject to Dynegy approval). |  |  |  | 0 | P | N | N
12 | 18369 | AMA | BEAVER PLANT | 14 | OVERHAUL | 2002-05-01 08:00 | 2002-06-01 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major engine and compressors. |  |  |  | 0 | P | N | N
13 | 18522 | AMA | BEAVER PLANT | ESD | ESD | 2002-05-02 08:00 | 2002-05-02 16:00 | 0.3 |  | OPS |  | 350 | 116.7 | Annual ESD. (7 to 8 hours). |  |  |  | 0 | P | N | N
14 | 18583 | AMA | BEAVER PLANT | B LINE ORIFICE | REMOVE ORIFICE PLATE | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 0 | 0 | They believe the orifice plate is bent on the B line measurement at Beaver. They need to remove it when Beaver has their ESD. Actual time table for the work is estimated. It could be more or less. Flow affect is Spearman volumes. Estimated(68 mmfcd). |  |  |  | 0 | P | N | N
15 | 18365 | AMA | BEAVER PLANT | 9 | OVERHAUL | 2002-07-29 08:00 | 2002-08-30 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major engine & compressors. |  |  |  | 0 | P | N | N
16 | 18263 | AMA | CANADIAN | 1 & 3 | ANNUAL ESD | 2002-09-11 08:00 | 2002-09-11 16:00 | 0.3 |  | OPS |  | 2.6 | 0.9 | Annual ESD. |  |  |  | 0 | P | N | N
17 | 18607 | AMA | CANADIAN RIVER STA. | 1&3 | POWER CYLINDER LINERS | 2002-03-18 12:30 | 2002-03-27 16:00 | 9.2 |  | OPS |  | 5 | 45.8 | Four power cylinder liners leaking. Will remove all eight liners and replace gaskets. |  | 2002-03-18 12:30 |  | 0 | U | N | N
18 | 18338 | AMA | CLAUDE | 1 | ANNUAL ESD | 2002-05-14 09:00 | 2002-05-14 18:00 | 0.4 |  | OPS |  | 0 | 0 | Conducting annual ESD. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
19 | 18340 | AMA | CLAUDE | 1 | SAFETY DEVICES | 2002-10-08 09:00 | 2002-10-09 08:00 | 1 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
20 | 18555 | AMA | ELLIS 1 | 2 | 1500 HR. INSPECTION | 2002-03-21 09:00 | 2002-03-21 12:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hr Inspection. |  |  |  | 0 | U | N | N
21 | 18554 | AMA | ELLIS 1 | 1 | 1500 HR. INSPECTION | 2002-04-15 09:00 | 2002-04-15 11:00 | 0.1 |  | OPS |  | 2 | 0.2 | 1500 hr. Inspection. |  |  |  | 0 | U | N | N
22 | 18553 | AMA | ELLIS 1 | 4 | 1500 HR. INSPECTON | 2002-04-17 09:00 | 2002-04-17 12:00 | 0.1 |  | OPS |  | 5 | 0.6 | 1500 hr. Inspection. |  |  |  | 0 | U | N | N
23 | 18552 | AMA | ELLIS 1 | 3 | 1500 HR. INSPECTION | 2002-04-19 09:00 | 2002-04-19 11:00 | 0.1 |  | OPS |  | 2 | 0.2 | 1500 hr. inspection. |  |  |  | 0 | U | N | N
24 | 18459 | AMA | ELLIS 1 | ALL | ANNUAL ESD | 2002-05-07 09:00 | 2002-05-07 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. Will blind flange and not blow the station down. |  |  |  | 0 | P | N | N
25 | 18385 | AMA | ELLIS 1 | 1 | OVERHAUL | 2002-10-15 08:00 | 2002-11-15 16:00 | 31.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
26 | 18513 | AMA | ELLIS 2 | ALL | ESD | 2002-05-15 09:00 | 2002-05-15 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
27 | 18377 | AMA | ELLIS 2 | 2 | OVERHAUL | 2002-07-15 08:00 | 2002-07-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major compressor. |  |  |  | 0 | P | N | N
28 | 18588 | AMA | ELLIS 3 | 6 | 1500 HR. INSPECTION | 2002-04-07 09:00 | 2002-04-07 12:00 | 0.1 |  | OPS |  | 0 | 0 | 1500 hour inspection. |  |  |  | 0 | P | N | N
29 | 18261 | AMA | HEMPHILL 2 | ALL | ANNUAL ESD | 2002-09-10 08:00 | 2002-09-10 16:00 | 0.3 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
30 | 18260 | AMA | HEMPHILL 3 | ALL | ANNUAL ESD | 2002-09-09 08:00 | 2002-09-09 16:00 | 0.3 |  | OPS |  | 1.4 | 0.5 | Annual ESD. |  |  |  | 0 | P | N | N
31 | 18264 | AMA | HEMPHILL 4 | ALL | ANNUAL ESD | 2002-09-12 08:00 | 2002-09-12 09:00 | 0 |  | OPS |  | 1.4 | 0.1 | Annual ESD. |  |  |  | 0 | P | N | N
32 | 18593 | AMA | HUTCH 1 | 1 2 | RELIEF VALVE TESTING | 2002-03-26 08:00 | 2002-03-26 16:00 | 0.3 |  | OPS |  | 0 | 0 | Testing the relief valves. |  |  |  | 0 | P | N | N
33 | 18505 | AMA | NORTHRUP | 1 2 | RELIEF VALVE TEST | 2002-03-19 08:00 | 2002-03-19 11:00 | 0.1 |  | OPS |  | 15 | 1.9 | Testing the the relief valves. |  |  |  | 0 | P | N | N
34 | 18524 | AMA | NORTHRUP | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 10 | 5 | Annual ESD. |  |  |  | 0 | P | N | N
35 | 18331 | AMA | P3 | ALL | SURGE CONTROL TIE-IN & ESD | 2002-03-26 08:00 | 2002-03-27 16:00 | 1.3 |  | OPS |  | 100 | 133.3 | Annual ESD. We will need to remove some material that we are going to reuse and test it before we can make our tie-ins. (They will be able to by-pass the station to make some deliveries). |  |  |  | 0 | P | N | N
36 | 18332 | AMA | P3 | 1 | SAFETY DEVICES | 2002-04-23 08:00 | 2002-04-24 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
37 | 18371 | AMA | P3 | 1 | OVERHAUL | 2002-05-01 08:00 | 2002-05-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Exchange GP PT & AGB. |  |  |  | 0 | P | N | N
38 | 18333 | AMA | P3 | 2 | SAFETY DEVICES | 2002-05-08 08:00 | 2002-05-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
39 | 18334 | AMA | P3 | 3 | SAFETY DEVICES | 2002-05-22 08:00 | 2002-05-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
40 | 18336 | AMA | P3 | 5 | SAFETY DEVICES | 2002-06-18 08:00 | 2002-06-20 18:00 | 2.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
41 | 18335 | AMA | P3 | 4 | SAFETY DEVICES | 2002-08-22 08:00 | 2002-08-23 18:00 | 1.4 |  | OPS |  | 0 | 0 | Test and calibrate safety and shutdown devices. |  |  |  | 0 | P | N | N
42 | 18339 | AMA | PAMPA | 1 | ESD & SAFETY DEVICES | 2002-04-08 08:00 | 2002-04-09 18:00 | 1.4 |  | OPS |  | 0 | 0 | Conducting annual ESD test and calibrating safety devices. If the unit is running we will re-schedule. |  |  |  | 0 | P | N | N
43 | 18525 | AMA | PERRYTON BARLOW | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 7 | 3.5 | Annual ESD. |  |  |  | 0 | P | N | N
44 | 17016 | AMA | ROGER MILLS | 5 | MECHNICAL FAILURE | 2001-09-19 16:00 | 2002-03-30 16:00 | 192 |  | OPS |  | 0 | 0 | They had a mechnical failure on unit #5. Not sure of the exact completion. (Completion date moved into March 2002). |  | 2001-09-19 16:00 |  | 0 | U | N | N
45 | 18455 | AMA | ROGER MILLS | ALL | RELIEF VALVE TEST | 2002-04-09 07:30 | 2002-04-10 16:00 | 1.4 |  | OPS |  | 0 | 0 | Annual relief valve testing. |  |  |  | 0 | P | N | N
46 | 18454 | AMA | ROGER MILLS | ALL | ANNUAL ESD | 2002-07-22 08:00 | 2002-07-22 12:00 | 0.2 |  | OPS |  | 0 | 0 | Annual ESD test. |  |  |  | 0 | P | N | N
47 | 18592 | AMA | SPEARMAN | ALL | RELIEF VALVE TESTING | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 |  | OPS |  | 0 | 0 | Testing the relief valves. |  |  |  | 0 | P | N | N
48 | 18523 | AMA | SPEARMAN | ESD & A LINE | ESD & A LINE LEAKS | 2002-05-02 08:00 | 2002-05-03 16:00 | 1.3 |  | OPS |  | 68 | 90.7 | Annual ESD. Need to repair several A Line leaks. |  |  |  | 0 | P | N | N
49 | 18238 | AMA | SUNRAY | 4 | RH 3&4 CYLINDER | 2001-11-30 08:00 | 2002-06-01 16:00 | 183.3 |  | OPS |  | 0 | 0 | The rings are out on the RH 3&4 cylinder. (Waiting for clearence to overhaul unit). |  | 2001-11-30 08:00 |  | 0 | U | N | N
50 | 18239 | AMA | SUNRAY | 5 | CRACKED HEAD | 2001-12-22 08:00 | 2002-06-03 16:00 | 163.3 |  | OPS |  | 0 | 0 | LH #3 head is cracked- It will require a complete overhaul on the LH side. (This work is subject to approval). |  | 2001-12-22 08:00 |  | 0 | U | N | N
51 | 18526 | AMA | SUNRAY | ALL | ESD | 2002-05-02 08:00 | 2002-05-02 20:00 | 0.5 |  | OPS |  | 144 | 72 | Annual ESD. |  |  |  | 0 | P | N | N
52 | 18387 | AMA | SUNRAY | 6 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
53 | 18388 | AMA | SUNRAY | 4 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | LH Engine & Compressor. |  |  |  | 0 | P | N | N
54 | 18389 | AMA | SUNRAY | 5 | OVERHAUL | 2002-11-01 08:00 | 2002-11-20 16:00 | 19.3 |  | OPS |  | 0 | 0 | Engine both side & compressor. |  |  |  | 0 | P | N | N
55 | 18514 | AMA | WOODWARD 1 | ALL | ESD | 2002-06-12 09:00 | 2002-06-12 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
56 | 18378 | AMA | WOODWARD 1 | 3 | OVERHAUL | 2002-08-01 08:00 | 2002-08-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
57 | 18515 | AMA | WOODWARD 2 | ALL | ESD | 2002-07-17 09:00 | 2002-07-17 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
58 | 18381 | AMA | WOODWARD 2 | 4 | OVERHAUL | 2002-09-01 08:00 | 2002-09-30 16:00 | 29.3 |  | OPS |  | 0 | 0 | Major Engine. |  |  |  | 0 | P | N | N
59 | 18516 | AMA | WOODWARD 3 | ALL | ESD | 2002-06-19 09:00 | 2002-06-19 11:00 | 0.1 |  | OPS |  | 0 | 0 | Annual ESD. |  |  |  | 0 | P | N | N
60 | 18382 | AMA | WOODWARD 3 | 4 | OVERHAUL | 2002-09-15 08:00 | 2002-09-30 16:00 | 15.3 |  | OPS |  | 0 | 0 | Major Compressor. |  |  |  | 0 | P | N | N