## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 19, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18586 | BEA | BUSHTON | 27 | REPAIR LEAK | 2002-03-14 06:00 | 2002-03-15 15:30 | 1.4 |  | OPS |  | 0 | 0 | Repair leak on water heater. |  |  |  | 0 | U | N | N
2 | 18606 | BEA | BUSHTON | 23 | COMPRESSOR ROD | 2002-03-19 07:30 | 2002-03-20 15:30 | 1.3 |  | OPS |  | 0 | 0 | Replace #1 compressor rod. |  |  |  | 0 | U | N | N
3 | 17151 | BEA | BUSHTON | 26 | OVERHAUL (ON HOLD) | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
4 | 18527 | BEA | BUSHTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 20:00 | 0.5 |  | OPS |  | 300 | 162.5 | Annual ESD. We should be able to bypass some volumes through the station using Clifton H.P. |  |  |  | 0 | P | N | N
5 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL & CRACKED MANIFOLD | 2002-03-04 07:00 | 2002-03-25 15:30 | 21.3 |  | OPS |  | 50 | 1066.7 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. Repair Manifold. (Flow affect is about 50 mmcfd depending on the needs on the pipeline). |  | 2002-03-04 07:00 |  | 0 | P | N | N
7 | 18567 | BEA | CUNNINGHAM | 1 2 3 | ELECTRIC CO. SERVICE | 2002-03-20 08:00 | 2002-03-20 12:00 | 0.2 |  | OPS |  | 200 | 33.3 | The electric company needs to perform maintenance on their service. This work is being done due to their equipment failure on 03/01/02. (Unit #4 & #6 will still be available). The electric units will be down. |  |  |  | 0 | P | N | N
8 | 18569 | BEA | CUNNINGHAM | ALL | MAIN PLANT DRIPS | 2002-04-30 07:00 | 2002-04-30 16:00 | 0.4 |  | OPS |  | 0 | 0 | Repair/replace 1" line on Main Plant Drips. This is a consolidated audit action item. (It will affect max Inj. and Wdl). |  |  |  | 0 | P | N | N
9 | 18568 | BEA | CUNNINGHAM | ALL | ESD | 2002-06-06 07:00 | 2002-06-06 16:00 | 0.4 |  | OPS |  | 0 | 0 | Annual ESD test. (Will affect max Inj. and Wdl. |  |  |  | 0 | P | N | N
10 | 18512 | BEA | NGPL | TRAILBLAZER | NGPL TRAILBLAZER I/C | 2002-04-09 08:00 | 2002-04-11 16:00 | 2.3 |  | OPS |  | 450 | 1050 | NGPL is having a complete outage on their side. |  |  |  | 0 | P | N | N
11 | 18533 | BEA | PALMYRA | 23 | POWER PISTON | 2002-03-14 07:30 | 2002-03-14 16:00 | 0.4 |  | OPS |  | 0 | 0 | Pull #4 power piston for inspection and install new power piston rings and recondition power cylinder head. |  |  |  | 0 | P | N | N
12 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-21 16:00 | 15.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
13 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
14 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Beatrice Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 19, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18586 | BEA | BUSHTON | 27 | REPAIR LEAK | 2002-03-14 06:00 | 2002-03-15 15:30 | 1.4 |  | OPS |  | 0 | 0 | Repair leak on water heater. |  |  |  | 0 | U | N | N
2 | 18606 | BEA | BUSHTON | 23 | COMPRESSOR ROD | 2002-03-19 07:30 | 2002-03-20 15:30 | 1.3 |  | OPS |  | 0 | 0 | Replace #1 compressor rod. |  |  |  | 0 | U | N | N
3 | 17151 | BEA | BUSHTON | 26 | OVERHAUL (ON HOLD) | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
4 | 18527 | BEA | BUSHTON | ALL | ESD | 2002-05-07 07:30 | 2002-05-07 20:00 | 0.5 |  | OPS |  | 300 | 162.5 | Annual ESD. We should be able to bypass some volumes through the station using Clifton H.P. |  |  |  | 0 | P | N | N
5 | 17152 | BEA | BUSHTON | 27 | OVERHAUL | 2002-06-03 08:00 | 2002-07-03 16:00 | 30.3 |  | OPS |  | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
6 | 17154 | BEA | CUNNINGHAM | 5 | OVERHAUL & CRACKED MANIFOLD | 2002-03-04 07:00 | 2002-03-25 15:30 | 21.3 |  | OPS |  | 50 | 1066.7 | Major overhaul MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. Repair Manifold. (Flow affect is about 50 mmcfd depending on the needs on the pipeline). |  | 2002-03-04 07:00 |  | 0 | P | N | N
7 | 18567 | BEA | CUNNINGHAM | 1 2 3 | ELECTRIC CO. SERVICE | 2002-03-20 08:00 | 2002-03-20 12:00 | 0.2 |  | OPS |  | 200 | 33.3 | The electric company needs to perform maintenance on their service. This work is being done due to their equipment failure on 03/01/02. (Unit #4 & #6 will still be available). The electric units will be down. |  |  |  | 0 | P | N | N
8 | 18569 | BEA | CUNNINGHAM | ALL | MAIN PLANT DRIPS | 2002-04-30 07:00 | 2002-04-30 16:00 | 0.4 |  | OPS |  | 0 | 0 | Repair/replace 1" line on Main Plant Drips. This is a consolidated audit action item. (It will affect max Inj. and Wdl). |  |  |  | 0 | P | N | N
9 | 18568 | BEA | CUNNINGHAM | ALL | ESD | 2002-06-06 07:00 | 2002-06-06 16:00 | 0.4 |  | OPS |  | 0 | 0 | Annual ESD test. (Will affect max Inj. and Wdl. |  |  |  | 0 | P | N | N
10 | 18512 | BEA | NGPL | TRAILBLAZER | NGPL TRAILBLAZER I/C | 2002-04-09 08:00 | 2002-04-11 16:00 | 2.3 |  | OPS |  | 450 | 1050 | NGPL is having a complete outage on their side. |  |  |  | 0 | P | N | N
11 | 18533 | BEA | PALMYRA | 23 | POWER PISTON | 2002-03-14 07:30 | 2002-03-14 16:00 | 0.4 |  | OPS |  | 0 | 0 | Pull #4 power piston for inspection and install new power piston rings and recondition power cylinder head. |  |  |  | 0 | P | N | N
12 | 17166 | BEA | PALMYRA | 21 | OVERHAUL | 2002-05-06 08:00 | 2002-05-21 16:00 | 15.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
13 | 17167 | BEA | PALMYRA | 22 | OVERHAUL | 2002-05-27 08:00 | 2002-06-14 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
14 | 17168 | BEA | PALMYRA | 23 | OVERHAUL | 2002-06-17 08:00 | 2002-07-05 16:00 | 18.3 |  | OPS |  | 0 | 0 | Compressor overhaul on a Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  |  | 0 | P | N | N
15 | 16327 | BEA | SO OMAHA | CREEK XING | OMAHA 3RD BL | 2002-07-15 08:00 | 2002-07-15 16:00 | 0.3 |  | 453 | C.014544 | 0 | 0 | Replace and lower approximately 200 feet of the 16" Omaha 3rd branch line at MP 16.86. |  |  |  | 0 | P | N | N