## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 19, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18609 | MID | JAL | 1&2 | FUEL GAS OPERATOR | 2002-03-19 13:45 | 2002-03-21 15:00 | 2.1 |  | OPS |  | 0 | 0 | Repair operator for fuel gas ESD. Part will have to be sent in and repaired. Can not operate the station without this equipment. |  | 2002-03-19 13:45 |  | 0 | U | N | N
2 | 18566 | MID | KERMIT | 1 2 | RELIEF VALVE TESTS | 2002-03-26 08:00 | 2002-03-26 18:30 | 0.4 |  | OPS |  | 0 | 0 | Test relief valves on #1 and #2 turbines at the station.Seminole would be available to run if needed. |  |  |  | 0 | P | N | N
3 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 12:00 | 1.2 |  | OPS |  | 0 | 0 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. Flow affect should be 0. |  |  |  | 0 | P | N | N
4 | 18510 | MID | SPRAYBERRY | 4 | COMPLETE INSPECTION | 2002-03-12 08:00 | 2002-03-28 16:00 | 16.3 |  | OPS |  | 0 | 0 | Make a comple inspection on #4 unit. Wewill drain oil from crankcase.Inspect bearings. Web deflections and torque anchor bolts. Compressor rod run out. Locate the water source and fix it. (There will be a flow affect if noms get above 80 mmcfd). |  | 2002-03-12 08:00 |  | 0 | P | N | N
5 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 180 | 60 | Annual ESD and maintenance. The flow affect will depend on the volumes available to move thru the station. |  |  |  | 0 | P | N | N
6 | 18483 | MID | WT-2 | ALL | SCRUBBER WORK | 2002-03-20 08:00 | 2002-03-21 16:00 | 1.3 |  | OPS |  | 300 | 400 | Replacing a 12" valve on #1 scrubber and repair the internal piping to #1 scrubber. |  |  |  | 0 | P | N | N
7 | 18383 | MID | WT-2 | 201 | OVERHAUL | 2002-09-15 08:00 | 2002-10-20 16:00 | 35.3 |  | OPS |  | 0 | 0 | Compressor OH. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc
ETS Planned And Unplanned Outages - January 1, 2002 Through December 31, 2002
Midland Region Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted March 19, 2002 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 18609 | MID | JAL | 1&2 | FUEL GAS OPERATOR | 2002-03-19 13:45 | 2002-03-21 15:00 | 2.1 |  | OPS |  | 0 | 0 | Repair operator for fuel gas ESD. Part will have to be sent in and repaired. Can not operate the station without this equipment. |  | 2002-03-19 13:45 |  | 0 | U | N | N
2 | 18566 | MID | KERMIT | 1 2 | RELIEF VALVE TESTS | 2002-03-26 08:00 | 2002-03-26 18:30 | 0.4 |  | OPS |  | 0 | 0 | Test relief valves on #1 and #2 turbines at the station.Seminole would be available to run if needed. |  |  |  | 0 | P | N | N
3 | 18325 | MID | PLAINS | 1 | ANNUAL ESD | 2002-03-19 08:00 | 2002-03-20 12:00 | 1.2 |  | OPS |  | 0 | 0 | Annual ESD & calibrate transmitters. Test all shut downs devices put in new battery charge. (Will put on @ 18:00 03/19/02 and take back down on 3/20/02 if needed). Will see if El Paso can work with us on the outage. Flow affect should be 0. |  |  |  | 0 | P | N | N
4 | 18510 | MID | SPRAYBERRY | 4 | COMPLETE INSPECTION | 2002-03-12 08:00 | 2002-03-28 16:00 | 16.3 |  | OPS |  | 0 | 0 | Make a comple inspection on #4 unit. Wewill drain oil from crankcase.Inspect bearings. Web deflections and torque anchor bolts. Compressor rod run out. Locate the water source and fix it. (There will be a flow affect if noms get above 80 mmcfd). |  | 2002-03-12 08:00 |  | 0 | P | N | N
5 | 18319 | MID | SPRAYBERRY | ESD | ANNUAL ESD | 2002-05-22 08:00 | 2002-05-22 16:00 | 0.3 |  | OPS |  | 180 | 60 | Annual ESD and maintenance. The flow affect will depend on the volumes available to move thru the station. |  |  |  | 0 | P | N | N
6 | 18483 | MID | WT-2 | ALL | SCRUBBER WORK | 2002-03-20 08:00 | 2002-03-21 16:00 | 1.3 |  | OPS |  | 300 | 400 | Replacing a 12" valve on #1 scrubber and repair the internal piping to #1 scrubber. |  |  |  | 0 | P | N | N
7 | 18383 | MID | WT-2 | 201 | OVERHAUL | 2002-09-15 08:00 | 2002-10-20 16:00 | 35.3 |  | OPS |  | 0 | 0 | Compressor OH. |  |  |  | 0 | P | N | N