## Sheet1
LOG OF DAILY VALUATION ISSUES
CLASS
A - Deal Capture
B - Deal Valuation
C - Breakdown in transfer of data to RiskTrac (Officializing Process) - Human
D1 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (UK)
D2 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (US)
E - Curve Issues
F - No ones fault. System needs to change.
G - Other
H - Not identified.
|  |  |  | RESPONSIBLE |  |  |  | VAR | CREDIT | IMPACT CASH | STATUS
DATE | BOOK/AREA | Group | COMMODITY/OFFICE | PARTY | CLASS | PROBLEM | ACTION PLAN | RERUN? | AFFECTED? | FLOWS? | (DATE)
2001-06-07 | Eastern Spreadsheets 1&2 | EEL | UK Power | James New | E | Since a Power Curve for Jun 7th was not saved, the spreadsheets were unable to run a valuation and report MTM & Risk exposures for Jun 7th. Therefore data reported is as of Jun 6. | Risk Management is working to develop process to insure that all needed curve data is saved for each day. Additionally, need to establish procedures for reporting MTM and P&L when process fails. | N | Y | Y | Pending
2001-06-07 | UK Power | EEL | UK Power | James New | D1 | UK Power Book was officialized on time, however the feed did not complete until 6:50 am due to length of time needed for extract process. | Resolution has been developed and is currently being tested. Test feed should be in place by 06/11/01 | N | Y | Y | Pending
2001-06-07 | UK Power | EEL | UK Power | James New | E | Traders failed to save Power Curves for June 7th. Therefore, no P&L Curve shift available. All positions were properly loaded into RisktRAC | Risk Management is working to develop process to insure that all needed curve data is saved for each day. | N | N | N | Pending
2001-06-06 | PWR-NG-WEST-GD-GDL | EA-Power | West Power | Fran Chang | C | Book was not officialized. Book has no positions and therefore had no impact on VaR or Credit. However, going forward failure to officialize all active books could result in potential errors. | Risk Management, John Postlewaite and Fran Chang, have been instructed in the use of the Active/Inactive book website to ensure that end of the day procedures identify active books that have not been officialized. | N | N | N | Done
2001-06-06 | UK Gas | EEL | UK-GAS | James New | D1 | There was a problem in producing the file for FTP to Houston and therefore the data could not be loaded into RisktRAC. The problem was due to a change in the index changed on the underlying table causing the extraction to slow down. Problem was identified and corrected. | IT has changed the feeds indexing strategy | Y | Y | Y | Done
2001-06-05 | Australian Weather (GG) Credit File | EEL | Australian Weather (GG) | Justin Den Hertog | H | Based on information from Australia, their daily process were completed, however the file was not captured by Houston process. Houston IT is researching the issue to further identify | Houston IT has reviewed needed file saving process with Australian Risk Management. IT has also provided additional information, regarding data saving, that may prevent future problems. | N | Y | N | Done
2001-06-05 | Nordic Weather Credit File | EEL | Nordic Weather | Didrik Thraner Nielsen | D1 | Credit file was submitted late. Working with BA to identify issue. | Delay was caused by continued IT issues encountered by Backup BA due to testing of new system. Risk management has instructed BA to use alternate computer to prevent continued occurance of problem. | N | Y | N | Done
2001-06-05 | Coal Positions | EGM | COAL | Michaels Stark | E | Positions related to a specific curve, F-CAPE-TC, was not captured in the system which impacts the VaR calculation. Deals were being moved to different books and using different curves to value. |  | N | N | N | Pending
2001-06-04 | Factor Loading/Primary Curves |  |  | RAC | G | Due to current processes and procedures in place, factor loadings have not been approved since April 17, 2001. This lack of factor loading prevents the addition of new primary curves in RisktRAC. Therefore certain secondary curves are not mapped to the appropriate primary curves. The addition of the new primary curves could impact VaR. | Coordinate with various groups to identify improved process for approving factor loadings and primary curves into system. | N | N | N | Pending
2001-06-04 | Unify Power File | EGM | US-Power | Samuel Blaylock | D2 | Uniy Power File not transmitted, which impacts the Margin position for Enron. | Power Database was recently converted to SQL and continues to be refined. Refining process may be interfering with batch processing of file. IT has rescheduled batch process and assigned personnel to monitor file process to avoid future problems. Database will be finalized this weeken, so future problems should be avoided. | N | Y | Y | Done
2001-06-04 | UK Power | EEL | UK Power | James New | D1 | UK Power Book was officialized on time, however the feed did not complete until 6:50 am due to database issues. The database problem was caused by "Rollback Segment" error , which is caused by the size of data conflicting with other users. | DBA have improved rollback segment, but IT to research solution to prevent further occurance. | N | Y | Y | Pending
2001-06-04 | Nordic Weather Credit File | EEL | Weather | Didrik Thraner Nielfen | C | Book not officialized due IT problems encountered by backup personnel. Assigned BA was out of the office and backup experienced IT problems on her computer. In the A.M. backup BA used another computer to officialize book. | Risk Management has communicated procedures for using alternate computer resources when primary fails. | Y | Y | Y | Done
2001-06-01 | Bandwidth Curve | EBS | Bandwidth | Gary Stadler | E | Volatilty Curve Data not Captured in RisktRAC. | Following up with IT to determine issue and resolution | Y | N | N | Pending
2001-06-01 | EBS-BWT | EEL | EBS-BWT | James New | C | Risk Management advised that file is late because of month-end issues and a larger than normal number of deals to be input. |  | Y | Y | Y | Pending
2001-06-01 | UK Power | EEL | UK Power | James New | D1 | Book was loaded into RisktRac 14 mins late at 6:14 AM Houston time. | Resolution has been developed and is currently being tested. Should be moved to production around 06/08/01 | N | N | N | Pending
2001-06-01 | Nordic Power | EEL | Nordic Power | James New | C | Business holiday for 06/04/01, however appropriate holiday schedule not followed. Communicated procedures required that 06/01/01 data be officialized prior to holiday. | Recommunicate holiday procedures with appropriate Business Risk Managers to insure that data is appropriatesly reported. | N | Y | Y | Pending
2001-05-31 | UK Power | EEL | UK Power | James New | D1 | Book was loaded into RisktRac 14 mins late at 6:14 AM Houston time. | Steps are being taken by IT to try to reduce the feed time of moving the UK Power file to RisktRac. | Y | Y | N | Pending
2001-05-29 | Nordic Power | EEL | Nordic Power | James New | D1 | Experienced problems sending their feed to RisktRac due to a failure in the overnight Nordic MTM system run. | IT is working on this issue. | N | N | N | Pending
2001-05-24 | Eastern Books | EEL | UK Eastern | James New | D1 | Problems loading current day spreadsheet as a result, 70 Bcf of hedges did not make it to RisktRac. | IT is working on this issue. | N | Y | Y | Pending
2001-05-24 | UK Power | EEL | UK Power | James New | D1 | Database is not functioning properly. (IT issues) | Houston IT working on fixing this problem. |  |  |  | Pending
2001-05-22 | UK Gas | EEL | UK Gas | James New | E | PPP power curve was loaded into the curve file thus causing incorrect valuation and problems with the position files. | Waiting for an Action Plan from UK. | Y | N | N | Pending
2001-05-22 | Nordic Power | EEL | Nordic Power | James New | D1 | File had to be re-send because of a deal that was doubled up. File was re-sent before the first file sent completed reconciling deal and position table. | Houston IT suggested when having to re-send file, develop a test to check if first file was completed and wait 10 mins before sending the second one. | N | N | N | Pending
2001-05-21 | Unified Power | EA-POWER | Power | Leslie Reeves | D1 | Unified power system failed and had to be re-run. | Unified system personnel are monitoring the system to determine cause of the problem. | N | Y | N | Pending
2001-05-18 | Nordic Power | EEL | Nordic Power | James New | D1 | Multiple UK files came in at the same time, therefore, the Nordic file was not able to get through. | Have the DBA increase the size to allow files to be sent simultaneously. | Y | Y | N | Pending
2001-05-08 | Continental Power | EEL | Continental Power | James New | D1 | Monday was a bank holiday and IT switched Portcalc off as they did not want the systems to run overnight. However, it was not turned on by IT for Tuesday 8 May close of business overnight run. Consequently, Portcalc mtm did not run and there was no data for 8 May to be officialized by risk management. The Portcalc mtm had to be subsequently re-run by IT during the current day and was then officialized and loaded into Risktrac at 7:35 am Houston time. | Procedure to be put in place so that the dates for running of the mtm are clearly stated and defined for the benefit of IT. This will ensure that any confusion is removed as to the dates for the mtm run. | Y | Y | Y | Pending
2001-05-08 | Nordic Power | EEL | Nordic Power | James New | D1 | Nordic Power data for 8 May did not load into Risktrac until 6:13 am Houston time. This was due to a random IT error in that some options failed to be calculated in the overnight mtm run. Nordic risk management had to manually determine which of the book's option positions failed to be calculated and then had to manually recalculate these options before officialization could be initiated. | Waiting for an Action Plan from Michael Kass. | N | N | N | Pending
2001-04-30 | FT-CAND-AB-GDL-GDL, INTRA-CAND-BC-BAS, INTRA-CAND-BC-GD-GDL, INTRA-CAND-BE-PRC, INTRA-CAN-WE-DG-DGL, FT-CAND-OP-GD-GDL | EA-CAN | Canada | Peggy Hedstrom | C | Books not officialized. When running the exception reports, an incorrect effective date was used, resulting in the inaccurate capture of PostID's that were not officialized. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. Canada Risk Mgmt. Group to be trained on using Active/Inactive book website. | Y | Y | Y | Pending
2001-04-27 | EBS Books | EBS | EBS US |  | D2 | Takes 1+ hour to upload books into RiskTrac. | Risk + RAC to determine if there is an easier way. Debbie Brackett and Ramesh will meet with Kristin Albrecht to discuss prioritizing file load. | N | N | N | Pending
2001-04-27 | INTRA-CAND-WE-GD-GDL | EA-CAN | Canada | Peggy Hedstrom | C | Book not officialized | Implement Active/Inactive website.Canada Risk Mgmt. Group to be trained on using Active/Inactive book website. |  |  |  | Pending
2001-06-01 | UK Gas | EEL | UK Gas | James New | C | Trader officialized book twice, which caused a delay in loading valid numbers. | IT deleted incorrect data. | Y | Y | Y | Done
2001-06-01 | EPMI-PJM-FTR-PRC | EA-POWER | US Power | Marilyn Tisdale | F | Book was officialized as part of a portcalc process, however it contained no open forward positions. Enpower does not transmit PostIds to RisktRac for books without Open forward positions. Therefore, no impact on VaR or other systems. | Since there was no failure in procedures or impact on systems, no further action considered necessary. | N | N | N | Done
2001-06-01 | Continental Power | EEL | Continental Power | James New | D1 | Due to a number format problem due to sensitivity analysis on the vol curve at month end the MTM process failed over the Weekend. Problem was corrected and process reiniated in the AM. | Going forward, Risk management to ensure that at the beginning of each month the volitility curve is saved down in correct format. |  |  |  | Done
2001-05-31 | Continental Power | EEL | Continental Power | James New | C | Experienced an overnight failure in Portcalc due to a trade being booked by a trader in a new currency (USD) and no USD curves loaded being to value USD denominated trades. | Risk Management has required traders to notify when they will book any trades in new currencies and Dove Calc will now skip a deal if it can not value due to missing curves instead of stopping the MTM process. | Y | Y | N | Done
2001-05-31 | South America Power | EA-POWER | SA Power | Sarah Smith | B | Due to work being performed on the model used to value deals there was a change in the spreadsheet structure that added a column. The addition of the column created an incorrect data link for positions. Process to verify positions loaded into RisktRAC overlooked. | Format on spreadsheet was corrected and data reloaded. Process to verify positions loaded was recommunicated to appropriate personnel. | y | y | y | Done
2001-05-31 | FT-HPLC-IDX, FT-LONESTAR-IDX | EA-GAS | US Gas Texas | David Baumbach | F | Due to IT issues, books were not showing as being officialized. | When Book Administrators re-officialized books, positions came through. | N | N | N | Done
2001-05-31 | FRT-HO-PRC and FRT-WTI-PRC | EGM | Freight | Todd Hall | C | Appropriate fields not selected during Metacalc process, which prevented capture of data. | Risk Management has recommunicated appropriate officialization process to Business Administrator. Use of Active/Inactive list will help identify any future failures in Metacalc process. | N | y | y | Done
2001-05-30 | INTRA-TEXAS-PHY | EA-GAS | US Gas Texas | Jeff Gossett | F | Book was replaced by ENA-IM-CARTHAGE, therefore, there were no position in this book. | Need to notify Risk Controls whenever a book is made inactive. | N | N | N | Done
2001-05-29 | EBS-ADV-PRC | EBS | US EBS | Belinda Woo | C | Book administrator forgot to officialize. | Manager needs to review website to ensure all post Ids are officialized. | Y | Y | N | Done
2001-05-29 | FT-ONT-CENTRAL-PRC | EA-GAS | US Gas Central | Jeff Gossett | C | Book administrator forgot to officialize. | Manager needs to review website to ensure all post Ids are officialized. | Y | Y | N | Done
2001-05-29 | INTRA-DENVER-PRC | EA-GAS | US Gas West | Jeff Gossett | C | Book administrator forgot to officialize. | Manager needs to review website to ensure all post Ids are officialized. | N | N | N | Done
2001-05-25 | Eastern Books | EEL | UK Eastern | James New | G | Due to power outage, officialized the 24th instead of the 28th. | N/A | N | N | N | Done
2001-05-24 | MG-AGRI-COCOA-PRC | EGM | Interest/ FX Group | Sheila Glover | C | Book administrator forgot to load spreadsheet. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. | Y | Y | N | Done
2001-05-24 | EPMI-LT-SERC-PRC, EPMI-LT-SPP-PRC, EPMI-SE-ANALYST-PRC, EPMI-ST-SOUTHEAST-PRC, EPMI-ST-SERC-PRC, EPMI-ST-SPP-PRC | EA-POWER | US Power East | Stacey White | C | Book administrator forgot to officialize. | Book Administrator did not utilize the active/ inactive website. | Y | Y | Y | Done
2001-05-23 | UK Power | EEL | UK Power | James New | D1 | Curve database was full resulting in UK Power curves not fully loaded into system for MTM calculation. | IT 24 hour support group has been notified to ensure that enough space is available before curve loading is initiated. | Y | Y | Y | Done
2001-05-21 | Nordic Power | EEL | Nordic Power | James New | D1 | Multiple UK files came in at the same time, therefore, the Nordic file was not able to get through. | Increase the DBA size today -05/22/01-to allow files to be sent simultaneously. | Y | Y | N | Done
2001-05-17 | JL-SAPWR-XL-PRC | EEL | SA Power | Sarah Smith | C | Liquidated swaps; therefore, spreadsheet should have been officialized one more time with a zero. | Book will be officialized one last time with a zero for May 17th. | N | Y | N | Done
2001-05-16 | UK Power | EEL | UK Power | James New | D1 | UK Power book was late as there were technical problems experienced on the PC which runs the spreadsheet officialization excel macro. | IT will try to run macro from another PC. | N | N | N | Done
2001-05-14 | LUMBER-US-PRC | EIM | US Lumber | Brenda Herod | C | Book was not officialized, Book Administrator forgot. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. | Y | Y | N | Done
2001-05-14 | UK Power, UK Gas, Nordic Power | EEL | UK Power, UK Gas, Nordic Power | James New | D1 | VAR from RisktRac does not reconcile to the VAR from the spreadsheet file sent for DPR reporting. | Risk Control continues to report the VAR from the spreadsheet file sent from the London office. | N | N | N | Done
2001-05-14 | Australian Weather (GG) | EEL | Australian Weather (GG) | Justin Den Hertog | C | Book Administrator sent file with the wrong extension for 05/14. | Book Administrator will delete the old .bkp version and load jn the fresh .xls version. | N | N | N | Done
2001-05-11 | UK Power | EEL | UK Power | James New | D1 | UK Power was officialized late due to an error in running the Dove Calc application. | Procedure to be put in place so that the dates for running of the mtm are clearly stated and defined for the benefit of IT. This will ensure that any confusion is removed as to the dates for the mtm run. | N | N | N | Done
2001-05-11 | Nordic Power | EEL | Nordic Power | James New | D1 | The feed from London was late primarily due to an error in the running of the Nordic mtm data. | Identified and understand reason for delay/problem. If system locks again, now able to resolve it very quickly. | N | N | N | Done
2001-05-11 | FT-NORTHWEST-IDX | EA-GAS | US Gas | Jeff Gossett | C | Book was not officialized. Book has no positions. | Book will be made inactive after tonight. (05/14/01) | N | N | N | Done
2001-05-11 | PWR-SE-GAS-MTM-GDL | EA-POWER | US Power East | Stacey White | C | Book was not officialized. Book has no positions. | Book will be made inactive after tonight. (05/14/01) | N | N | N | Done
2001-05-10 | MG-AGRI-COCOA-PRC | EGM | US Financial | Sheila Glover | C | Book was not officialized. Forgot to load spreadsheet. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. Training of staff on Monday, May 14th. | Y | N | N | Done
2001-05-10 | FT-CAND-EGSC-C-BAS | EA-CAN | Canada Gas | Peggy Hedstrom | C | Forgot to manually overwrite the Basis book with the post ID from the Price book. | Utilization of new Active/Inactive book website should help identify any unofficialized books during end of day process. | Y | N | N | Done
2001-05-10 | UK Power | EEL | UK Power | James New | D1 | UK Power file loaded into Risktrac late due to a change in password on the server used to send data to Risktrac. | All files updated for new password. | N | N | N | Done
2001-05-09 | FT-CAND-PWR-PRC, CAND-PWR-GD-GDL, CAND-PWR-PR-PRC | EA-CAN | Canada Gas | Peggy Hedstrom | C | Canadian Power trader had gas positions that were not being captured in the AGG-ECT portfolio. Therefore, VAR and gas positions were not correctly reported. | Short-term solution is to add gas positions to the gas bench and copy the Canadian Gas portfolio to the AGG-ECT portfolio and start officializing in US dollars. Long-term solution is to identify and ensure that all books with positions are being captured on the respective benchmark reports and books are included in AGG-ECT. | N | N | N | Done
2001-05-09 | Australian Weather (GG) | EEL | Australian Weather (GG) | Justin Den Hertog | C | Book Administrator sent file with the wrong extension resulted in information not properly being converted for processing. | Additional training is required to bring Book Administrator up to speed. | N | Y | N | Done
2001-05-08 | FT-NW-XL-OPT-BAS | EA-GAS | US Gas | Jeff Gossett | C | Book was officialized with wrong book name on the file. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. | Y | N | N | Done
2001-05-08 | INTRA-DENVER-PRC | EA-GAS | US Gas | Jeff Gossett | C | Book was officialized with the incorrect date. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. | Y | N | N | Done
2001-05-08 | UK Power | EEL | UK Power | James New | D1 | Previous day's data was officialized as current day data not available at time of officialization. This did not load into Risktrac until 6:05 am Houston time. The reason previous day's data had to be officialized was due to an IT error involving the overnight curve upload procedure. The process is automatic, but if thre are system problems as there were last night, then the process is required to be re-run manually. The manual re-run procedure was done correctly by the 24hr IT software support team and thus the Enpower mtm did not run. | The 24hr support team is now aware of procedures to re-start mtm if overnight system fails. | N | N | N | Done
2001-05-07 | MG-AGRI-COCOA-PRC | EGM | US Financial | Sheila Glover | G | London Holiday; positions were not rolled by Book Administrator. | Incorporating a holiday calendar in the RisktRAC system that will roll positions from prior day whenever there is a holiday. | Y | Y | Y | Done
2001-05-07 | INTRA-CAND-WEST-BAS | EA-CAN | CAD Gas | Peggy Hedstrom | C | Book was not manually pulled in. Canadian office officialized INTRA-CAND-WEST-PRC after the Houston office had already left for the night. | Canadian office will contact Houston office to notify them of late officialization in the future. | Y | Y | Y | Done
2001-05-07 | Eastern Books | EEL | UK Eastern | James New | C | Officialized twice. | UK Risk Management group and UK IT group are trying to resolve the issue. | N | N | N | Done
2001-05-07 | UK Metals | EEL | UK Metals | James New | D1 | No positions in these books due to problems with the file load. Size of data was too big for table to calculate. | DBA will need to increase system size to accommodate file size. | N | N | N | Done
2001-05-07 | Continental Gas | EEL | Continental Gas | James New | C | Incorrect curve loaded. Position came in ok. | UK Risk Management group working to resolve the problem. | N | N | Y | Done
2001-05-07 | UK Power & UK Continental Power Books | EEL | UK Power, Continental Power | James New | D1 | There was an EN-Power server issue. Positions eventually came in. | UK Risk Management group and UK IT group are trying to resolve the issue. | N | N | N | Done
2001-05-04 | PAPER-EUROPE-PRC | EGM | Paper | Kris Hanson | C | Book was not officialized. Relatively new person in position. Book was reofficialized at 8 am. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. Training of staff. | Y | Y | Y | Done
2001-05-04 | PWR-EA-PWCN-OPT-PRC, PWR-EA-PWNT-OPT-PRC, PWR-EAST-PWCN-PRC, PWR-EAST-PWNT-PRC, PWR-EAST-PWQJ-PRC, PWR-EAST-PWTC-PRC | EA-POWER | US Power | Stacey White | F | Power books no longer being calc'ed and has no positions. | Need to make inactive in RisktRAC and CAS. | N | N | N | Done
2001-05-04 | FT-BRIDGE-SUBA-GDL | EA-GAS | US Gas |  | C | Book was not officialized. Relatively new person in position. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. Training of staff. | N | N | N | Done
2001-05-04 | EPMI-HRLY-ERCOT-PRC, EPMI-ST-WHOURLY-PRC | EA-POWER | US Power | Stacey White | C | Book was not officialized as book is flat and contains no positions. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. | N | N | N | Done
2001-05-04 | EPMI-ETOWN-SVC-PRC, EPMI-LTON-SVCE-PRC, PWR-GD-LT-OPTB-GDL, PWR-GD-LT-OPTB-PRC | EA-POWER | US Power | Stacey White | C | New books. There are no positions in these books as yet. Books should be marked and considered active in the future. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. | N | N | N | Done
2001-05-03 | WEATHER-NG-PRC | EA-GAS | US Gas | Todd Hall | C | Book not officialized. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process. Weather Risk Mgmt. Group to be trained on using Active/Inactive book website. | Y | Y | N | Done
2001-05-03 | FT-CAND-ROLLOFF-BAS, FT-CAND-ROLLOFF-IDX | EA-GAS | US Gas | Brian Gills | C | No positions in these books. | Books will be marked inactive in RiskTrac. | N | N | N | Done
2001-05-02 | GD-MARKET-BAS, GD-MARKET-GDL, GD-MARKET-PRC, INTRA-CES-ENTGY-IDX, INTRA-CES-ENTGY-PRC, INTRA-CES-ENTGY-BAS | EA-GAS | US Gas | Jeff Gossett/ Greg Whiting | F | Books marked as inactive need to be officialized at month-end to meet accounting liquidation requirement. | Greg Whiting will contact Jeff Gossett to determine a solution to the problem. | N | N | N | Done
2001-05-02 | UK Gas | EEL | UKGAS | UK IT Gas | D1 | Experienced problems sending their feed. Valuation system not working due to a change in the front end system on the gas desk. | UK IT group re-sent the file and it processed into Risktrac correctly. | N | Y | N | Done
2001-05-01 | PWR-MG-GS-MTM-GLD | EA-POWER | US Power | Stacey White | C | Book not officialized. | Website was utilized, but book was assigned to incorrect trading group. | Y | Y | Y | Done
2001-05-01 | ERAC-ERMS-XL-PRC, HGO-ERMS-XL-PRC, PROD-ERMS-XL-PRC, RLL-ERMS-XL-PRC | EGM | Global Products | Todd Hall | C | Books not officialized. Book Administrator misunderstood the uploading process. | Training of staff. | Y | Y | Y | Done
2001-05-01 | LT-TRANS-CE-(BAS, GDL, IDX,PRC), LT-TRANS-WE-(BAS, GDL, IDX,PRC) | EA-GAS | US Gas | Jeff Gossett | C | Books were new and should have been made inactive. | Positions in Central and West books need to be rolled to books LT-TRANS-EA-(BAS, GDL, IDX,PRC) | N | N | N | Done
2001-05-01 | INTRA-DENVER-BAS, INTRA-DENVER-IDX | EA-GAS | US Gas | Jeff Gossett | C | Books not officialized. | Books will be marked inactive in RiskTrac | N | N | N | Done
2001-05-01 | FT-CENT-IDX | EA-GAS | US Gas | Jeff Gossett | C | Book not officialized. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process | N | Y | Y | Done
2001-05-01 | US-UK-ARB-02GO-PRC, US-UK-GO-ARB-PRC, US-UK-GR-ARB-GOI-PRC, US-UK-GR-HO-ARB-PRC, US-UK-GR-KE-ARB-PRC, US-UK-GR-KR-ARB-PRC, US-UK-HO-ARB-PRC, US-UK-KE-ARB-PRC, US-UK-KERO-ARB-PRC | EGM | Global Products | Todd Hall | C | No more activity in these books. | Books need to be officialized with a zero position. | N | Y | N | Done
2001-04-30 | GD-TEXAS-GDL & ST-BAMMEL-HPL-GDL | EA-GAS | US Gas | Jeff Gossett | C | Books not officialized. | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process | N | Y | N | Done
2001-04-30 | UKGASGSA1 | EEL | UK Gas | James New |  | To be determined |  |  |  |  | Done
2001-04-27 | INTRA-CAND-WEST-BAS | EA-CAN | Canada | Peggy Hedstrom | C | Book not officialized | Implement Active/Inactive website.Canada Risk Mgmt. Group to be trained on using Active/Inactive book website. |  |  |  | Done
2001-04-27 | INTRA-CAND-WEST-PRC | EA-CAN | Canada | Peggy Hedstrom | C | Book not officialized | Implement Active/Inactive website.Canada Risk Mgmt. Group to be trained on using Active/Inactive book website. |  |  |  | Done
2001-04-27 | UK Power | EEL | UK Power | Houston IT | D1 | UK Power feed came in late 6:20. | Server slow. | Y | Y | N | Done
2001-04-27 | Misc. Books | EGM | Agricultural Books | Sheila Glover | C | BA officialized books for the 12th, 17th, & 18th. Credit picked up information again. | Training of staff. | N | Y | N | Done
2001-04-27 | E-TRANSIT-ACC-PRC | EBS | EBS | Kristin Albrecht | C | EBS Risk Management Group did not complete the final stage of the spreasheet validation process. | Run RiskTrac post ID report before leaving at night. | N | Y | N | Done
2001-04-27 | E-TRANSPORT-ACC-PR | EBS | EBS | Kristin Albrecht | C | EBS Risk Management Group did not complete the final stage of the spreadsheet validation process. | Run RiskTrac post ID report before leaving at night. | N | Y | N | Done
2001-04-27 | Gas Unify |  |  |  | D2 | Unify did not feed into credit (took all night instead of 5 min.). | IT to watch more closely. 5/1 Per Debbie - done. | N | Y | N | Done
2001-04-27 | Excel format error on spreadsheet | EEL | EBS UK | Neil Tarling | C / D1 | Added extra column on spreadsheet. Did not make it to credit and Jim Fallon Monday's report. | 5/1 Format is corrected. Links in spreadsheet broke. | N | Y | N | Done
2001-04-27 | FT-NW-XL-OPT-BAS, FT-NWXL-OPT-PRC, GD-NEW-XL-OPT-BAS, GD-NEW-XL-OPT-PRC | EA | US Gas | Jeff Gossett | C | New people in group uploaded 4/26 spreadsheets when they should not have. Credit must delete. Credit should not be responsible for deleting data. | Training of new staff. Reupload with 0 MTM value the 2 books with position. 4/30 Spreadsheets reloaded | N | Y | Y | Done
2001-04-27 | INTRA-CAND-BC-BAS | EA-CAN | Canada | Jeff Gossett | C | Manual overide was not done by Houston Risk Management Group. | Address which group should be responsible (Jeff & Debbie). Done - to remain in Houston |  |  |  | Done
2001-04-26 | DPR Prelim vs Final | EES | EES Gas | Warren Prihoda | A | Park Place deal was not booked at prelim. | Ensure deals are captured same day (Review Global Standards) | N | Y | Y | Done
2001-04-26 | FT-WEST-IDX | EA-GAS | West Gas | Darron Giron | C | Books not officialized | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process | N | Y | N | Done
2001-04-26 | GD-NEW-IDX | EA-GAS | West Gas | Darron Giron | C | Books not officialized | Implementation of new Active/Inactive book website should help identify any unofficialized books during end of day process | N | Y | N | Done
2001-04-26 | INTRA-CAND-BC-BAS & INTRA-CAND-BC-PRC | EA-CAN | Canada |  | D2 | They have the same credit position for two different days. Credit must go in and delete one of them. Credit should not be responsible for deleting data. | Canada book restructing project. | N | Y | N | Done
2001-04-25 | Power Unify |  |  |  | D2 | Unify did not feed into credit (took all night instead of 5 min.). Start up of sequel server 2000 was the cause. | IT to watch more closely. 5/1 Per Debbie - done. | N | Y | N | Done