## summary
ENRON NORTH AMERICA
Energy Services |  |  |  |  | Report Date: |  |  | 2025-09-27 00:08
Austin Energy - 2001
COST SUMMARY ($ thousands) |  |  |  |  | Expenditures to date: |  |  | As of 8/24/00
Revision # 05
Actuals
Construction Costs |  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance | %
Excluding Financing Fee | MW | as of 8/24/00 | As of 8/24/00 | As of 8/24/00 |  | As of 8/24/00 | from CE | Complete
Austin, Tx | 178 | 89457.191 | 68.989 | 89397.1 |  | 89466.089 | -8.898 | 0.07711%
TOTAL PROJECTS | 178 | 89457.191 | 68.989 | 89397.1 |  | 89466.089 | -8.898 | 0.07711%
Target $$/MW |  | 502.5685 |  |  |  | 502.6185
Actuals
Financing Costs |  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance
Project |  | as of 8/24/00 | As of 8/24/00 | As of 8/24/00 |  | As of 8/24/00 | from CE
Wilton Center, IL |  | 1500 | 0 | 1500 |  | 1500 | 0
Calvert City, KY |  | 1500 | 0 | 1500 |  | 1500 | 0
Wheatland, IN |  | 1500 | 0 | 1500 |  | 1500 | 0
TOTAL PROJECTS |  | 4500 | 0 | 4500 |  | 4500 | 0
Changes to Current Estimate Explanations
8/25 $1.2MM Adjustment to Development Expenses and EE&CC fee
Current Estimate vs Actual Variance Explanations (000s)
Nothing planned for ENA travel expenses.
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/082500.xls'#$summary

## Austin Energy
Enron North America
Enron Sandhill | [52 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/082500.xls'#$Austin Energy
Cost Summary as of August 24, 2000 | [48 empty] | 2025-09-27 00:08
[6 empty] | MW |  | 178 |  | MW | [5 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  | Anticipated
[7 empty] | Expense / | ENA |  | Increase / |  | ENA |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  | Capital | Control Budget |  | (Savings) |  | Current Estimate |  | 2000-05-31 | 2000-06-01 | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | 2000-10-31 |  | 2000-11-30 |  | 2000-12-31 |  | 2001-01-31 |  | 2001-02-28 |  | 2001-03-31 |  | 2001-04-30 |  | 2001-05-31 |  | 2001-06-30 |  | 2001-07-31 |  | 2001-08-31 | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[8 empty] | 5/1/00 |  |  |  | 8/25/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 |  | As of 8/24/00 | As of 8/24/00 |  | As of 8/24/00
MAJOR EQUIPMENT
| TURBINE UNITS - GE LM6000 (4) |  |  |  |  | ECT | Capital | 57360000 |  | 0 |  | 57360000 | [13 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 | [9 empty] | 0 | 0 |  |  |  | 57360000 |  | 57360000 |  | 0
| Other |  |  |  |  | ECT | Capital | 81000 |  | 0 |  | 81000 | [13 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 81000 |  | 81000 |  | 0
0
| Subtotal General Electric | [6 empty] | 57441000 |  | 0 |  | 57441000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 57441000 |  | 57441000 |  | 0
| SPARE PARTS | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT | Capital | 1436000 |  | 0 |  | 1436000 | [32 empty] | 0 |  |  |  | 1436000 |  | 1436000 |  | 0
| TRANSFORMERS - Other Misc Charges | [6 empty] | 0 |  |  |  | 0 | [32 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT | Capital | [37 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT | Capital | [37 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT | Capital | [37 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT | Capital | 0 |  |  |  | 0 | [32 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
[6 empty] | ECT | [38 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT | Capital |  |  | 0 | [34 empty] | 0 |  | 0
| Other |  |  |  |  | ECT | Capital | 0 |  | 0 | [34 empty] | 0 |  | 0 |  | 0 |  | 0
[49 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [6 empty] | 1436000 |  | 0 |  | 1436000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 1436000 |  | 1436000 |  | 0
| TOTAL MAJOR EQUIPMENT | [6 empty] | 58877000 |  | 0 |  | 58877000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 58877000 |  | 58877000 |  | 0
NEPCO SITE CONSTRUCTION COSTS
[14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
General Provisions
| EQUIPMENT & SMALL TOOL |  |  |  |  | Nepco | Capital | 741803 |  |  |  | 741803 | [32 empty] | 0 |  |  |  | 741803 |  | 741803 |  | 0
| PROJECT MANAGEMENT |  |  |  |  | Nepco | Capital | 1572876 |  |  |  | 1572876 | [32 empty] | 0 |  |  |  | 1572876 |  | 1572876 |  | 0
| PROJECT INDIRECTS |  |  |  |  | Nepco | Capital | 1328662 |  |  |  | 1328662 | [32 empty] | 0 |  |  |  | 1328662 |  | 1328662 |  | 0
| ENGINEERING |  |  |  |  | Nepco | Capital | 790828 |  | 0 |  | 790828 | [32 empty] | 0 |  |  |  | 790828 |  | 790828 |  | 0
| FREIGHT |  |  |  |  | Nepco | Capital | 243000 |  | 0 |  | 243000 | [32 empty] | 0 |  |  |  | 243000 |  | 243000 |  | 0
| CONTINGENCY |  |  |  |  | Nepco | Capital | 1532227 |  | 0 |  | 1532227 | [32 empty] | 0 |  |  |  | 1532227 |  | 1532227 |  | 0
| RESERVES | [5 empty] | Capital | 0 |  | 0 |  | 0 | [32 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
[10 empty] | 0 | [34 empty] | 0 |  | 0 |  | 0 |  | 0
| TOTAL General Provisions | [5 empty] | Capital | 6209396 |  | 0 |  | 6209396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6209396 | 0 | 6209396 | 0 | 0
| BOP Procurement | [43 empty] | 0
| A/G PIPING |  |  |  |  | Nepco |  | 0 |  |  |  | 0 | [32 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| A/G ELECTRICAL |  |  |  |  | Nepco |  | 0 |  |  |  | 0 | [32 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| INSTRUMENTATION |  |  |  |  | Nepco |  | 0 |  |  |  | 0 | [32 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| EQUIPMENT |  |  |  |  | Nepco |  | 14927696 |  |  |  | 14927696 | [32 empty] | 0 |  |  |  | 14927696 |  | 14927696 |  | 0
| TOTAL BOP Procurement | [5 empty] | Capital | 14927696 |  | 0 |  | 14927696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14927696 | 0 | 14927696 | 0 | 0
Construction
| SITE PREPARATION/IMPROVEMENTS | [6 empty] | 404846 |  |  |  | 404846 | [32 empty] | 0 |  |  |  | 404846 |  | 404846 |  | 0
| UNDERGROUND ELECTRICAL | [6 empty] | 469736 |  |  |  | 469736 | [32 empty] | 0 | 0 |  | 0 | 469736 | 469736 | 469736 | 1409208 | 0
| UNDERGROUND PIPING | [6 empty] | 317869 |  |  |  | 317869 | [32 empty] | 0 |  |  |  | 317869 |  | 317869 |  | 0
| CONCRETE | [6 empty] | 752981 |  |  |  | 752981 | [32 empty] | 0 |  |  |  | 752981 |  | 752981 |  | 0
| GROUT | [6 empty] | 41482 |  |  |  | 41482 | [32 empty] | 0 | 0 |  | 0 | 41482 | 41482 | 41482 | 124446 | 0 | 248892 | 497784 | 995568
| STRUCTURAL STEEL | [6 empty] | 44805 |  |  |  | 44805 | [32 empty] | 0 |  |  |  | 44805 |  | 44805 |  | 0
| ARCHITECTURAL | [6 empty] | 2724 |  |  |  | 2724 | [32 empty] | 0 |  |  |  | 2724 |  | 2724 |  | 0
| BUILDINGS | [6 empty] | 105033 |  |  |  | 105033 | [32 empty] | 0 |  |  |  | 105033 |  | 105033 |  | 0
| A/G PIPING | [6 empty] | 1095979 |  |  |  | 1095979 | [32 empty] | 0 |  |  |  | 1095979 |  | 1095979 |  | 0
| A/G ELECTRICAL | [6 empty] | 804952 |  |  |  | 804952 | [32 empty] | 0 |  |  |  | 804952 |  | 804952 |  | 0
| INSTRUMENTATION | [6 empty] | 155089 |  |  |  | 155089 | [32 empty] | 0 |  |  |  | 155089 |  | 155089 |  | 0
| INSULATION & PAINTING | [6 empty] | 184616 |  |  |  | 184616 | [32 empty] | 0 |  |  |  | 184616 |  | 184616 |  | 0
| MECHANICAL EQUIPMENT | [6 empty] | 672551 |  |  |  | 672551 | [32 empty] | 0 |  |  |  | 672551 |  | 672551 |  | 0
| PLANT STARTUP | [6 empty] | 838916 |  |  |  | 838916 | [32 empty] | 0 |  |  |  | 838916 |  | 838916 |  | 0
| SCOPE CHANGES - SCR Modification & Sequence of Events | [6 empty] | 0 |  | 125000 |  | 125000 | [32 empty] | 0 |  | 0 |  | 125000 |  | 125000 |  | 0
| TOTAL Construction | [6 empty] | 5891579 |  | 125000 |  | 6016579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6016579 | 511218 | 6016579 | 1533654 | 0 | 248892
| SWITCHYARD | [6 empty] | 0 |  |  |  | 0 | #REF! |  | #REF! | [30 empty] | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [6 empty] | 27028671 |  | 125000 |  | 27153671 | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | 27153671 | #REF! | 27153671 | #REF! | 0 | #REF!
OVERHEADS & FEES
| EE&CC |  |  |  |  | EECC | Capital | 0 |  | 500000 |  | 500000 | [5 empty] | 31282 | [26 empty] | 31282 |  | 0 |  | 468718 |  | 500000 |  | 0
| NEPCO |  |  |  |  | NEPCO | Capital | 1701329 |  | 0 |  | 1701329 | [32 empty] | 0 |  | 0 |  | 1701329 |  | 1701329 |  | 0
| BASE FEE |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other (Warranty) | [5 empty] | Capital | 25000 |  | 0 |  | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 25000 |  | 25000 |  | 0
[49 empty] | 0 |  |  |  | 0
| TOTAL OVERHEADS & FEES | [6 empty] | 1726329 |  | 500000 |  | 2226329 |  | 0 |  | 0 |  | 31282 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 31282 |  | 0 |  | 2195047 |  | 2226329 |  | 0
ADDERS SANDHILL
| Other |  |  |  |  | ECT | Capital | 668000 |  | 0 |  | 668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 668000 |  | 668000 |  | 0
0
| TOTAL ADDERS | [6 empty] | 668000 |  | 0 |  | 668000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 668000 |  | 668000 |  | 0
TOTAL NEPCO & EE&CC SCOPE | [7 empty] | 88300000 |  | 625000 |  | 88925000
MOBILIZATION OF O&M
| Mobilization Fee OEC |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | [32 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Reimbursble Costs OEC | [5 empty] | Capital | 0 |  | 0 |  | 0 | [32 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
SALES TAX ON EQUIPMENT | [5 empty] | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
SPARE PARTS | [5 empty] | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
ENVIRONMENTAL COSTS
| Air Permitting - ENSR | [5 empty] | Expense | 0 |  | 20000 |  | 20000 |  | 0 |  | 403 |  | 0 |  | 6406 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6809 |  | 0 |  | 13191 |  | 20000 |  | 0
| Waste Water Discharge | [5 empty] | Expense | 0 |  | 10000 |  | 10000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 10000 |  | 10000 |  | 0
| Nox Testing | [5 empty] | Expense |  |  | 10000 |  | 10000 |  | 0 |  | 0 | [28 empty] | 0 |  | 0 |  | 10000 |  | 10000 |  | 0
Other
| Subtotal Environmental Costs | [6 empty] | 0 |  | 40000 |  | 40000 |  | 0 |  | 403 |  | 0 |  | 6406 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6809 |  | 0 |  | 33191 |  | 40000 |  | 0
ELECTRICAL INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 22000 |  | 22000 |  | 22000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0 | 22000 |  | 0 |  | 0 |  | 22000 |  | 0
GAS INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Startup Fuel
| Power Sales | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
INSURANCE DURING CONSTR | [6 empty] | Capital | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
CAPITALIZED SALARIES | [6 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [24 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
DEVELOPMENT EXPENSES
| Salaries | [5 empty] | Expense | 0 |  | 0 | [34 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Travel Expenses | [5 empty] | Expense | 0 |  | 0 |  | 0 |  | 1627 |  | 2688 |  | 217 |  | 4366 | [24 empty] | 8898 |  | 0 |  | 0 |  | 8898 |  | -8898
| Consulting - TurnerCollie & Braden | [5 empty] | Expense | 0 |  | 136000 |  | 136000 | [32 empty] | 0 |  | 0 |  | 136000 |  | 136000 |  | 0
| Consulting - GLC (Bill Stokes) | [5 empty] | Expense | 0 |  | 209191 |  | 209191 | [32 empty] | 0 |  | 0 |  | 209191 |  | 209191 |  | 0
| Geotechnical Report | [5 empty] | Expense | 0 |  | 65000 |  | 65000 | [32 empty] | 0 |  | 0 |  | 65000 |  | 65000 |  | 0
| Gene Preston - Transmission consultant | [5 empty] | Expense |  |  | 10000 |  | 10000 | [32 empty] | 0 |  | 0 |  | 10000 |  | 10000 |  | 0
| Other | [8 empty] | 0 | [34 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| TOTAL DEVELOPMENT EXPENSE | [6 empty] | 0 |  | 420191 |  | 420191 | 0 | 1627 | 0 | 2688 | 0 | 217 | 0 | 4366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898 | 0 | 0 | 0 | 420191 | 0 | 429089 | 0 | -8898
LEGAL EXPENSES
| Vinson & Elkins | [5 empty] | Expense | 0 |  | 0 | [34 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Bracewell & Patterson | [8 empty] | 10000 |  | 10000 | [32 empty] | 0 |  | 0 |  | 10000 |  | 10000 |  | 0
| Other | [5 empty] | Expense | 0 |  | 10000 |  | 10000 | [32 empty] | 0 |  | 0 |  | 10000 |  | 10000 |  | 0
[45 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [6 empty] | 0 | 0 | 20000 | 0 | 20000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 20000 |  | 20000 |  | 0
INTEREST DURING CONSTRUCTION (6.5%) | [6 empty] | Capital | 0 |  | 0 |  | 0 | [32 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
ENA TOTAL Project Costs | [7 empty] | 0 |  | 502191 |  | 502191 | #REF! | 23627 | #REF! | 3091 | #REF! | 217 | #REF! | 10772 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | 37707 | #REF! | 0 | #REF! | 473382 | #REF! | 511089 | #REF! | -8898 | #REF!
CONTINGENCY (5% of Development Costs) | [6 empty] | Capital | 0 |  | 30000 |  | 30000 | [33 empty] | 2030320 |  | 2030320 | 30000 | 2030320 | 30000 | 2030320 | 0
GRAND TOTAL | [7 empty] | 88300000 |  | 1157191 |  | 89457191 | #REF! | 23627 | #REF! | 3091 | #REF! | 31499 | #REF! | 10772 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | 68989 | #REF! | 0 | #REF! | 89397100 | #REF! | 89466089 | #REF! | -8898
$/Kw