## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - May 1, 2001 Through December 31, 2001
NORTHERN & TRANSWESTERN Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted September 12, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17395 | ALB | CRAWFORD | 756 | CLEAN & INHIBIT THE CRAWFORD LOOP 16 | 2001-10-15 07:00 | 2001-10-18 16:00 | 3.4 |  | OPS |  | 20 | 67.5 | Flow will need to be cut from 54 mmcf/day to 40 mmcf/day. Arther Pue farm tap & Highlands Crawford Delivery will be shut in so that no chemical will get into the system. |  |  |  | 0 | P | N | N
2 | 17216 | ALB | KINGMAN | PG&E STN | PG&E MEAS STN | 2001-09-19 07:00 | 2001-09-20 07:00 | 1 |  | OPS |  | 200 | 200 | Change out filters and econ filter case at PG&E/TW Measurement Station. The flow at PG&E and South Socal will be taken to zero. (Approx. 200 mmcfd) |  |  |  | 0 | P | N | N
3 | 17355 | ALB | STATION 1 | 103 | MAINTENANCE | 2001-09-13 07:00 | 2001-09-14 16:00 | 1.4 |  | OPS |  | 50 | 68.8 | Maintenance. |  |  |  | 0 | U | N | N
4 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
5 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
6 | 17478 | AMA | BEAVER PLANT | A LINE | A LINE REPAIR | 2001-09-12 12:00 | 2001-09-12 16:00 | 4.3 |  | OPS |  | 45 | 195 | A line repair north of the Beaver Plant. |  |  |  | 0 | P | N | N
7 | 17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-15 08:00 | 2001-10-20 16:00 | 5.3 |  | OPS |  | 2 | 10.7 | Install new Opto control Panel 1500 Hr. Inspection |  |  |  | 0 | P | N | N
8 | 17473 | AMA | NORTHRUP | 1 | OIL SEAL | 2001-09-13 08:00 | 2001-09-14 16:00 | 1.3 |  | OPS |  | 8 | 10.7 | P-3 will replace compressor oil seal on the compressor crankshaft. 1042 HP |  |  |  | 0 | P | N | N
9 | 17062 | BEA | BUSHTON | 23 24 25 | AFTER COOLER TOWERS | 2001-10-02 07:30 | 2001-10-03 18:00 | 1.5 |  | 453 | C.014662 |  |  | Install new Marley aftercooler towers. (We will need to shut in injections during this outage.The net flow to storage can be made up by flowing higher injections before and after the outage.). |  |  |  | 0 | P | N | N
10 | 16935 | BEA | BUSHTON |  | LYONS FUEL GAS | 2001-10-02 08:00 | 2001-10-03 16:00 | 1.3 |  | 453 | C.014723 | 0 | 0 | Install 500 000 BTU/hr heater on the main fuel gas supply line and connect the Lyons gas into the main plant fuel gas. Also install filter/separator on the Lyons supply gas line. |  |  |  | 0 | P | N | N
11 | 17472 | BEA | BUSHTON | ALL | ESD | 2001-10-10 09:00 | 2001-10-10 14:00 | 0.2 |  | OPS |  | 0 | 0 | ESD Bushton Comp Station using Yale enclosures. While station is down complete maint. job tasks. |  |  |  | 0 | P | N | N
12 | 17155 | BEA | CUNNINGHAM | 6 | OVERHAUL | 2001-10-08 08:00 | 2001-10-26 16:00 | 18.3 |  | OPS |  | 0 | 0 | Major overhaul on MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Actual start date is tentative). |  |  |  | 0 | P | N | N
13 | 17332 | BEA | CUNNINGHAM | ALL | ELEC SWITCH GEAR | 2001-11-12 07:00 | 2001-11-16 16:00 | 4.4 |  | OPS |  | 0 | 0 | Electric test switch gear and 4000 volt motors. |  |  |  | 0 | P | N | N
14 | 17309 | LIB | HUGOTON | 16 | MAJOR OVERHAUL | 2001-09-10 08:00 | 2001-10-12 16:00 | 32.3 |  | OPS |  | 8 | 258.7 | Major overhaul on a GMVC-10 power and compressor end based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  | 2001-09-10 08:00 |  | 0 | P | N | N
15 | 17364 | MID | KERMIT | K-B 30" | KERMIT SETTLING WORK | 2001-09-11 07:00 | 2001-09-12 07:00 | 1 |  | OPS |  | 350 | 350 | Need to blow 7 miles of the K-B line back to the first block valve north of Kermit. To replace a valve and correct earth settling on some of the pipe. |  |  |  | 0 | P | N | N
16 | 17422 | MIN | VENTURA | HANLONTOWN | HANLONTOWN VALVE | 2001-09-11 09:00 | 2001-09-11 14:00 | 0.2 |  | OPS |  | 0 | 0 | Replace outlet valve to Hanlontown located at the Fertile TBS. Fertile and Hanlontown will be fed using bottle trucks with 7 farm tap customers being shut off during the replacement. |  |  |  | 0 | P | N | N
17 | 17423 | MIN | VENTURA | STATION | INLET VALVE | 2001-09-12 08:00 | 2001-09-12 12:00 | 0.2 |  | OPS |  | 0 | 0 | Change out station inlet valve using bottle trucks to maintain town. 1 ftp customer. Affects Meservey BL |  |  |  | 0 | P | N | N
18 | 17177 | MIN | WILLMAR | BROWERVILLE BL | BROWERVILLE BL | 2001-09-17 08:00 | 2001-09-21 16:00 | 4.3 | MNB70501 | 453 | C.014814 | 0 | 0 | Replace and lower 120' of 3" pipe across County Road 88 on the Browerville BL at MP 4.85. Tie in will require bottle trucks to feed TBS. Landowners on FTP's at MP 3.213 and 7.274 will have to be notified and will be out of service during the pipeline r | emoval and tie in of the new segment. |  |  | 0 | P | N | N

## LetterSizeRegionLoc (2)
ETS Planned And Unplanned Outages - May 1, 2001 Through December 31, 2001
NORTHERN & TRANSWESTERN Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted September 12, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17395 | ALB | CRAWFORD | 756 | CLEAN & INHIBIT THE CRAWFORD LOOP 16 | 2001-10-15 07:00 | 2001-10-18 16:00 | 3.4 |  | OPS |  | 20 | 67.5 | Flow will need to be cut from 54 mmcf/day to 40 mmcf/day. Arther Pue farm tap & Highlands Crawford Delivery will be shut in so that no chemical will get into the system. |  |  |  | 0 | P | N | N
2 | 17216 | ALB | KINGMAN | PG&E STN | PG&E MEAS STN | 2001-09-19 07:00 | 2001-09-20 07:00 | 1 |  | OPS |  | 200 | 200 | Change out filters and econ filter case at PG&E/TW Measurement Station. The flow at PG&E and South Socal will be taken to zero. (Approx. 200 mmcfd) |  |  |  | 0 | P | N | N
3 | 17355 | ALB | STATION 1 | 103 | MAINTENANCE | 2001-09-13 07:00 | 2001-09-14 16:00 | 1.4 |  | OPS |  | 50 | 68.8 | Maintenance. |  |  |  | 0 | U | N | N
4 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-10-22 08:00 | 2001-10-26 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
5 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-05 08:00 | 2001-11-07 16:00 | 2.3 |  | OPS |  | 130 | 303.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
6 | 17478 | AMA | BEAVER PLANT | A LINE | A LINE REPAIR | 2001-09-12 12:00 | 2001-09-12 16:00 | 4.3 |  | OPS |  | 45 | 195 | A line repair north of the Beaver Plant. |  |  |  | 0 | P | N | N
7 | 17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-15 08:00 | 2001-10-20 16:00 | 5.3 |  | OPS |  | 2 | 10.7 | Install new Opto control Panel 1500 Hr. Inspection |  |  |  | 0 | P | N | N
8 | 17473 | AMA | NORTHRUP | 1 | OIL SEAL | 2001-09-13 08:00 | 2001-09-14 16:00 | 1.3 |  | OPS |  | 8 | 10.7 | P-3 will replace compressor oil seal on the compressor crankshaft. 1042 HP |  |  |  | 0 | P | N | N
9 | 17062 | BEA | BUSHTON | 23 24 25 | AFTER COOLER TOWERS | 2001-10-02 07:30 | 2001-10-03 18:00 | 1.5 |  | 453 | C.014662 |  |  | Install new Marley aftercooler towers. (We will need to shut in injections during this outage.The net flow to storage can be made up by flowing higher injections before and after the outage.). |  |  |  | 0 | P | N | N
10 | 16935 | BEA | BUSHTON |  | LYONS FUEL GAS | 2001-10-02 08:00 | 2001-10-03 16:00 | 1.3 |  | 453 | C.014723 | 0 | 0 | Install 500 000 BTU/hr heater on the main fuel gas supply line and connect the Lyons gas into the main plant fuel gas. Also install filter/separator on the Lyons supply gas line. |  |  |  | 0 | P | N | N
11 | 17472 | BEA | BUSHTON | ALL | ESD | 2001-10-10 09:00 | 2001-10-10 14:00 | 0.2 |  | OPS |  | 0 | 0 | ESD Bushton Comp Station using Yale enclosures. While station is down complete maint. job tasks. |  |  |  | 0 | P | N | N
12 | 17155 | BEA | CUNNINGHAM | 6 | OVERHAUL | 2001-10-08 08:00 | 2001-10-26 16:00 | 18.3 |  | OPS |  | 0 | 0 | Major overhaul on MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (Actual start date is tentative). |  |  |  | 0 | P | N | N
13 | 17332 | BEA | CUNNINGHAM | ALL | ELEC SWITCH GEAR | 2001-11-12 07:00 | 2001-11-16 16:00 | 4.4 |  | OPS |  | 0 | 0 | Electric test switch gear and 4000 volt motors. |  |  |  | 0 | P | N | N
14 | 17309 | LIB | HUGOTON | 16 | MAJOR OVERHAUL | 2001-09-10 08:00 | 2001-10-12 16:00 | 32.3 |  | OPS |  | 8 | 258.7 | Major overhaul on a GMVC-10 power and compressor end based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  | 2001-09-10 08:00 |  | 0 | P | N | N
15 | 17364 | MID | KERMIT | K-B 30" | KERMIT SETTLING WORK | 2001-09-11 07:00 | 2001-09-12 07:00 | 1 |  | OPS |  | 350 | 350 | Need to blow 7 miles of the K-B line back to the first block valve north of Kermit. To replace a valve and correct earth settling on some of the pipe. |  |  |  | 0 | P | N | N
16 | 17422 | MIN | VENTURA | HANLONTOWN | HANLONTOWN VALVE | 2001-09-11 09:00 | 2001-09-11 14:00 | 0.2 |  | OPS |  | 0 | 0 | Replace outlet valve to Hanlontown located at the Fertile TBS. Fertile and Hanlontown will be fed using bottle trucks with 7 farm tap customers being shut off during the replacement. |  |  |  | 0 | P | N | N
17 | 17423 | MIN | VENTURA | STATION | INLET VALVE | 2001-09-12 08:00 | 2001-09-12 12:00 | 0.2 |  | OPS |  | 0 | 0 | Change out station inlet valve using bottle trucks to maintain town. 1 ftp customer. Affects Meservey BL |  |  |  | 0 | P | N | N
18 | 17177 | MIN | WILLMAR | BROWERVILLE BL | BROWERVILLE BL | 2001-09-17 08:00 | 2001-09-21 16:00 | 4.3 | MNB70501 | 453 | C.014814 | 0 | 0 | Replace and lower 120' of 3" pipe across County Road 88 on the Browerville BL at MP 4.85. Tie in will require bottle trucks to feed TBS. Landowners on FTP's at MP 3.213 and 7.274 will have to be notified and will be out of service during the pipeline r | emoval and tie in of the new segment. |  |  | 0 | P | N | N