## Sooner 01
Owner Name | OG&E Electric Service
Station Name | Sooner Power Station
Unit Name | Sooner 01
NERC Region | SPP
State | OK
Fuel Type | Coal
Capacity | 568 MW
Start Date | 2001-10-08
End Date | 2001-12-02
Prv. Start Date | 2001-09-21
Prv. End Date | 2001-11-15
Comments | Turb O/H--Didn't have enough man power to do the work now
SIC | 4911
Plant ID | 1013000
Unit ID | 1006549
Outage ID | 12579

## Donald Cook 01
Owner Name | AEP
Station Name | Donald C Cook Nuclear Power Station
Unit Name | Donald C Cook 01
NERC Region | ECAR
State | MI
Fuel Type | Nuclear
Capacity | 1,152 MW
Start Date | 2001-08-27
End Date | 2001-09-28
Prv. Start Date | 2001-08-27
Prv. End Date | 2001-09-23
Comments | Water pump repairs. Still in cold shutdown. Will be down for another week.
SIC | 4911
Plant ID | 1000365
Unit ID | 1005087
Outage ID | 18167