## Sheet1
LDs for GE-Equipment Late Delivery Dates For TECO's Project
LD Rates & Dates
|  | 5500 | 10000 | 15000
Item | Delivered On | Bet' 1/31 & 2/14 | Bet' 2/15 & 3/1 | Bet' 3/2 & >> | LDs ($)
Wrong torque converter data was originally delivered 4-23-00 | 2000-04-23 | 15 | 15 | 51 | 997500
Wrong Mark-5 Software was originally delivered 4-27-00 | 2000-04-27 | 15 | 15 | 56 | 1072500
Wrong insulation size for inlet bleed heat was originally delivered 4-13-00 | 2000-04-13 | 15 | 15 | 41 | 847500
Wrong Inlet Housing was originally delivered 3-8-00 | 2000-03-08 | 15 | 15 | 32 | 712500
Wrong enclosure wall was originally delivered 3-2-00 | 2000-03-02 | 15 | 15 | 1 | 247500
Valve, Stop-Fuel Gas 4-18-00 | 2000-04-18 | 15 | 15 | 46 | 922500
Unistrut piping 4-25-00 | 2000-04-25 | 15 | 15 | 53 | 1027500
Turbine Filters Shipped (short 6) 4-6-00 | 2000-04-06 | 15 | 15 | 34 | 742500
Transducer Arrgt 4-27-00 Fla. Power Intersection City, FL | 2000-04-27 | 15 | 15 | 55 | 1057500
Terminal Board 5-1-00 | 2000-05-01 | 15 | 15 | 59 | 1117500
RST analog I/O Board 4-24-00 | 2000-04-24 | 15 | 15 | 52 | 1012500
Pressure gage assembly (short) 5-9-00 | 2000-05-09 | 15 | 15 | 68 | 1252500
Orifice Plates (cooling water) 4-28-00 | 2000-04-28 | 15 | 15 | 56 | 1072500
Generator Fire Protection Chemtron 4-20-00 | 2000-04-20 | 15 | 15 | 48 | 952500
Elec. Power Meter 3-23-00 | 2000-03-23 | 15 | 15 | 21 | 547500
Diode for closing coil (pacs) 5-1-00 | 2000-05-01 | 15 | 15 | 59 | 1117500
Clips for filter house filters 4-13-00 | 2000-04-13 | 15 | 15 | 41 | 847500
chemtron 1-nozzel initial/1 nozzel extended 4-26-00 | 2000-04-26 | 15 | 15 | 54 | 1042500
Chemtron 120v-60 hz 124 vpc sol plt vlvasy 4-20-00 | 2000-04-20 | 15 | 15 | 48 | 952500
Bolts missing from Turbine Housing 4-4-00 | 2000-04-04 | 15 | 15 | 32 | 712500
Bolts and washers-- Misc. (Braden Manuf) Duct 3-15-00 | 2000-03-15 | 15 | 15 | 13 | 427500
Bolt and washers for exhaust-Misc. 3-23-00 | 2000-03-23 | 15 | 15 | 21 | 547500
6 pre-filters turbine 4-20-00 | 2000-04-20 | 15 | 15 | 48 | 952500
5 ea. 90 degree Iron Elbow 4-17-00 | 2000-04-17 | 15 | 15 | 45 | 907500
4 gaskets 4-19-00 | 2000-04-19 | 15 | 15 | 47 | 937500
3-split flange kits 3-9-00 | 2000-03-09 | 15 | 15 | 7 | 337500
3 ea. Union threaded 4-28-00 | 2000-04-28 | 15 | 15 | 56 | 1072500
2 strainers for gas and fuel systems 4-24-00 | 2000-04-24 | 15 | 15 | 52 | 1012500
15' rigid conduit 4-14-00 | 2000-04-14 | 15 | 15 | 42 | 862500
1 warning sign Instl 4-3-00 | 2000-04-03 | 15 | 15 | 31 | 697500
Contract LDs Dates:
Jan 31 through Feb 14 = $5,500
Feb 15 through Mar 1 = $10,000
Mar 2 and later = $15,000