## Hope Creek 01
Owner Name | PSEG Power LLC
Station Name | Hope Creek Nuclear Power Station
Unit Name | Hope Creek 01
NERC Region | MAAC
State | NJ
Fuel Type | Nuclear
Capacity | 1,170 MW
Start Date | 2001-10-10
End Date | 2001-10-28
Prv. Start Date | 2001-10-12
Prv. End Date | 2001-10-30
Comments | Refueling
SIC | 4931
Plant ID | 1012731
Unit ID | 1004437
Outage ID | 11864

## Powerton 06
Owner Name | Midwest Generation LLC
Station Name | Powerton Power Station
Unit Name | Powerton 06
NERC Region | MAIN
State | IL
Fuel Type | Coal
Capacity | 893 MW
Start Date | 2002-03-02
End Date | 2002-05-24
Prv. Start Date | 2001-10-10
Prv. End Date | 2002-01-02
Comments | Very extensive piping replacement work scheduled, postponed until contractor was signed. Just had meeting yesterday about Moving to March.
SIC | 4931
Plant ID | 1013200
Unit ID | 1006937
Outage ID | 12159

## Salem 01
Owner Name | PSEG Power LLC
Station Name | Salem Nuclear Power Station
Unit Name | Salem 01
NERC Region | MAAC
State | NJ
Fuel Type | Nuclear
Capacity | 1170
Start Date | 2001-09-24
End Date | 2001-10-30
Prv. Start Date | 2001-09-24
Prv. End Date | 2001-10-10
Comments | Valve Repairs
SIC | 4931
Plant ID | 1018459
Unit ID | 1004455
Outage ID | 18526

## Rockingham CT 03
Owner Name | Rockingham Power LLC
Station Name | Rockingham County Merchant Power Station
Unit Name | Rockingham 03
NERC Region | SERC
State | NC
Fuel Type | Natural Gas
Capacity | 160 MW
Start Date | 2001-10-25
End Date | 2001-11-07
Prv. Start Date | 2001-09-28
Prv. End Date | 2001-10-11
Comments | Comb Inspection
SIC | 4931
Plant ID | 1035773
Unit ID | 1012400
Outage ID | 13532

## Rockingham CT 01
Owner Name | Rockingham Power LLC
Station Name | Rockingham County Merchant Power Station
Unit Name | Rockingham 01
NERC Region | SERC
State | NC
Fuel Type | Natural Gas
Capacity | 160 MW
Start Date | 2001-10-25
End Date | 2001-11-07
Prv. Start Date | 2001-09-28
Prv. End Date | 2001-10-11
Comments | Comb Inspection
SIC | 4931
Plant ID | 1035773
Unit ID | 1012395
Outage ID | 13530

## Nueces Bay 07
Owner Name | AEP - Central Power & Light Company
Station Name | Nueces Bay Power Station
Unit Name | Nueces Bay 07
NERC Region | ERCOT
State | TX
Fuel Type | Natural Gas
Capacity | 351 MW
Start Date | 2001-10-26
End Date | 2001-12-06
Prv. Start Date | 2001-10-10
Prv. End Date | 2001-11-20
Comments | Turbine / Generator Overhaul
SIC | 4911
Plant ID | 1014405
Unit ID | 1008100
Outage ID | 13538