## LegalSizeRegionLoc
ETS Planned And Unplanned Outages - October 1, 2001 Through November, 2001
NORTHERN & TW REGIONS Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 10, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-11-10 08:00 | 2001-11-14 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
2 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-17 08:00 | 2001-11-21 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
3 | 16752 | ALB | STATION 8 | ALL | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  | 2001-09-04 08:00 |  | 0 | P | N | N
4 | 17663 | AMA | BEAVER 13 | 1 | REPLACE STUDS | 2001-10-03 13:00 | 2001-10-12 16:00 | 9.1 |  | OPS |  | 5 | 45.6 | Replace compressor cylinder studs. |  | 2001-10-03 13:00 |  | 0 | U | N | N
5 | 17447 | AMA | ELLIS 1 | 1 | 1500 HR INSP | 2001-10-11 09:00 | 2001-10-11 12:00 | 0.1 |  | OPS |  | 2 | 0.3 | 1500 Hr Inspection. Install new throttle linkage. 506 HP |  |  |  | 0 | P | N | N
6 | 17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-15 08:00 | 2001-10-20 16:00 | 5.3 |  | OPS |  | 2 | 10.7 | Install new Opto control Panel 1500 Hr. Inspection |  |  |  | 0 | P | N | N
7 | 17450 | AMA | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 |  | OPS |  | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  |  | 0 | P | N | N
8 | 17354 | BEA | BEATRICE | BEA/PAL | BEATRICE/PALMYRA CASING | 2001-10-08 07:00 | 2001-10-12 15:00 | 4.3 | NEM590B | OPS |  | 0 | 0 | Remove casing from abandoned railroad ROW on the 24" Beatrice-Palmyra at MP 2.82. Contract Services will be utilized for removal process. |  |  |  | 0 | P | N | N
9 | 16952 | BEA | BEATRICE | C LINE | TRAILBLAZER TO C LINE | 2001-10-18 08:00 | 2001-10-19 08:00 | 1 |  | 453 | C.014625 | 230 | 230 | Install a new line from the Trailblazer line to the C line and modify existing valve to allow the TB to A line tie-over to be utilized. (TB line will require a 16 hour outage where there will be no flow from Trailblazer). Blk Vlv 63101 BBB01 will be clos | ed to isolate the line segment. C line suction upstream of ML block vlv will also require an outage. |  |  | 0 | P | N | N
10 | 17472 | BEA | BUSHTON | ALL | ESD | 2001-10-11 09:00 | 2001-10-11 14:00 | 0.2 |  | OPS |  | 0 | 0 | ESD Bushton Comp Station using Yale enclosures. While station is down complete maint. job tasks. |  |  |  | 0 | P | N | N
11 | 17497 | BEA | BUSHTON | CONTROLLER #5 | CHECK VALVE | 2001-10-16 08:00 | 2001-10-16 15:00 | 0.3 |  | OPS |  | 130 | 37.9 | Remove check valve flapper from controller 5 check valve. (This date is tentative). Outage depends on approval and when Jomax Const can start. |  |  |  | 0 | P | N | N
12 | 17155 | BEA | CUNNINGHAM | 6 | OVERHAUL | 2001-10-08 08:00 | 2001-11-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Major overhaul on MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (This outage will decrease the total injection & withdrawal rate by 100mmcfd). |  |  |  | 0 | P | N | N
13 | 17332 | BEA | CUNNINGHAM | ALL | ELEC SWITCH GEAR | 2001-11-12 07:00 | 2001-11-16 16:00 | 4.4 |  | OPS |  | 0 | 0 | Week of 11/12-16 all electrics will not be available. 11/12 & 13 dual fuels are available. 11/14 dual fuels are not available from 8:00 to 16:00 11/15 - 12 noon all units and plants should be available. Electric test switch gear and 4000 volt motors. |  |  |  | 0 | P | N | N
14 | 17700 | DES | EARLVILLE | 1 | SERVICE | 2001-10-13 07:00 | 2001-10-13 17:00 | 0.4 |  | OPS |  | 0 | 0 | Change all air filters and waterwash unit. 15000 HP |  |  |  | 0 | P | N | N
15 | 16066 | DES | GALENA | 1 | ANNUAL PM | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 1 Annual PM. 4000 HP |  |  |  | 0 | P | N | N
16 | 16067 | DES | GALENA | 2 | ANNUAL PM | 2001-11-12 08:00 | 2001-11-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 2 Annual PM. 4000 HP |  |  |  | 0 | P | N | N
17 | 17228 | DES | PLATTEVILLE | TOMAH TBS | TOMAH VALVE | 2001-10-01 08:00 | 2001-10-12 16:00 | 11.3 |  | 453 | C.014839 | 0 | 0 | Tomah Valve #4 replacement. Install new valve setting 11901-BYB04 @ the Sparta Takeoff. Stopple fittings will be installed upstream and downstram of BV BYB04 and a 4" temp.bypass fab. & installed. Reduce pressure to 65% maop (520 psig) regulated at LaCre | scent during stopple ops. |  |  | 0 | P | N | N
18 | 16040 | DES | WATERLOO | 5 | INSTALL PLC | 2001-10-01 08:00 | 2001-10-31 16:00 | 30.3 |  | 425 | C.014520 | 0 | 0 | Shut down unit 5 at Waterloo for the installation of a new PLC and the replacement of selected end devices. |  | 2001-10-01 08:00 |  | 0 | P | N | N
19 | 17705 | LIB | MULLINVILLE TA Line | EXPOSED A LINE | Exposed A Line | 2001-09-24 08:00 | 2001-10-31 16:00 | 68.3 |  | OPS |  | 0 | 0 | Pat Vaughn has made a drawing of a type of Wier that may work in this application and forward his drawing on to engineering for a cost estimate. (The completion date of this outage is tentative, due to approval of the work and contractor availability). The work needs to be done ASAP. |  | 2001-09-24 08:00 |  | 0 | U | N | N
20 | 17699 | LIB | MULLINVILLE | 26 | TESTING & MAINTENANCE | 2001-09-24 08:00 | 2001-11-30 16:00 | 67.3 |  | OPS |  | 0 | 0 | Compressor testing and maintenance due to excessive vibration. 11475 HP |  | 2001-09-24 08:00 |  | 0 | U | N | N
21 | 17544 | LIB | SUBLETTE | 26 | VIBRATION TROUBLE | 2001-09-20 12:00 | 2001-10-12 12:00 | 22 |  | OPS |  | 0 | 0 | Bearing failure or the oil pump. Will put on other units to cover loss in volumes. Some of the gas will be sent towards Holcomb. (Waiting for parts to return). They could possibly get the Turbine wash done as well. |  | 2001-09-20 12:00 |  | 0 | U | N | N
22 | 17680 | MID | KERMIT | 1 | LEAK ON 30" DISCHARGE VALVE | 2001-10-04 08:00 | 2001-10-12 16:00 | 8.3 |  | OPS |  | 0 | 0 | Kermit #1 turbine 30" discharge shafer valve flange leaking. They need to dig up valve and replace the gaskets. (This outage will affect deliveries when flows are in the 300 to 400 range). Right now the unit is not required. |  | 2001-10-04 08:00 |  | 0 | U | N | N
23 | 17227 | MID | PLAINVIEW | 1 | STARTER | 2001-11-05 08:00 | 2001-11-19 16:00 | 14.3 |  | OPS |  | 0 | 0 | Install new starter and controls. 9100 HP |  |  |  | 0 | P | N | N
24 | 17226 | MID | SEMINOLE | 1 | STARTER | 2001-11-26 08:00 | 2001-12-03 16:00 | 7.3 |  | OPS |  | 0 | 0 | Install new starter and new controls. 9100 HP |  |  |  | 0 | P | N | N
25
26 | 17667 | MIN | CHATFIELD | 1 | REPLACE COUPLING | 2001-10-06 07:00 | 2001-12-15 07:00 | 70 |  | OPS |  | 0 | 0 | Replacement of coupling on the electric motor/compressor. 1250 HP |  |  |  | 0 | P | N | N
27 | 16490 | MIN | FARMINGTON | ALL | MAINTENANCE | 2001-06-12 09:00 | 2001-10-17 16:00 | 122.3 |  | OPS |  | 0 | 0 | Annual ESD testing. Plant to be down for several months for maintenance. (10/10/01) Maintenance is nearing completion. A few delays due to weather, pouring support for D line tie-in,and also tie-ins for the ESD and power gas lines. |  | 2001-06-12 09:00 |  | 0 | P | N | N
28 | 17531 | MIN | N BRANCH | ANOKA 1 TBS | ANOKA 1 TBS MODS | 2001-10-29 08:00 | 2001-11-13 16:00 | 15.3 |  | 453 | C.014893 | 0 | 0 | Modify existing station to provide a pressure increase and pad gas meter for customer (Minnegasco). Complete station outage will be required. Anoka 1A and Coon Rapids 1B will br brought into service during Anoka #1 outage. |  |  |  | 0 | P | N | N
29 | 17693 | MIN | NEGAUNEE | PIPELINE | PIPELINE MAINTENANCE | 2001-10-29 08:00 | 2001-11-14 15:30 | 16.3 | MIM10101 | OPS |  | 0 | 0 | Inspect 5 locations identified by high resolution tool (smart pig). Reduced operation pressure 60% = 410#. |  |  |  | 0 | P | N | N

## LetterSizeRegionLoc (2)
ETS Planned And Unplanned Outages - October 1, 2001 Through November, 2001
NORTHERN & TW REGIONS Only - Sorted By Region/Location
The information provided is tentative and may be changed without further notice. Northern Natural Gas, Transwestern Pipeline and Florida Gas Transmission are not responsible for any reliance on this information.
Data Extracted October 10, 2001 | [11 empty] | Est. Flow | Est. Vol. |  |  | Act. | Act. | Act.
No. | ID# | Region | Location | Units | Title | EstStart | EstComp | Duration | Line | Proj. Mgr | W.O. # | Affected | Affected | DescOfWork | DescOfWork2 | Start | Compl. | Flow Aff. | P/U | Pub | Ver
[12 empty] | (Mmcfd) | [5 empty] | mmcf/d
1 | 17090 | ALB | STATION 2 | MAINLINE | RED ROCK TIE-IN | 2001-11-10 08:00 | 2001-11-14 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the suction side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
2 | 17091 | ALB | STATION 2 | LOOP LINE | RED ROCK TIE-IN | 2001-11-17 08:00 | 2001-11-21 16:00 | 4.3 |  | OPS |  | 130 | 563.3 | New block and side valve assemblies for new compressor and scrubbers will be installed on the sucton side main and loop lines at each station. The tie-in will entail isolating a line segment within the plant yard. |  |  |  | 0 | P | N | N
3 | 16752 | ALB | STATION 8 | ALL | AUTOMATION | 2001-09-04 08:00 | 2001-10-31 16:00 | 57.3 |  | OPS |  | 0 | 0 | Station 8 automation project. 8000 HP |  | 2001-09-04 08:00 |  | 0 | P | N | N
4 | 17663 | AMA | BEAVER 13 | 1 | REPLACE STUDS | 2001-10-03 13:00 | 2001-10-12 16:00 | 9.1 |  | OPS |  | 5 | 45.6 | Replace compressor cylinder studs. |  | 2001-10-03 13:00 |  | 0 | U | N | N
5 | 17447 | AMA | ELLIS 1 | 1 | 1500 HR INSP | 2001-10-11 09:00 | 2001-10-11 12:00 | 0.1 |  | OPS |  | 2 | 0.3 | 1500 Hr Inspection. Install new throttle linkage. 506 HP |  |  |  | 0 | P | N | N
6 | 17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-15 08:00 | 2001-10-20 16:00 | 5.3 |  | OPS |  | 2 | 10.7 | Install new Opto control Panel 1500 Hr. Inspection |  |  |  | 0 | P | N | N
7 | 17450 | AMA | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 |  | OPS |  | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  |  | 0 | P | N | N
8 | 17354 | BEA | BEATRICE | BEA/PAL | BEATRICE/PALMYRA CASING | 2001-10-08 07:00 | 2001-10-12 15:00 | 4.3 | NEM590B | OPS |  | 0 | 0 | Remove casing from abandoned railroad ROW on the 24" Beatrice-Palmyra at MP 2.82. Contract Services will be utilized for removal process. |  |  |  | 0 | P | N | N
9 | 16952 | BEA | BEATRICE | C LINE | TRAILBLAZER TO C LINE | 2001-10-18 08:00 | 2001-10-19 08:00 | 1 |  | 453 | C.014625 | 230 | 230 | Install a new line from the Trailblazer line to the C line and modify existing valve to allow the TB to A line tie-over to be utilized. (TB line will require a 16 hour outage where there will be no flow from Trailblazer). Blk Vlv 63101 BBB01 will be clos | ed to isolate the line segment. C line suction upstream of ML block vlv will also require an outage. |  |  | 0 | P | N | N
10 | 17472 | BEA | BUSHTON | ALL | ESD | 2001-10-11 09:00 | 2001-10-11 14:00 | 0.2 |  | OPS |  | 0 | 0 | ESD Bushton Comp Station using Yale enclosures. While station is down complete maint. job tasks. |  |  |  | 0 | P | N | N
11 | 17497 | BEA | BUSHTON | CONTROLLER #5 | CHECK VALVE | 2001-10-16 08:00 | 2001-10-16 15:00 | 0.3 |  | OPS |  | 130 | 37.9 | Remove check valve flapper from controller 5 check valve. (This date is tentative). Outage depends on approval and when Jomax Const can start. |  |  |  | 0 | P | N | N
12 | 17155 | BEA | CUNNINGHAM | 6 | OVERHAUL | 2001-10-08 08:00 | 2001-11-02 16:00 | 25.3 |  | OPS |  | 0 | 0 | Major overhaul on MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (This outage will decrease the total injection & withdrawal rate by 100mmcfd). |  |  |  | 0 | P | N | N
13 | 17332 | BEA | CUNNINGHAM | ALL | ELEC SWITCH GEAR | 2001-11-12 07:00 | 2001-11-16 16:00 | 4.4 |  | OPS |  | 0 | 0 | Week of 11/12-16 all electrics will not be available. 11/12 & 13 dual fuels are available. 11/14 dual fuels are not available from 8:00 to 16:00 11/15 - 12 noon all units and plants should be available. Electric test switch gear and 4000 volt motors. |  |  |  | 0 | P | N | N
14 | 17700 | DES | EARLVILLE | 1 | SERVICE | 2001-10-13 07:00 | 2001-10-13 17:00 | 0.4 |  | OPS |  | 0 | 0 | Change all air filters and waterwash unit. 15000 HP |  |  |  | 0 | P | N | N
15 | 16066 | DES | GALENA | 1 | ANNUAL PM | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 1 Annual PM. 4000 HP |  |  |  | 0 | P | N | N
16 | 16067 | DES | GALENA | 2 | ANNUAL PM | 2001-11-12 08:00 | 2001-11-16 16:00 | 4.3 |  | OPS |  | 0 | 0 | Galena Unit 2 Annual PM. 4000 HP |  |  |  | 0 | P | N | N
17 | 17228 | DES | PLATTEVILLE | TOMAH TBS | TOMAH VALVE | 2001-10-01 08:00 | 2001-10-12 16:00 | 11.3 |  | 453 | C.014839 | 0 | 0 | Tomah Valve #4 replacement. Install new valve setting 11901-BYB04 @ the Sparta Takeoff. Stopple fittings will be installed upstream and downstram of BV BYB04 and a 4" temp.bypass fab. & installed. Reduce pressure to 65% maop (520 psig) regulated at LaCre | scent during stopple ops. |  |  | 0 | P | N | N
18 | 16040 | DES | WATERLOO | 5 | INSTALL PLC | 2001-10-01 08:00 | 2001-10-31 16:00 | 30.3 |  | 425 | C.014520 | 0 | 0 | Shut down unit 5 at Waterloo for the installation of a new PLC and the replacement of selected end devices. |  | 2001-10-01 08:00 |  | 0 | P | N | N
19 | 17705 | LIB | MULLINVILLE TA Line | EXPOSED A LINE | Exposed A Line | 2001-09-24 08:00 | 2001-10-31 16:00 | 68.3 |  | OPS |  | 0 | 0 | Pat Vaughn has made a drawing of a type of Wier that may work in this application and forward his drawing on to engineering for a cost estimate. (The completion date of this outage is tentative, due to approval of the work and contractor availability). Th |  | 2001-09-24 08:00 |  | 0 | U | N | N
20 | 17699 | LIB | MULLINVILLE | 26 | TESTING & MAINTENANCE | 2001-09-24 08:00 | 2001-11-30 16:00 | 67.3 |  | OPS |  | 0 | 0 | Compressor testing and maintenance due to excessive vibration. 11475 HP |  | 2001-09-24 08:00 |  | 0 | U | N | N
21 | 17544 | LIB | SUBLETTE | 26 | VIBRATION TROUBLE | 2001-09-20 12:00 | 2001-10-12 12:00 | 22 |  | OPS |  | 0 | 0 | Bearing failure or the oil pump. Will put on other units to cover loss in volumes. Some of the gas will be sent towards Holcomb. (Waiting for parts to return). They could possibly get the Turbine wash done as well. |  | 2001-09-20 12:00 |  | 0 | U | N | N
22 | 17680 | MID | KERMIT | 1 | LEAK ON 30" DISCHARGE VALVE | 2001-10-04 08:00 | 2001-10-12 16:00 | 8.3 |  | OPS |  | 0 | 0 | Kermit #1 turbine 30" discharge shafer valve flange leaking. They need to dig up valve and replace the gaskets. (This outage will affect deliveries when flows are in the 300 to 400 range). Right now the unit is not required. |  | 2001-10-04 08:00 |  | 0 | U | N | N
23 | 17227 | MID | PLAINVIEW | 1 | STARTER | 2001-11-05 08:00 | 2001-11-19 16:00 | 14.3 |  | OPS |  | 0 | 0 | Install new starter and controls. 9100 HP |  |  |  | 0 | P | N | N
24 | 17226 | MID | SEMINOLE | 1 | STARTER | 2001-11-26 08:00 | 2001-12-03 16:00 | 7.3 |  | OPS |  | 0 | 0 | Install new starter and new controls. 9100 HP |  |  |  | 0 | P | N | N
25
26 | 17667 | MIN | CHATFIELD | 1 | REPLACE COUPLING | 2001-10-06 07:00 | 2001-12-15 07:00 | 70 |  | OPS |  | 0 | 0 | Replacement of coupling on the electric motor/compressor. 1250 HP |  |  |  | 0 | P | N | N
27 | 16490 | MIN | FARMINGTON | ALL | MAINTENANCE | 2001-06-12 09:00 | 2001-10-17 16:00 | 122.3 |  | OPS |  | 0 | 0 | Annual ESD testing. Plant to be down for several months for maintenance. (10/10/01) Maintenance is nearing completion. A few delays due to weather, pouring support for D line tie-in,and also tie-ins for the ESD and power gas lines. |  | 2001-06-12 09:00 |  | 0 | P | N | N
28 | 17531 | MIN | N BRANCH | ANOKA 1 TBS | ANOKA 1 TBS MODS | 2001-10-29 08:00 | 2001-11-13 16:00 | 15.3 |  | 453 | C.014893 | 0 | 0 | Modify existing station to provide a pressure increase and pad gas meter for customer (Minnegasco). Complete station outage will be required. Anoka 1A and Coon Rapids 1B will br brought into service during Anoka #1 outage. |  |  |  | 0 | P | N | N
29 | 17693 | MIN | NEGAUNEE | PIPELINE | PIPELINE MAINTENANCE | 2001-10-29 08:00 | 2001-11-14 15:30 | 16.3 | MIM10101 | OPS |  | 0 | 0 | Inspect 5 locations identified by high resolution tool (smart pig). Reduced operation pressure 60% = 410#. |  |  |  | 0 | P | N | N