## Catawba 02
Owner Name | Catawba Nuclear Power Station
Station Name | Duke Energy Corporation
Unit Name | Catawba 02
NERC Region | SERC
State | SC
Fuel Type | Nuclear
Capacity | 1205 MW
Start Date | 2001-09-15
End Date | 2001-10-18
Prv. Start Date | 2001-09-15
Prv. End Date | 2001-10-14
Comments | Refueling
SIC | 4911
Plant ID | 1013575
Unit ID | 1008375
Outage ID | 10871

## Coolwater 03c ST
Owner Name | Reliant Energy Coolwater
Station Name | Coolwater Power Station 3&4
Unit Name | Unit 03C ST
NERC Region | WSCC
State | CA
Fuel Type | Steam
Capacity | 124 MW
Start Date | 2002-04-05
End Date | 2002-04-22
Prv. Start Date | 2001-10-12
Prv. End Date | 2001-10-29
Comments | This date is only an approxmiate date, the plant only knows that the work will be done sometime in the spring.
SIC | 4931
Plant ID | 1502747
Unit ID | 1006010
Outage ID | 18550

## Lake Cogen ST 01
Owner Name | GPU International Inc.
Station Name | Lake Cogen
Unit Name | Unit 01 CT/HRSG
NERC Region | FRCC
State | FL
Fuel Type | Natural Gas
Capacity | 27 MW
Start Date | 2001-10-26
End Date | 2001-10-30
Prv. Start Date | 2001-10-11
Prv. End Date | 2001-10-15
Comments
SIC | 4931
Plant ID | 1012710
Unit ID | 1012061
Outage ID | 15878

## Lake Cogen 02 CTHRSG
Owner Name | GPU International Inc.
Station Name | Lake Cogen
Unit Name | Unit 02 CT/HRSG
NERC Region | FRCC
State | FL
Fuel Type | Natural Gas
Capacity | 49 MW
Start Date | 2001-10-26
End Date | 2001-10-30
Prv. Start Date | 2001-10-11
Prv. End Date | 2001-10-15
Comments
SIC | 4931
Plant ID | 1012710
Unit ID | 1012059
Outage ID | 18412

## Lake Cogen 01 CTHRSG
Owner Name | GPU International Inc.
Station Name | Lake Cogen
Unit Name | Unit 01 CT/HRSG
NERC Region | FRCC
State | FL
Fuel Type | Natural Gas
Capacity | 49 MW
Start Date | 2001-10-26
End Date | 2001-10-30
Prv. Start Date | 2001-10-11
Prv. End Date | 2001-10-15
Comments
SIC | 4931
Plant ID | 1012710
Unit ID | 1012056
Outage ID | 15875

## Ray D Nixon 01
Owner Name | Colorado Springs Utilities
Station Name | Ray D Nixon Power Station
Unit Name | Ray D Nixon 01
NERC Region | WSCC
State | CO
Fuel Type | Coal
Capacity | 207 MW
Start Date | 2001-10-01
End Date | 2001-10-19
Prv. Start Date | 2001-10-01
Prv. End Date | 2001-11-04
Comments | Turbine Overhaul
SIC | 4911
Plant ID | 1016431
Unit ID | 1005678
Outage ID | 15022

## Monticello 03
Owner Name | TXU
Station Name | Monticello Power Station
Unit Name | Monticello 03
NERC Region | ERCOT
State | TX
Fuel Type | Coal
Capacity | 793
Start Date | 2001-10-05
End Date | 2001-10-15
Prv. Start Date | 2001-10-05
Prv. End Date | 2001-10-11
Comments | Boiler Inspection.
SIC | 4911
Plant ID | 1002103
Unit ID | 1008600
Outage ID | 16390

## Sommers 02
Owner Name | San Antonio City Public Service Board
Station Name | O W Sommers Power Station
Unit Name | Sommers 02
NERC Region | ERCOT
State | TX
Fuel Type | Nat. gas/Fuel Oil
Capacity | 446 MW
Start Date | 2001-10-19
End Date | 2001-12-13
Prv. Start Date | 2001-10-12
Prv. End Date | 2001-12-06
Comments | Control Upgrade
SIC | 4911
Plant ID | 1002208
Unit ID | 1005825
Outage ID | 15811

## Riveria Beach 04
Owner Name | Florida Power & Light Company
Station Name | Riveria Beach Power Station
Unit Name | Riveria Beach Power Station
NERC Region | FRCC
State | FL
Fuel Type | Natural Gas
Capacity | 310 MW
Start Date | 2001-11-02
End Date | 2001-12-27
Prv. Start Date | 2001-10-05
Prv. End Date | 2001-11-29
Comments | Turbine O/H
SIC | 4911
Plant ID | 1500935
Unit ID | 1005186
Outage ID | 10634