## 101501a
PLANNED UNPLANNED OUTAGES AFFECTING THE BUSHTON UNIVERSE.
2001-10-15
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
17460 | LIB | MULLINVILLE | 17 | POWER END | 2001-09-04 08:00 | 2001-12-31 16:00 | 118.3 | 0 | 0 | Power end maintenance. Inspection for parts needed. | 2001-09-04 08:00 |  | 0 | U
17591 | LIB | BEAVER 1 | 2 | COMPRESSOR CRANKSHAFT REPAIR | 2001-09-10 18:30 | 2001-10-19 16:00 | 38.9 | 0 | 0 | Compressor Crankcshaft Repair - Update 9/28 - extend date to 10/19. | 2001-09-10 18:30 |  | 0 | U
17544 | LIB | SUBLETTE | 26 | REPLACING POWER TURB. | 2001-09-20 12:00 | 2001-10-26 16:00 | 36.2 | 0 | 0 | They need to replace the power turbine.Will put on other units to cover loss in volumes. Some of the gas will be sent towards Holcomb. (Waiting for parts to return).They could possibly get the Turbine wash done as well. | 2001-09-20 12:00 |  | 0 | U
17588 | AMA | BEAVER 2 | 3 | PISTON & HEAD | 2001-09-22 09:00 | 2001-10-19 16:00 | 27.3 | 0 | 0 | Change 2 pistons and 1 head. (Waiting on Rod) | 2001-09-22 09:00 |  | 0 | U
17705 | LIB | MULLINVILLE TA LINE | EXPOSED A LINE | EXPOSED A LINE | 2001-09-24 08:00 | 2001-10-31 16:00 | 37.3 | 0 | 0 | Pat Vaughn has made a drawing of a type of Wier that may work in this application and forward his drawing on to engineering for a cost estimate. (The completion date of this outage is tentative due to approval of the work and contractor availability). Th | 2001-09-24 08:00 |  | 0 | U
17699 | LIB | MULLINVILLE | 26 | TESTING & MAINTENANCE | 2001-09-24 08:00 | 2001-11-30 16:00 | 67.3 | 0 | 0 | Compressor testing and maintenance due to excessive vibration. 11475 HP | 2001-09-24 08:00 |  | 0 | U
16965 | LIB | STEVENS 7 | 4 | MP2 TASKS | 2001-10-01 08:00 | 2001-10-12 16:00 | 11.3 | 0 | 0 | MP2 tasks and comp. insp. |  |  | 0 | P
16909 | LIB | MORTON 1 | 10 | MP2 TASKS | 2001-10-01 12:00 | 2001-10-22 16:00 | 21.2 | 0 | 0 | MP2 tasks. | 2001-10-01 12:00 |  | 0 | P
17698 | LIB | FINNEY 4 | 1 | BEARING SENSOR | 2001-10-05 14:00 | 2001-12-31 16:30 | 87.1 | 0 | 0 | Lost main bearing sensor. Pulled doors off to check sensor and found metal in crankcase. Drained oil and located problem. Unit will have to be re-worked. | 2001-10-05 14:00 |  | 0 | U
17466 | LIB | MULLINVILLE | 19 | ANNUAL INSP | 2001-10-09 08:00 | 2001-10-19 16:00 | 10.3 | 0 | 0 | Annual inspection. | 2001-10-11 08:00 |  | 0 | P
17661 | LIB | CLARK 2 | ALL | ESD | 2001-10-09 09:00 | 2001-10-09 12:00 | 0.1 | 1 | 0.1 | ESD |  |  | 0 | P
17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-12 13:00 | 2001-10-20 16:00 | 8.1 | 2 | 16.3 | Install new Opto control Panel 1500 Hr. Inspection. Update 10/12 - taking unit down to get a jump on Monday's panel board installation. Will adjust other units to accommodate volume. |  |  | 0 | P
16964 | LIB | STEVENS 7 | 3 | MP2 TASKS | 2001-10-15 08:00 | 2001-10-19 16:00 | 4.3 | 0 | 0 | MP2 tasks and comp. insp. |  |  | 0 | P
17470 | LIB | STEVENS 1 | 7 | REPLACE CONTROLLER | 2001-10-22 08:00 | 2001-10-23 16:00 | 1.3 | 0 | 0 | Replace TEC 9000 controller with DE2500. |  |  | 0 | P
17467 | LIB | MULLINVILLE | 22 | ANNUAL INSP | 2001-10-22 08:00 | 2001-11-02 16:00 | 11.3 | 0 | 0 | Annual inspection. |  |  | 0 | P
17655 | LIB | HOLCOMB | 9 | TURBO OVERHAUL | 2001-10-22 08:00 | 2001-11-09 16:00 | 18.3 | 0 | 0 | They need to overhaul the turbo charger. |  |  | 0 | P
17691 | LIB | STEVENS 2 | 3 | SERVICE | 2001-10-23 08:00 | 2001-10-23 16:00 | 0.3 | 0 | 0 | Service the unit. |  |  | 0 | P
17471 | LIB | TEXAS 1 | 2 | MP2 TASKS | 2001-10-29 08:00 | 2001-11-02 16:00 | 4.3 | 0 | 0 | MP2 tasks. |  |  | 0 | P
15944 | AMA | SPEARMAN | 2 | OVERHAUL | 2001-10-29 08:00 | 2001-11-16 12:00 | 18.2 | 0 | 0 | Minor overhaul. The date may change depending on #3 CB control project. 2250 HP (Will not start on this outage until unit 3 is back to normal operation). Start date moved back to coordinate with customer outages per their request. |  |  | 0 | P
17708 | LIB | HUGOTON | 16 | POST CHECK | 2001-10-30 08:00 | 2001-10-30 12:00 | 0.2 | 0 | 0 | Powt check unit from major overhaul that was done. 1800 HP |  |  | 0 | P
17450 | AMA | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  | 0 | P
17497 | BEA | BUSHTON | CONTROLLER #5 | CHECK VALVE | 2001-10-31 08:00 | 2001-10-31 15:00 | 0.3 | 130 | 37.9 | Remove check valve flapper from controller 5 check valve. (This date is tentative). Outage depends on approval and when Jomax Const can start. |  |  | 0 | P
17465 | LIB | MULLINVILLE | 18 | ANNUAL INSP | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 | 0 | 0 | Annual inspection. |  |  | 0 | P
17609 | LIB | MORTON 1 | 4 | MAINTENANCE | 2001-11-06 07:30 | 2001-11-07 16:00 | 1.4 | 0 | 0 | Oil change compression test power valves. |  |  | 0 | P
15911 | LIB | STEVENS 2 | 8 | SERVICE & PM | 2001-11-06 08:00 | 2001-11-06 16:00 | 0.3 | 0 | 0 | Service unit panel board S/D & PM |  |  | 0 | P
15926 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2001-11-07 08:00 | 2001-11-13 16:00 | 6.3 | 0 | 0 | Service units. |  |  | 0 | P
15907 | LIB | STEVENS 2 | 6 | SERVICE | 2001-11-27 08:00 | 2001-11-27 16:00 | 0.3 | 0 | 0 | Service unit. |  |  | 0 | P
16441 | LIB | TATE | 1 | OVERHAUL | 2001-12-03 08:00 | 2001-12-17 16:00 | 14.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
17610 | LIB | MORTON 1 | 4 | CONTROLS PM | 2001-12-04 07:30 | 2001-12-07 16:00 | 3.4 | 0 | 0 | Controls PM |  |  | 0 | P
17480 | LIB | HUGOTON | 17 | MAINTENANCE | 2001-12-06 08:00 | 2001-12-06 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 7800 HP |  |  | 0 | P
17612 | LIB | MORTON 6 | 2 | OIL CHANGE | 2001-12-11 07:30 | 2001-12-11 16:00 | 0.4 | 0 | 0 | Oil change. |  |  | 0 | P
17611 | LIB | MORTON 1 | 3 | CONTROLS PM | 2001-12-11 07:30 | 2001-12-14 16:00 | 3.4 | 0 | 0 | Controls PM |  |  | 0 | P
15903 | LIB | STEVENS 2 | 3 | PM | 2001-12-11 08:00 | 2001-12-11 16:00 | 0.3 | 0 | 0 | Panel board S/D & PM. |  |  | 0 | P
15928 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2001-12-11 08:00 | 2001-12-13 16:00 | 2.3 | 0 | 0 | Service units. |  |  | 0 | P
17613 | LIB | MORTON 6 | 1 | OIL CHANGE | 2001-12-12 07:30 | 2001-12-12 16:00 | 0.4 | 0 | 0 | Oil change. |  |  | 0 | P
16442 | LIB | TATE | 3 | OVERHAUL | 2001-12-17 08:00 | 2001-12-31 16:00 | 14.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
11089 | LIB | MORTON 1 | 11 | SHOP O/H | 2001-12-30 08:00 | 2001-12-30 16:00 | 0.3 | 0 | 0 | Top End Head Change. Postponed until a later date. |  |  | 0 | P
11090 | LIB | MORTON 1 | 12 | SHOP O/H | 2001-12-30 08:00 | 2001-12-30 16:00 | 0.3 | 0 | 0 | Top End Head Change. Postponed until a later date. |  |  | 0 | P
17614 | LIB | MORTON 1 | 5 | CONTROLS PM | 2002-01-09 07:30 | 2002-01-11 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17615 | LIB | MORTON 1 | 6 | CONTROLS PM | 2002-01-16 07:30 | 2002-01-18 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17616 | LIB | MORTON 1 | 7 | CONTROLS PM | 2002-02-04 07:30 | 2002-02-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17673 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17617 | LIB | MORTON 1 | 10 | CONTROLS PM | 2002-02-11 07:30 | 2002-02-15 16:00 | 4.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17671 | LIB | TEXAS 1 | 3 | INSPECTION | 2002-02-18 08:00 | 2002-02-22 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-13 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17668 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-10 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P