## Ormond Beach 02
Owner Name | Reliant Energy Ormond Beach LLC
Station Name | Ormond Beach Power
Unit Name | Unit 02
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas
Capacity | 806 MW
Start Date | 2001-10-05
End Date | 2001-10-18
Prv. Start Date | 2001-10-05
Prv. End Date | 2001-10-21
Comments | Unit is back on line and ramping up but is still derated
SIC | 4931
Plant ID | 1013123
Unit ID | 1006709
Outage ID | 18629

## El Segundo 03
Owner Name | El Segundo Power LLC
Station Name | El Segundo Power Station
Unit Name | Unit 03
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas
Capacity | 342 MW
Start Date | 2001-10-08
End Date | 2001-10-21
Prv. Start Date | 2001-10-08
Prv. End Date | 2001-10-18
Comments | Having Problems with boiler; they hope to be up by this weekend
SIC | 4931
Plant ID | 1013744
Unit ID | 1006016
Outage ID | 18613

## Big Cajun II 03
Owner Name | Louisiana Generating
Station Name | Big Cajun II Power Station
Unit Name | Big Cajun II 03
NERC Region | SERC
State | LA
Fuel Type | Coal
Capacity | 611 MW
Start Date | 2002-03-15
End Date | 2002-04-25
Prv. Start Date | 2001-10-16
Prv. End Date | 2001-11-26
Comments | The work will be done in the spring; approx spring start date
SIC | 4911
Plant ID | 1005163
Unit ID | 1004084
Outage ID | 10756

## GRDA 01
Owner Name | Grand River Dam Authority
Station Name | GRDA Power Station
Unit Name | GRDA 01
NERC Region | SPP
State | OK
Fuel Type | Coal
Capacity | 490 MW
Start Date | 2001-10-12
End Date | 2001-11-01
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-11-10
Comments | Boiler Work
SIC | 4911
Plant ID | 1016875
Unit ID | 1006083
Outage ID | 13691

## Hatch 02
Owner Name | Georgia Power Company
Station Name | Edwin I Hatch Nuclear Power Station
Unit Name | Hatch 02
NERC Region | SERC
State | GA
Fuel Type | Nuclear
Capacity | 865 MW
Start Date | 2001-09-15
End Date | 2001-10-19
Prv. Start Date | 2001-09-15
Prv. End Date | 2001-10-25
Comments | Hoping to be at 100% on Monday.
SIC | 4911
Plant ID | 1012040
Unit ID | 1004272
Outage ID | 8185

## Duane Arnold 01
Owner Name | Alliant-IES Utilities Inc.
Station Name | Duane Arnold Nuclear Power Station
Unit Name | Duane Arnold 01
NERC Region | MAIN
State | IA
Fuel Type | Nuclear
Capacity | 597 MW
Start Date | 2001-10-17
End Date | 2001-10-21
Prv. Start Date | 2001-10-17
Prv. End Date | 2001-10-20
Comments | Electrical problem. Unit is hoping to come back on line on Sunday.
SIC | 4911
Plant ID | 1012744
Unit ID | 1004913
Outage ID | 18671

## Rocky Mountain 03
Owner Name | Oglethorpe Power Company
Station Name | Rocky Mountain Pumped Storage
Unit Name | Hydro 03
NERC Region | SERC
State | GA
Fuel Type | Hydro
Capacity | 282 MW
Start Date | 2001-11-03
End Date | 2001-11-23
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-11-08
Comments | Maintenance
SIC | 4911
Plant ID | 1011981
Unit ID | 1012957
Outage ID | 18210

## Mitchell 01
Owner Name | American Electric Power Company Incorporated
Station Name | Mitchell Power Station
Unit Name | Mitchell 01
NERC Region | ECAR
State | WV
Fuel Type | Coal
Capacity | 816 MW
Start Date | 2001-10-12
End Date | 2002-01-04
Prv. Start Date | 2001-10-12
Prv. End Date | 2001-11-08
Comments | Boiler Work
SIC | 4911
Plant ID | 1017322
Unit ID | 1007867
Outage ID | 16103

## Seabrook 01
Owner Name | Northeast Utilities
Station Name | Seabrook Nuclear Power Station
Unit Name | Seabrook 01
NERC Region | NPCC
State | NH
Fuel Type | Nuclear
Capacity | 1,242 MW
Start Date | 2001-10-15
End Date | 2001-10-20
Prv. Start Date | 2001-10-15
Prv. End Date | 2001-10-16
Comments | Unit's currently in hot standby. Preparing to come on line tomorrow.
SIC | 4911
Plant ID | 1015015
Unit ID | 1008197
Outage ID | 18660

## Pasco ST 01
Owner Name | Pasco Cogen Limited
Station Name | Pasco Cogen
Unit Name | ST 01
NERC Region | SERC
State | FL
Fuel Type | Natural Gas
Capacity | 49 MW
Start Date | 2002-03-01
End Date | 2002-03-02
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-10-20
Comments | External Inspection and Boroscope
SIC | 4931
Plant ID | 1013166
Unit ID | 1012005
Outage ID | 17070

## Pasco 02
Owner Name | Pasco Cogen Limited
Station Name | Pasco Cogen
Unit Name | Unit 02 CT/HRSG
NERC Region | SERC
State | FL
Fuel Type | Natural Gas
Capacity | 49 MW
Start Date | 2002-03-01
End Date | 2002-03-02
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-10-20
Comments | External Inspection and Boroscope
SIC | 4931
Plant ID | 1013166
Unit ID | 1012007
Outage ID | 17069

## Pasco 01
Owner Name | Pasco Cogen Limited
Station Name | Pasco Cogen
Unit Name | Unit 01 CT/HRSG
NERC Region | SERC
State | FL
Fuel Type | Natural Gas
Capacity | 49 MW
Start Date | 2002-03-01
End Date | 2002-03-02
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-10-20
Comments | External Inspection and Boroscope
SIC | 4931
Plant ID | 1013166
Unit ID | 1012006
Outage ID | 17068