## Hammond 02
Owner Name | Georgia Power Company
Station Name | Hammond Power Station
Unit Name | Hammond 02
NERC Region | SERC
State | GA
Fuel Type | Coal
Capacity | 125 MW
Start Date | 2001-10-19
End Date | 2001-12-09
Prv. Start Date | 2001-09-22
Prv. End Date | 2001-10-01
Comments | Boiler/Burner
SIC | 4911
Plant ID | 1516000
Unit ID | 1004514
Outage ID | 8710

## Stryker Creek 01
Owner Name | TXU
Station Name | Stryker Creek Power Station
Unit Name | Unit 01
NERC Region | ERCOT
State | TX
Fuel Type | Nat. gas/Fuel Oil
Capacity | 177 MW
Start Date | 2001-11-02
End Date | 2001-11-15
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-11-01
Comments | Boiler insp.
SIC | 4911
Plant ID | 1000059
Unit ID | 1008591
Outage ID | 17978

## Braidwood 02
Owner Name | Exelon Nuclear
Station Name | Braidwood Nuclear Power Station
Unit Name | Braidwood 02
NERC Region | MAIN
State | IL
Fuel Type | Nuclear
Capacity | 1,225 MW
Start Date
End Date | 2001-10-23
Prv. Start Date
Prv. End Date
Comments | Generator work; Braidwood is moving up from 78% and should be at full power by end of day on Tuesday.
SIC | 4911
Plant ID | 1016362
Unit ID | 1007403
Outage ID

## Hatch 02
Owner Name | Georgia Power Company
Station Name | Edwin I Hatch Nuclear Power Station
Unit Name | Hatch 02
NERC Region | SERC
State | GA
Fuel Type | Nuclear
Capacity | 865 MW
Start Date | 2001-09-15
End Date | 2001-10-23
Prv. Start Date | 2001-09-15
Prv. End Date | 2001-10-19
Comments | Failed startup due to maintenance difficulties.
SIC | 4911
Plant ID | 1012040
Unit ID | 1004272
Outage ID | 8185