## 102201a
PLANNED AND UNPLANNED OUTAGES AFFECTING THE BUSHTON UNIVERSE.
2001-10-22
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
17588 | AMA | BEAVER 2 | 3 | PISTON & HEAD | 2001-09-22 09:00 | 2001-11-09 16:00 | 48.3 | 0 | 0 | Change 2 pistons and 1 head. (Waiting on Rod and oil rings). | 2001-09-22 09:00 |  | 0 | U
17740 | AMA | BEAVER 5 | 4 | ELMWOOD PLANT | 2001-10-17 11:00 | 2001-10-18 16:00 | 1.2 | 0 | 0 | Unit down due to Elmwood Plant commoned southeast 24" and 8". Unit will not be able to buck high discharge pressure. | 2001-10-18 11:00 |  | 0 | U
17449 | AMA | ELLIS 1 | 3 | 1500 HR INSP | 2001-10-12 13:00 | 2001-10-20 16:00 | 8.1 | 2 | 16.3 | Install new Opto control Panel 1500 Hr. Inspection. Update 10/12 - taking unit down to get a jump on Monday's panel board installation. Will adjust other units to accommodate volume. |  |  | 0 | P
17450 | AMA | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  | 0 | P
15944 | AMA | SPEARMAN | 2 | OVERHAUL | 2001-10-29 08:00 | 2001-11-16 12:00 | 18.2 | 0 | 0 | Minor overhaul. The date may change depending on #3 CB control project. 2250 HP (Will not start on this outage until unit 3 is back to normal operation). Start date moved back to coordinate with customer outages per their request. |  |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P
17735 | BEA | BUSHTON | 32 | UNIT EXCHANGE | 2001-10-15 08:00 | 2001-11-01 16:00 | 17.3 | 0 | 0 | Unit 32 is in California for repair. We are putting unit 25 from Mullinvile it's place until further notice or unit 32 has been been completed and returned to service. | 2001-10-15 08:00 |  | 0 | P
17497 | BEA | BUSHTON | CONTROLLER #5 | CHECK VALVE | 2001-11-09 08:00 | 2001-11-09 15:00 | 0.3 | 130 | 37.9 | Remove check valve flapper from controller 5 check valve. (This date is tentative). Outage depends on approval and when Jomax Const can start. |  |  | 0 | P
16935 | BEA | BUSHTON |  | LYONS FUEL GAS | 2001-11-14 08:00 | 2001-11-21 16:00 | 7.3 | 0 | 0 | Install 500 000 BTU/hr heater on the main fuel gas supply line and connect the Lyons gas into the main plant fuel gas. Also install filter/separator on the Lyons supply gas line. |  |  | 0 | P
17591 | LIB | BEAVER 1 | 2 | COMPRESSOR CRANKSHAFT REPAIR | 2001-09-10 18:30 | 2001-10-26 16:00 | 45.9 | 0 | 0 | Compressor Crankcshaft Repair - Update 9/28 - extend date to 10/19. | 2001-09-10 18:30 |  | 0 | U
17698 | LIB | FINNEY 4 | 1 | BEARING SENSOR | 2001-10-05 14:00 | 2001-12-31 16:30 | 87.1 | 0 | 0 | Lost main bearing sensor. Pulled doors off to check sensor and found metal in crankcase. Drained oil and located problem. Unit will have to be re-worked. | 2001-10-05 14:00 |  | 0 | U
17727 | LIB | FINNEY 4 | 1 | REWORK UNIT | 2001-10-12 12:00 | 2001-12-31 16:30 | 80.2 | 0 | 0 | Unit was down on high bearing temp. Unit will have to be reworked and will be down 8 weeks or more. | 2001-10-12 12:00 |  | 0 | U
17655 | LIB | HOLCOMB | 9 | TURBO OVERHAUL | 2001-10-22 08:00 | 2001-11-09 16:00 | 18.3 | 0 | 0 | They need to overhaul the turbo charger. |  |  | 0 | P
17708 | LIB | HUGOTON | 16 | POST CHECK | 2001-10-30 08:00 | 2001-10-30 12:00 | 0.2 | 0 | 0 | Powt check unit from major overhaul that was done. 1800 HP |  |  | 0 | P
17480 | LIB | HUGOTON | 17 | MAINTENANCE | 2001-12-06 08:00 | 2001-12-06 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 7800 HP |  |  | 0 | P
17611 | LIB | MORTON 1 | 3 | CONTROLS PM | 2001-12-11 07:30 | 2001-12-14 16:00 | 3.4 | 0 | 0 | Controls PM |  |  | 0 | P
17609 | LIB | MORTON 1 | 4 | MAINTENANCE | 2001-11-06 07:30 | 2001-11-07 16:00 | 1.4 | 0 | 0 | Oil change compression test power valves. |  |  | 0 | P
17610 | LIB | MORTON 1 | 4 | CONTROLS PM | 2001-12-04 07:30 | 2001-12-07 16:00 | 3.4 | 0 | 0 | Controls PM |  |  | 0 | P
17614 | LIB | MORTON 1 | 5 | CONTROLS PM | 2002-01-09 07:30 | 2002-01-11 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17615 | LIB | MORTON 1 | 6 | CONTROLS PM | 2002-01-16 07:30 | 2002-01-18 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17616 | LIB | MORTON 1 | 7 | CONTROLS PM | 2002-02-04 07:30 | 2002-02-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
16909 | LIB | MORTON 1 | 10 | MP2 TASKS | 2001-10-01 12:00 | 2001-10-22 16:00 | 21.2 | 0 | 0 | MP2 tasks. | 2001-10-01 12:00 |  | 0 | P
17617 | LIB | MORTON 1 | 10 | CONTROLS PM | 2002-02-11 07:30 | 2002-02-15 16:00 | 4.4 | 0 | 0 | Controls PM. |  |  | 0 | P
11089 | LIB | MORTON 1 | 11 | SHOP O/H | 2001-12-30 08:00 | 2001-12-30 16:00 | 0.3 | 0 | 0 | Top End Head Change. Postponed until a later date. |  |  | 0 | P
11090 | LIB | MORTON 1 | 12 | SHOP O/H | 2001-12-30 08:00 | 2001-12-30 16:00 | 0.3 | 0 | 0 | Top End Head Change. Postponed until a later date. |  |  | 0 | P
17613 | LIB | MORTON 6 | 1 | OIL CHANGE | 2001-12-12 07:30 | 2001-12-12 16:00 | 0.4 | 0 | 0 | Oil change. |  |  | 0 | P
17612 | LIB | MORTON 6 | 2 | OIL CHANGE | 2001-12-11 07:30 | 2001-12-11 16:00 | 0.4 | 0 | 0 | Oil change. |  |  | 0 | P
17460 | LIB | MULLINVILLE | 17 | POWER END | 2001-09-04 08:00 | 2001-12-31 16:00 | 118.3 | 0 | 0 | Power end maintenance. Inspection for parts needed. | 2001-09-04 08:00 |  | 0 | U
17465 | LIB | MULLINVILLE | 18 | ANNUAL INSP | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 | 0 | 0 | Annual inspection. |  |  | 0 | P
17466 | LIB | MULLINVILLE | 19 | ANNUAL INSP | 2001-10-09 08:00 | 2001-10-23 16:00 | 14.3 | 0 | 0 | Annual inspection. | 2001-10-11 08:00 |  | 0 | P
17467 | LIB | MULLINVILLE | 22 | ANNUAL INSP | 2001-10-23 08:00 | 2001-11-02 16:00 | 10.3 | 0 | 0 | Annual inspection. |  |  | 0 | P
17699 | LIB | MULLINVILLE | 26 | TESTING & MAINTENANCE | 2001-09-24 08:00 | 2001-10-31 16:00 | 37.3 | 0 | 0 | Compressor testing and maintenance due to excessive vibration. 11475 HP (Update 10/15/01) Hickham Industries is doing some analysis on the unit this week to give us a better a plan of attack.. | 2001-09-24 08:00 |  | 0 | U
17705 | LIB | MULLINVILLE TA LINE | EXPOSED A LINE | EXPOSED A LINE | 2001-09-24 08:00 | 2001-10-31 16:00 | 37.3 | 0 | 0 | Pat Vaughn has made a drawing of a type of Wier that may work in this application and forward his drawing on to engineering for a cost estimate. (The completion date of this outage is tentative due to approval of the work and contractor availability). Th | 2001-09-24 08:00 |  | 0 | U
17470 | LIB | STEVENS 1 | 7 | REPLACE CONTROLLER | 2001-10-22 08:00 | 2001-10-23 16:00 | 1.3 | 0 | 0 | Replace TEC 9000 controller with DE2500. |  |  | 0 | P
15903 | LIB | STEVENS 2 | 3 | PM | 2001-12-11 08:00 | 2001-12-11 16:00 | 0.3 | 0 | 0 | Panel board S/D & PM. |  |  | 0 | P
17691 | LIB | STEVENS 2 | 3 | SERVICE | 2001-10-23 08:00 | 2001-10-23 16:00 | 0.3 | 0 | 0 | Service the unit. |  |  | 0 | P
15907 | LIB | STEVENS 2 | 6 | SERVICE | 2001-11-27 08:00 | 2001-11-27 16:00 | 0.3 | 0 | 0 | Service unit. |  |  | 0 | P
15911 | LIB | STEVENS 2 | 8 | SERVICE & PM | 2001-11-06 08:00 | 2001-11-06 16:00 | 0.3 | 0 | 0 | Service unit panel board S/D & PM |  |  | 0 | P
15926 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2001-11-07 08:00 | 2001-11-13 16:00 | 6.3 | 0 | 0 | Service units. |  |  | 0 | P
15928 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2001-12-11 08:00 | 2001-12-13 16:00 | 2.3 | 0 | 0 | Service units. |  |  | 0 | P
17732 | LIB | STEVENS 4 | 4 | MP2 WORK | 2001-11-28 07:00 | 2001-11-29 16:00 | 1.4 | 0 | 0 | MP@ work on unit 4. No volume loss. |  |  | 0 | P
16964 | LIB | STEVENS 7 | 3 | MP2 TASKS | 2001-10-29 08:00 | 2001-11-02 16:00 | 4.3 | 0 | 0 | MP2 tasks and comp. insp. |  |  | 0 | P
17544 | LIB | SUBLETTE | 26 | OVERHAULING UNIT | 2001-09-20 12:00 | 2001-12-21 16:00 | 92.2 | 0 | 0 | Overhaul on the unit. They need to replace the power turbine. Will put on other units to cover loss in volumes. Some of the gas will be sent towards Holcomb. | 2001-09-20 12:00 |  | 0 | U
16441 | LIB | TATE | 1 | OVERHAUL | 2001-12-03 08:00 | 2001-12-17 16:00 | 14.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
16442 | LIB | TATE | 3 | OVERHAUL | 2001-12-17 08:00 | 2001-12-31 16:00 | 14.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
17471 | LIB | TEXAS 1 | 2 | MP2 TASKS | 2001-10-29 08:00 | 2001-11-02 16:00 | 4.3 | 0 | 0 | MP2 tasks. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-10 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17668 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17671 | LIB | TEXAS 1 | 3 | INSPECTION | 2002-02-18 08:00 | 2002-02-22 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-13 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17673 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P