## 102501a
PLANNED AND UNPLANNED OUTAGES AFFECTING THE BUSHTON UNIVERSE.
2001-10-25
The information provided is tentative and may be changed without further notice. Northern Natural Gas Transwestern and Florida Gas Transmission are not responsible for any reliance on this information.
# | Region | Location | Units | Title | EstStart | EstComp | Dur (Days) | Est Flow Affected | Est Thru Affected | DescOfWork | ActStart | ActComp | Act Flow Affected | Planned Unplanned
17460 | LIB | MULLINVILLE | 17 | POWER END | 2001-09-04 08:00 | 2001-12-31 16:00 | 118.3 | 0 | 0 | Power end maintenance. Inspection for parts needed. | 2001-09-04 08:00 |  | 0 | U
17591 | LIB | BEAVER 1 | 2 | COMPRESSOR CRANKSHAFT REPAIR | 2001-09-10 18:30 | 2001-10-26 16:00 | 45.9 | 0 | 0 | Compressor Crankcshaft Repair - Update 9/28 - extend date to 10/19. | 2001-09-10 18:30 |  | 0 | U
17544 | LIB | SUBLETTE | 26 | OVERHAULING UNIT | 2001-09-20 12:00 | 2001-12-21 16:00 | 92.2 | 0 | 0 | Overhaul on the unit. They need to replace the power turbine. Will put on other units to cover loss in volumes. Some of the gas will be sent towards Holcomb. | 2001-09-20 12:00 |  | 0 | U
17548 | BEA | CUNNINGHAM | #3 DEHY | HEAT EXCHANGER ON #3 DEHY | 2001-09-21 08:00 | 2001-10-31 16:00 | 40.3 | 0 | 0 | Take Heat Exchanger out of #3 dehy to be repaired. We will have to take it to Tulsa to get fixed. Max withdrawl volumes will not be affected unless we go below 48 BCF GIP. | 2001-09-21 08:00 |  | 0 | U
17588 | AMA | BEAVER 2 | 3 | PISTON & HEAD | 2001-09-22 09:00 | 2001-11-09 16:00 | 48.3 | 0 | 0 | Change 2 pistons and 1 head. (Waiting on Rod and oil rings). | 2001-09-22 09:00 |  | 0 | U
17699 | LIB | MULLINVILLE | 26 | TESTING & MAINTENANCE | 2001-09-24 08:00 | 2001-10-31 16:00 | 37.3 | 0 | 0 | Compressor testing and maintenance due to excessive vibration. 11475 HP (Update 10/15/01) Hickham Industries is doing some analysis on the unit this week to give us a better a plan of attack.. | 2001-09-24 08:00 |  | 0 | U
17705 | LIB | MULLINVILLE TA LINE | EXPOSED A LINE | EXPOSED A LINE | 2001-09-24 08:00 | 2001-10-31 16:00 | 37.3 | 0 | 0 | Pat Vaughn has made a drawing of a type of Wier that may work in this application and forward his drawing on to engineering for a cost estimate. (The completion date of this outage is tentative due to approval of the work and contractor availability). Th | 2001-09-24 08:00 |  | 0 | U
16909 | LIB | MORTON 1 | 10 | MP2 TASKS | 2001-10-01 12:00 | 2001-10-22 16:00 | 21.2 | 0 | 0 | MP2 tasks. | 2001-10-01 12:00 |  | 0 | P
17698 | LIB | FINNEY 4 | 1 | BEARING SENSOR | 2001-10-05 14:00 | 2001-12-31 16:30 | 87.1 | 0 | 0 | Lost main bearing sensor. Pulled doors off to check sensor and found metal in crankcase. Drained oil and located problem. Unit will have to be re-worked. | 2001-10-05 14:00 |  | 0 | U
17155 | BEA | CUNNINGHAM | 6 | OVERHAUL | 2001-10-08 08:00 | 2001-11-02 16:00 | 25.3 | 0 | 0 | Major overhaul on MEP 12 cylinder power and compressor ends based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. (This outage will decrease the total injection & withdrawal rate by 100mmcfd). |  |  | 0 | P
17466 | LIB | MULLINVILLE | 19 | ANNUAL INSP | 2001-10-09 08:00 | 2001-10-23 16:00 | 14.3 | 0 | 0 | Annual inspection. | 2001-10-11 08:00 |  | 0 | P
17714 | BEA | CUNNINGHAM | UGS WELLS | INTERNAL CORROSION | 2001-10-12 07:00 | 2001-11-12 15:30 | 31.3 | 20 | 626.7 | Wells 36-13 and 36-14 are unavailable for withdrawal due to internal corrosion on the separators vessels. | 2001-10-12 07:00 |  | 0 | U
17727 | LIB | FINNEY 4 | 1 | REWORK UNIT | 2001-10-12 12:00 | 2001-12-31 16:30 | 80.2 | 0 | 0 | Unit was down on high bearing temp. Unit will have to be reworked and will be down 8 weeks or more. | 2001-10-12 12:00 |  | 0 | U
17735 | BEA | BUSHTON | 32 | UNIT EXCHANGE | 2001-10-15 08:00 | 2001-11-01 16:00 | 17.3 | 0 | 0 | Unit 32 is in California for repair. We are putting unit 25 from Mullinvile it's place until further notice or unit 32 has been been completed and returned to service. | 2001-10-15 08:00 |  | 0 | P
17740 | AMA | BEAVER 5 | 4 | ELMWOOD PLANT | 2001-10-17 11:00 | 2001-11-18 16:00 | 32.2 | 0 | 0 | Unit down due to Elmwood Plant commoned southeast 24" and 8". Unit will not be able to buck high discharge pressure. Unit will be down as long as Elmwood Plant is operating this way.(Station down until further Notice). | 2001-10-17 11:00 |  | 0 | U
17655 | LIB | HOLCOMB | 9 | TURBO OVERHAUL | 2001-10-22 08:00 | 2001-11-09 16:00 | 18.3 | 0 | 0 | They need to overhaul the turbo charger. |  |  | 0 | P
17746 | BEA | BUSHTON | 26 | HEAD GASKET | 2001-10-23 07:00 | 2001-10-23 12:00 | 0.2 | 60 | 12.5 | Change out head gasket #10 head. 2000 HP |  |  | 0 | U
17691 | LIB | STEVENS 2 | 3 | SERVICE | 2001-10-23 08:00 | 2001-10-23 16:00 | 0.3 | 0 | 0 | Service the unit. |  |  | 0 | P
17470 | LIB | STEVENS 1 | 7 | REPLACE CONTROLLER | 2001-10-23 08:00 | 2001-10-24 16:00 | 1.3 | 0 | 0 | Replace TEC 9000 controller with DE2500. |  |  | 0 | P
17467 | LIB | MULLINVILLE | 22 | ANNUAL INSP | 2001-10-23 08:00 | 2001-11-02 16:00 | 10.3 | 0 | 0 | Annual inspection. |  |  | 0 | P
16964 | LIB | STEVENS 7 | 3 | MP2 TASKS | 2001-10-29 08:00 | 2001-11-02 16:00 | 4.3 | 0 | 0 | MP2 tasks and comp. insp. |  |  | 0 | P
17471 | LIB | TEXAS 1 | 2 | MP2 TASKS | 2001-10-29 08:00 | 2001-11-02 16:00 | 4.3 | 0 | 0 | MP2 tasks. |  |  | 0 | P
15944 | AMA | SPEARMAN | 2 | OVERHAUL | 2001-10-29 08:00 | 2001-11-16 12:00 | 18.2 | 0 | 0 | Minor overhaul. The date may change depending on #3 CB control project. 2250 HP (Will not start on this outage until unit 3 is back to normal operation). Start date moved back to coordinate with customer outages per their request. |  |  | 0 | P
17708 | LIB | HUGOTON | 16 | POST CHECK | 2001-10-30 08:00 | 2001-10-30 12:00 | 0.2 | 0 | 0 | Powt check unit from major overhaul that was done. 1800 HP |  |  | 0 | P
17450 | AMA | ELLIS 1 | 4 | 1500 HR INSP | 2001-10-30 09:00 | 2001-10-30 11:00 | 0.1 | 5 | 0.4 | 1500 Hr. Inspection. 1035 HP |  |  | 0 | P
17465 | LIB | MULLINVILLE | 18 | ANNUAL INSP | 2001-11-05 08:00 | 2001-11-09 16:00 | 4.3 | 0 | 0 | Annual inspection. |  |  | 0 | P
17609 | LIB | MORTON 1 | 4 | MAINTENANCE | 2001-11-06 07:30 | 2001-11-07 16:00 | 1.4 | 0 | 0 | Oil change compression test power valves. |  |  | 0 | P
15911 | LIB | STEVENS 2 | 8 | SERVICE & PM | 2001-11-06 08:00 | 2001-11-06 16:00 | 0.3 | 0 | 0 | Service unit panel board S/D & PM |  |  | 0 | P
15926 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2001-11-07 08:00 | 2001-11-13 16:00 | 6.3 | 0 | 0 | Service units. |  |  | 0 | P
17497 | BEA | BUSHTON | CONTROLLER #5 | CHECK VALVE | 2001-11-09 08:00 | 2001-11-09 15:00 | 0.3 | 130 | 37.9 | Remove check valve flapper from controller 5 check valve. (This date is tentative). Outage depends on approval and when Jomax Const can start. |  |  | 0 | P
17332 | BEA | CUNNINGHAM | ALL | ELEC SWITCH GEAR | 2001-11-12 07:00 | 2001-11-16 16:00 | 4.4 | 0 | 0 | Week of 11/12-16 all electrics will not be available. 11/12 & 13 dual fuels are available. 11/14 dual fuels are not available from 8:00 to 16:00 11/15 - 12 noon all units and plants should be available. Electric test switch gear and 4000 volt motors. |  |  | 0 | P
16935 | BEA | BUSHTON |  | LYONS FUEL GAS | 2001-11-14 08:00 | 2001-11-21 16:00 | 7.3 | 0 | 0 | Install 500 000 BTU/hr heater on the main fuel gas supply line and connect the Lyons gas into the main plant fuel gas. Also install filter/separator on the Lyons supply gas line. |  |  | 0 | P
15907 | LIB | STEVENS 2 | 6 | SERVICE | 2001-11-27 08:00 | 2001-11-27 16:00 | 0.3 | 0 | 0 | Service unit. |  |  | 0 | P
17732 | LIB | STEVENS 4 | 4 | MP2 WORK | 2001-11-28 07:00 | 2001-11-29 16:00 | 1.4 | 0 | 0 | MP@ work on unit 4. No volume loss. |  |  | 0 | P
16441 | LIB | TATE | 1 | OVERHAUL | 2001-12-03 08:00 | 2001-12-17 16:00 | 14.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
17610 | LIB | MORTON 1 | 4 | CONTROLS PM | 2001-12-04 07:30 | 2001-12-07 16:00 | 3.4 | 0 | 0 | Controls PM |  |  | 0 | P
17480 | LIB | HUGOTON | 17 | MAINTENANCE | 2001-12-06 08:00 | 2001-12-06 14:00 | 0.3 | 3 | 0.8 | Service and maintenance. 7800 HP |  |  | 0 | P
17612 | LIB | MORTON 6 | 2 | OIL CHANGE | 2001-12-11 07:30 | 2001-12-11 16:00 | 0.4 | 0 | 0 | Oil change. |  |  | 0 | P
17611 | LIB | MORTON 1 | 3 | CONTROLS PM | 2001-12-11 07:30 | 2001-12-14 16:00 | 3.4 | 0 | 0 | Controls PM |  |  | 0 | P
15903 | LIB | STEVENS 2 | 3 | PM | 2001-12-11 08:00 | 2001-12-11 16:00 | 0.3 | 0 | 0 | Panel board S/D & PM. |  |  | 0 | P
15928 | LIB | STEVENS 2 | 9 10 11 | SERVICE | 2001-12-11 08:00 | 2001-12-13 16:00 | 2.3 | 0 | 0 | Service units. |  |  | 0 | P
17613 | LIB | MORTON 6 | 1 | OIL CHANGE | 2001-12-12 07:30 | 2001-12-12 16:00 | 0.4 | 0 | 0 | Oil change. |  |  | 0 | P
16442 | LIB | TATE | 3 | OVERHAUL | 2001-12-17 08:00 | 2001-12-31 16:00 | 14.3 | 0 | 0 | Major engine and compressor overhaul. |  |  | 0 | P
11089 | LIB | MORTON 1 | 11 | SHOP O/H | 2001-12-30 08:00 | 2001-12-30 16:00 | 0.3 | 0 | 0 | Top End Head Change. Postponed until a later date. |  |  | 0 | P
11090 | LIB | MORTON 1 | 12 | SHOP O/H | 2001-12-30 08:00 | 2001-12-30 16:00 | 0.3 | 0 | 0 | Top End Head Change. Postponed until a later date. |  |  | 0 | P
17614 | LIB | MORTON 1 | 5 | CONTROLS PM | 2002-01-09 07:30 | 2002-01-11 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17615 | LIB | MORTON 1 | 6 | CONTROLS PM | 2002-01-16 07:30 | 2002-01-18 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17616 | LIB | MORTON 1 | 7 | CONTROLS PM | 2002-02-04 07:30 | 2002-02-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17673 | LIB | TEXAS 2 | 7 | ENGINE SERVICE | 2002-02-06 08:00 | 2002-02-06 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17617 | LIB | MORTON 1 | 10 | CONTROLS PM | 2002-02-11 07:30 | 2002-02-15 16:00 | 4.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17671 | LIB | TEXAS 1 | 3 | INSPECTION | 2002-02-18 08:00 | 2002-02-22 16:00 | 4.3 | 0 | 0 | 8 000 hr. inspection |  |  | 0 | P
17618 | LIB | TEXAS 2 | 6 | CONTROLS PM | 2002-03-04 07:30 | 2002-03-06 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17619 | LIB | TEXAS 2 | 7 | CONTROLS PM | 2002-03-11 07:30 | 2002-03-13 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17668 | LIB | TEXAS 1 | 2 | ENGINE SERVICE | 2002-03-19 08:00 | 2002-03-19 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17620 | LIB | TEXAS 1 | 2 | CONTROLS PM | 2002-04-08 07:30 | 2002-04-10 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17621 | LIB | TEXAS 1 | 6 | CONTROLS PM | 2002-04-15 07:30 | 2002-04-17 16:00 | 2.4 | 0 | 0 | Controls PM. |  |  | 0 | P
17676 | LIB | TEXAS 2 | 6 | ENGINE SERVICE | 2002-04-18 08:00 | 2002-04-18 16:00 | 0.3 | 0 | 0 | Engine service. |  |  | 0 | P
17151 | BEA | BUSHTON | 26 | OVERHAUL | 2002-04-29 08:00 | 2002-05-31 16:00 | 32.3 | 0 | 0 | Major overhaul on the power and compressor ends of an Ingersoll Rand KVS412 based on analysis and run hours. Unit will be disassembled and inspected and returned to OEM standards. |  |  | 0 | P