## Walter C Beckjord 06
Owner Name | Cinergy Corporation
Station Name | Walter C Beckjord Power Station
Unit Name | W C Beckjord 06
NERC Region | ECAR
State | OH
Fuel Type | Coal
Capacity | 434 MW
Start Date | 2001-09-30
End Date | 2001-12-08
Prv. Start Date | 2001-09-30
Prv. End Date | 2001-11-23
Comments | Turbine / Boiler Work
SIC | 4911
Plant ID | 1013762
Unit ID | 1003875
Outage ID | 16875

## ManChief 02
Owner Name | Fulton Cogeneration
Station Name | ManChief Power Station
Unit Name | GT 02
NERC Region | WSCC
State | CO
Fuel Type | Nat. gas
Capacity | 140 MW
Start Date | 2001-10-06
End Date | 2001-11-04
Prv. Start Date | 2001-10-06
Prv. End Date | 2001-11-09
Comments | Design Issues
SIC | 4931
Plant ID | 1041780
Unit ID | 1013226
Outage ID | 18375

## ManChief 01
Owner Name | Fulton Cogeneration
Station Name | ManChief Power Station
Unit Name | GT 01
NERC Region | WSCC
State | CO
Fuel Type | Nat. gas
Capacity | 140 MW
Start Date | 2001-10-06
End Date | 2001-11-04
Prv. Start Date | 2001-10-06
Prv. End Date | 2001-11-09
Comments | Design Issues
SIC | 4931
Plant ID | 1041780
Unit ID | 1013225
Outage ID | 18373

## Pine Bluff ST 1
Owner Name | Calpine Corporation
Station Name | Pine Bluff Energy Center
Unit Name | Unit 01 ST
NERC Region | SERC
State | AR
Fuel Type | Natural Gas
Capacity | 50 MW
Start Date | 2001-11-06
End Date | 2001-11-11
Comments | Design Issues
SIC | 4931
Plant ID | 1032399
Unit ID | 1012294
Outage ID | 18819

## Pine Bluff CT HRSG 1
Owner Name | Calpine Corporation
Station Name | Pine Bluff Energy Center
Unit Name | Unit 01 CT/HRSG
NERC Region | SERC
State | AR
Fuel Type | Natural Gas
Capacity | 168 MW
Start Date | 2001-11-06
End Date | 2001-11-11
Comments | Design Issues
SIC | 4931
Plant ID | 1032399
Unit ID | 1012298
Outage ID | 18818

## Stryker Creek 01
Owner Name | TXU Electric
Station Name | Stryker Creek Power Station
Unit Name | Unit 01
NERC Region | ERCOT
State | TX
Fuel Type | Natural Gas / Fuel Oil
Capacity | 177 MW
Start Date | 2001-11-09
End Date | 2001-11-22
Prv. Start Date | 2001-11-02
Prv. End Date | 2001-11-15
Comments | Boiler Inspection
SIC | 4911
Plant ID | 1000059
Unit ID | 1008591
Outage ID | 17978

## Stryker Creek 02
Owner Name | TXU Electric
Station Name | Stryker Creek Power Station
Unit Name | Unit 02
NERC Region | ERCOT
State | TX
Fuel Type | Natural Gas / Fuel Oil
Capacity | 527 MW
Start Date | 2001-10-19
End Date | 2001-11-06
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-11-01
Comments | Boiler Inspection and Maintenance
SIC | 4911
Plant ID | 1000059
Unit ID | 1008592
Outage ID | 17977

## Dresden 02
Owner Name | Exelon Nuclear
Station Name | Dresden Nuclear Power Station
Unit Name | Dresden 02
NERC Region | MAIN
State | IL
Fuel Type | Nuclear
Capacity | 828 MW
Start Date | 2001-10-20
End Date | 2001-11-07
Prv. Start Date | 2001-10-20
Prv. End Date | 2001-11-20
Comments | Refuel, Hoping to be at 100% by Friday
SIC | 4931
Plant ID | 1009265
Unit ID | 1007231
Outage ID | 8100

## El Dorado 01
Owner Name | El Dorado Energy LLC
Station Name | El Dorado Energy Merchant Power Station
Unit Name | Unit 01 GT/HRSG
NERC Region | WSCC
State | NV
Fuel Type | Natural Gas
Capacity | 160 MW
Start Date | 2001-11-05
End Date | 2001-11-18
Prv. Start Date | 2001-11-03
Prv. End Date | 2001-11-16
Comments | Turbine Overhaul
SIC | 4931
Plant ID | 1034719
Unit ID | 1012198
Outage ID | 17347

## Council Bluffs 01
Owner Name | MidAmerican Energy
Station Name | Council Bluffs Power Station
Unit Name | Council Bluffs 03
NERC Region | MAPP
State | IA
Fuel Type | Coal
Capacity | 49 MW
Start Date | 2001-09-30
End Date | 2001-11-01
Prv. Start Date | 2001-09-30
Prv. End Date | 2001-11-10
Comments | Turbine Overhaul
SIC | 4911
Plant ID | 1014234
Unit ID | 1005308
Outage ID | 18288

## Council Bluffs 02
Owner Name | MidAmerican Energy
Station Name | Council Bluffs Power Station
Unit Name | Council Bluffs 02
NERC Region | MAPP
State | IA
Fuel Type | Coal
Capacity | 82 MW
Start Date | 2001-11-05
End Date | 2001-11-11
Prv. Start Date | 2001-11-02
Prv. End Date | 2001-11-08
Comments | Annual Maintenance
SIC | 4911
Plant ID | 1014234
Unit ID | 1005312
Outage ID | 18286