## San Juan 02
Owner Name | Public Service Company
Station Name | San Juan Generating Station
Unit Name | San Juan 02
NERC Region | WSCC
State | NM
Fuel Type | Coal
Capacity | 350 MW
Start Date | 2001-11-10
End Date | 2001-11-14
Prv. Start Date | 2001-11-10
Prv. End Date | 2001-11-13
Comments | Work is finished.
SIC | 4911
Plant ID | 1016385
Unit ID | 1007770
Outage ID | 18881

## Spurlock 01
Owner Name | East Kentucky Power
Station Name | H L Spurlock Power Station
Unit Name | Spurlock 01
NERC Region | ECAR
State | KY
Fuel Type | Coal
Capacity | 305 MW
Start Date | 2003-03-15
End Date | 2003-05-09
Prv. Start Date | 2002-01-16
Prv. End Date | 2002-03-26
Comments | They will be doing the SCR work in Jan. 02 but will not be off-line for the tie-in until March of 03.
SIC | 4911
Plant ID | 1014316
Unit ID | 1006481
Outage ID | 9693

## Spurlock 02
Owner Name | East Kentucky Power
Station Name | H L Spurlock Power Station
Unit Name | Spurlock 02
NERC Region | ECAR
State | KY
Fuel Type | Coal
Capacity | 508 MW
Start Date | 2001-09-24
End Date | 2001-11-15
Prv. Start Date | 2001-09-24
Prv. End Date | 2002-01-15
Comments | Finished SCR tie-in but needed to repair some control problems.
SIC | 4911
Plant ID | 1014316
Unit ID | 1006482
Outage ID | 16533

## Greene County 01
Owner Name | Alabama Power Company
Station Name | Greene County Power Station
Unit Name | Greene County 01
NERC Region | SERC
State | AL
Fuel Type | Coal
Capacity | 299 MW
Start Date | 2002-01-04
End Date | 2002-01-31
Prv. Start Date | 2001-11-02
Prv. End Date | 2001-11-29
Comments | Replace Condenser
SIC | 4911
Plant ID | 1006899
Unit ID | 1006843
Outage ID | 17643

## Conemaugh 02
Owner Name | PSEG Power LLC
Station Name | Conemaugh Power Station
Unit Name | Conemaugh 02
NERC Region | MAAC
State | PA
Fuel Type | Coal
Capacity | 936 MW
Start Date | 2001-09-21
End Date | 2001-11-21
Prv. Start Date | 2001-09-21
Prv. End Date | 2001-11-23
Comments | Turbine Overhaul
SIC | 4931
Plant ID | 1017267
Unit ID | 1004350
Outage ID | 10367

## R D Green 02
Owner Name | Western Kentucky Energy
Station Name | R D Green Power Station
Unit Name | R D Green 02
NERC Region | ECAR
State | KY
Fuel Type | Coal
Capacity | 264 MW
Start Date | 2001-11-04
End Date | 2001-11-19
Prv. Start Date | 2001-11-04
Prv. End Date | 2001-12-15
Comments | Valve work on Boiler
SIC | 4931
Plant ID | 1012562
Unit ID | 1006381
Outage ID | 16417