## White Bluff 02
Owner Name | Entergy Arkansas Incorporated
Station Name | White Bluff Power Station
Unit Name | White Bluff 02
NERC Region | SERC
State | AR
Fuel Type | Coal
Capacity | 850 MW
Start Date | 2001-10-19
End Date | 2001-12-02
Prv. Start Date | 2001-10-12
Prv. End Date | 2001-10-19
Comments | Boiler Overhaul
SIC | 4911
Plant ID | 1014425
Unit ID | 1006232
Outage ID | 18280

## Spurlock 01
Owner Name | East Kentucky Power Company
Station Name | H L Spurlock Power Station
Unit Name | Spurlock 01
NERC Region | ECAR
State | KY
Fuel Type | Coal
Capacity | 508 MW
Start Date | 2001-09-24
End Date | 2001-11-24
Prv. Start Date | 2001-09-24
Prv. End Date | 2001-11-15
Comments | SCR Tie-in is complete, but unit will stay down for testing of control system.
SIC | 4911
Plant ID | 1014316
Unit ID | 1006482
Outage ID | 16533

## San Juan 02
Owner Name | Public Service Company of New Mexico
Station Name | San Juan Generating Station
Unit Name | San Juan 02
NERC Region | WSCC
State | NM
Fuel Type | Coal
Capacity | 350 MW
Start Date | 2001-11-10
End Date | 2001-11-14
Prv. Start Date | 2001-11-10
Prv. End Date | 2001-11-15
Comments | In startup right now, hoping to be at 100% by Friday evening.
SIC | 4911
Plant ID | 1016385
Unit ID | 1007770
Outage ID | 18881

## Riverside 01
Owner Name | AEP - Public Service Company of Oklahoma
Station Name | Riverside Power Station
Unit Name | Riverside 01
NERC Region | SPP
State | OK
Fuel Type | Natural Gas / Fuel Oil
Capacity | 472 MW
Start Date | 2001-11-30
End Date | 2001-12-13
Prv. Start Date | 2001-11-15
Prv. End Date | 2001-11-28
Comments | Boiler / Valve Work
SIC | 4911
Plant ID | 1009107
Unit ID | 1007284
Outage ID | 1175

## Baxter Wilson 02
Owner Name | Entergy Mississippi Inc.
Station Name | Baxter Wilson Power Station
Unit Name | Unit 02
NERC Region | SERC
State | MS
Fuel Type | Nat. gas/ Fuel Oil
Capacity | 783 MW
Start Date | 2001-10-21
End Date | 2002-01-04
Prv. Start Date | 2001-10-14
Prv. End Date | 2001-11-24
Comments | Major O/H
SIC | 4911
Plant ID | 1017000
Unit ID | 1007640
Outage ID | 17110

## Trinidad 06
Owner Name | TXU Electric
Station Name | Trinidad Power Station
Unit Name | Unit 06
NERC Region | ERCOT
State | TX
Fuel Type | Natural Gas / Fuel Oil
Capacity | 239 MW
Start Date | 2001-10-19
End Date | 2001-11-18
Prv. Start Date | 2001-10-19
Prv. End Date | 2001-11-15
Comments | Control Upgrade / Boiler Work
SIC | 4911
Plant ID | 1000538
Unit ID | 1008669
Outage ID | 12034