## Dresden 03
Owner Name | Exelon Nuclear
Station Name | Dresden Nuclear Power Station
Unit Name | Dresden 03
NERC Region | MAIN
State | IL
Fuel Type | Nuclear
Capacity | 828 MW
Start Date | 2001-12-11
End Date | 2001-12-20
Prv. Start Date | 2001-12-11
Prv. End Date | 2001-12-16
Comments | Dry wall cracks
SIC | 4931
Plant ID | 1009265
Unit ID | 1007232
Outage ID | 19161

## South Bay 04
Owner Name | Duke Energy South Bay LLC
Station Name | South Bay Power Station
Unit Name | South Bay 04
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas
Capacity | 240 MW
Start Date | 2001-09-29
End Date | 2001-12-23
Prv. Start Date | 2001-09-29
Prv. End Date | 2001-12-14
Comments | Running behind; hoping to be done by the holiday.
SIC | 4931
Plant ID | 1013339
Unit ID | 1007052
Outage ID | 15337

## Hunters Point 04
Owner Name | Pacific Gas and Electric
Station Name | Hunters Point Power Station
Unit Name | Hunters Point 04
NERC Region | WSCC
State | CA
Fuel Type | Natural Gas
Capacity | 156 MW
Start Date | 2001-10-07
End Date | 2001-10-19
Prv. Start Date | 2001-10-07
Prv. End Date | 2001-12-16
Comments | Major Boiler
SIC | 4911
Plant ID | 1011051
Unit ID | 1004950
Outage ID | 15375

## Catawba 02
Owner Name | Duke Energy Corporation
Station Name | Catawba Nuclear Power Station
Unit Name | Catawba 02
NERC Region | SERC
State | SC
Fuel Type | Nuclear
Capacity | 1205
Start Date | 2001-12-07
End Date | 2001-12-24
Prv. Start Date | 2001-12-07
Prv. End Date | 2001-12-18
Comments | repalcement of reactor coolant pump motor
SIC | 4911
Plant ID | 1013575
Unit ID | 1008375
Outage ID | 19137

## Navajo 03
Owner Name | Salt River project Agricultural
Station Name | Navajo Power Station
Unit Name | Navajo 03
NERC Region | WSCC
State | AZ
Fuel Type | Coal
Capacity | 803 MW
Start Date | 2001-11-30
End Date | 2001-12-16
Prv. Start Date | 2001-11-30
Prv. End Date | 2002-02-27
Comments | Some generator work, not overhaul. They will be taking the unit back down in late Jan. early Feb. for a month. Have not set a firm date yet to do Gen rehab.
SIC | 4911
Plant ID | 1015877
Unit ID | 1007206
Outage ID | 19052