## Lacygne 01
Owner Name | Kansas City Power and Light
Station Name | Lacygne Power Station
Unit Name | Lacygne 01
NERC Region | SPP
State | KS
Fuel Type | Coal
Capacity | 893 MW
Start Date | 2001-11-04
End Date | 2001-12-26
Prv. Start Date | 2001-11-04
Prv. End Date | 2001-12-20
Comments | Having problems bringing it back on-line; should have it on-line right after the holidays.
SIC | 4911
Plant ID | 1014955
Unit ID | 1006085
Outage ID | 18542

## Mojave 01
Owner Name | Southern California Edison Company
Station Name | Mojave Power Station
Unit Name | Mojave 01
NERC Region | WSCC
State | NV
Fuel Type | Coal
Capacity | 818MW
Start Date | 2001-12-07
End Date | 2001-12-26
Prv. Start Date | 2001-12-07
Prv. End Date | 2001-12-22
Comments | complications with boiler
SIC | 4931
Plant ID | 1015381
Unit ID | 1006329
Outage ID | 19129

## Catawba 02
Owner Name | Duke Energy Company
Station Name | Catawba Nuclear Power Station
Unit Name | Catawba 02
NERC Region | SERC
State | SC
Fuel Type | Nuclear
Capacity | 1,205 MW
Start Date | 2001-12-07
End Date | 2001-12-22
Prv. Start Date | 12/0701
Prv. End Date | 2001-12-24
Comments | Reactor Coolant Pump Motor Replacement. Unit is in start up now and should be online tomorrow. They should reach full power by 12/24/01.
SIC | 4911
Plant ID | 1013575
Unit ID | 1008375
Outage ID | 19137

## Chalk Point 02
Owner Name | Mirant Mid-Atlantic, LLC
Station Name | Chalk Point Power Station
Unit Name | Unit 02
NERC Region | MAAC
State | MD
Fuel Type | Coal / Fuel Oil
Capacity | 364 MW
Start Date | 2001-10-05
End Date | 2001-12-23
Prv. Start Date | 2001-10-05
Prv. End Date | 2001-12-28
Comments | Overhaul
SIC | 4911
Plant ID | 1000422
Unit ID | 1005957
Outage ID | 17465