## Runbook
Enron SAP Financial Closing Runbook
Business Unit
STEP | CORP | Europe | 1/1/00 Go-live | EBS | 7/1/00 Go-live | Event | I/F ID | Program Name | INTERIM? | AUTO | MANUAL | WORKDAY | Interim Wkdy | STATUS | Job/Program/Tranx | Trigger | Responsible Party | Corp Contact | Europe Contact | EI/OEC/ EE&CC/ NEPCO Contact | Comments
1 |  |  | 4 | 4 | 4 | Labor Distribution -HR to FI |  |  |  |  | 4 |  | -10 |  | ALE-HR to FI | Payroll Periods | COE-HR | Chris Thai |  |  | This is the payroll run for every cycle.
2 |  |  | 4 | 4 | 4 | Labor Distribution - True Up - 16th | 281 |  |  |  | 4 |  | -10 |  | ZFI281_LABOR_DIST |  | Joel Velders/Mark Pope | Chris Thai |  |  | This is run after the middle of the month payroll is run.
3 |  |  | 4 | 4 | 4 | Maintenance of Overhead Costing Sheet rates - DUE |  |  |  |  | 4 |  | -5 |  | KZA1 |  | COE- Controlling | n/a | n/a |  | Business Units to provide rate updates monthly by -5 workday.
ALL COSTING SHEETS MUST BE SUBMITTED by 6pm CST, WORKDAY -5
4 | 4 | 4 | 4 | 4 | 4 | Create system message notifying MM users of MM period close date |  |  |  |  | 4 |  | -3 |  | SM02 | Workday | COE- MM | n/a | n/a | n/a | Also notify BASIS to postpone or cancel scheduled jobs during MM close timeframe.
ALL RECURRING ENTRY DOCUMENTS FOR ACCOUNTING MONTH MUST BE ENTERED by 8am CST, WORKDAY -1
ALL CURRENT MONTH MM TRANSACTIONS MUST BE COMPLETE by 6pm CST, WORKDAY -1
5 | 4 | 4 | 4 | 4 | 4 | Close MM Periods |  |  | N |  | 4 | -1 | -1 |  | SMMCP_Close_Period / MMPV | Last day of month | COE- MM | n/a | n/a | n/a | MM Users must be out of system. Also, BASIS postpones and/or cancel scheduled backup jobs.
6 | 4 | 4 | 4 | 4 | 4 | Execute Recurring Entries |  |  | N |  | 4 | -1 | -1 |  | F.14 | Entries Ready | COE- Financial | Regina Hawley | Rayees Moizuddin |  | Batch session naming convention: YYMMRECURR
7 | 4 | 4 | 4 | 4 | 4 | Post Recurring Entry Documents via BDC |  |  | N |  | 4 | -1 | -1 |  | SM35 | Recurring Entries Run | COE- Financial | n/a | n/a | n/a | BDC Session(s) have no name convention here
8 |  | 4 |  |  |  | London Centrefile | 476 |  | Y | 4 |  | -1 | -1 |  | ZFU_COMMON _FB01 / Variant : IA_00476_001 | Receive File | London COE - Fin | n/a | James Britton | n/a | Verify monthly centerfile interface has been received (20th of month)
9 |  | 4 |  |  |  | London Training Recharge |  |  |  |  | 4 |  | -1 |  |  |  | London COE - Fin | n/a | James Britton | n/a | Verify movement of costs
10 | 4 | 4 | 4 | 4 | 4 | Execute Test Depreciation Run |  |  | N |  | 4 | -1 | -1 |  | AFAB |  | COE- Assets/IM | Regina Hawley | Nuala Bennetts |  | Execute by Company Code
11 | 4 | 4 | 4 |  |  | Internal Order Settlement - CAP1 TEST |  |  | N |  | 4 | -1 | -1 |  | KO8G | JE's to Orders Done | COE- Controlling / London COE - Cont | Regina Hawley | James Britton | n/a
12 |  | 4 | 4 |  |  | Internal Order Settlement - AEO1 TEST |  |  | N |  | 4 | -1 | -1 |  | KO8G | JE's to Orders Done | COE- Controlling / London COE- Cont | n/a | James Britton | n/a
13 | 4 | 4 | 4 | 4 | 4 | Project System Settlement- Test |  |  | N |  | 4 | -1 | -1 |  | CJ8G | End of Month | COE- Project Systems | Regina Hawley | Nuala Bennetts |  | This will expand as we add variants.
ALL CURRENT MONTH AP TRANSACTIONS MUST BE ENTERED BY 8am CST, WORKDAY 1
13 | 4 | 4 | 4 | 4 | 4 | Close A/P for prior month, Open next period |  |  | N |  | 4 | 1 | 1 |  | OB52 | MM Period Rolled | COE- Financial | Elaine Schield | Sean Connor |  | Close "K" accounts for prior month, Open all accounts for new month. Need Contact to make go/no-go decision on closing vendors
14 | 4 | 4 | 4 | 4 | 4 | Close MM for prior month |  |  | N |  | 4 | 1 | 1 |  | OB52 | MM Period Rolled | COE- Financial | Elaine Schield | Sean Connor |  | Close "M" accounts for prior month, Open all accounts for new month.
14 |  |  | 4 |  |  | Execute Depreciation Run I |  |  | N |  | 4 | 1 | 1 |  | AFAB | G&A Postings Done | COE- Assets/IM | n/a | n/a |  | 01U9, 027W, 0388, 0502, 061M, 061N, 061P, 067S, 0815, 0413
15 |  |  | 4 |  |  | Post Depreciation |  |  | N |  | 4 | 1 | 1 |  | SM35 | Deprec Run Complete | COE- Assets/IM | n/a | n/a |  | Execute BDC Session(s) "RABUCHxx"
16 |  |  | 4 | 4 |  | PS Plan Overhead Allocation |  |  |  |  | 4 |  | 1 |  | CJ47 | Workday | COE- Controlling | n/a | n/a
17 |  |  | 4 | 4 |  | PS Plan Settlement |  |  |  |  | 4 |  | 1 |  | CJ9G | Workday | COE- Controlling | n/a | n/a
18 | 4 |  |  |  |  | CORP Plan Assessments |  |  |  |  | 4 |  | 1 |  | KSU5 | Workday | COE- Controlling | Dawn Derr | n/a | n/a
19 | 4 |  | 4 | 4 | 4 | Review Costing Sheets | [8 empty] | Outside SAP | Workday |  | n/a | n/a
20 | 4 | 4 | 4 | 4 | 4 | Clear General Ledger Accounts GR/IR Acct 30018000 |  |  | N |  | 4 | 1 | 1 |  | F.19 | MM Period Rolled | COE- Financial | n/a | n/a | n/a | Variant: GR/IR Clear / Future Autosys Job:SFICP_GR/IR_CLEARING
21 | 4 | 4 | 4 | 4 | 4 | Clear General Ledger Accounts GR/IR Acct 26165000 |  |  | N |  | 4 | 1 | 1 |  | F.19 | End of Month | COE- Financial | n/a | n/a | n/a | Variant: GR/IR Clear / Future Autosys Job:SFICP_GR/IR_CLEARING
21 | 4 | 4 | 4 | 4 | 4 | Month End Exchange Rate Calculation | 599 |  | N | 4 |  | 2 | 1 |  | ZTR_IF_FX_AVERAGE_ CALCULATION | Workday | Glen Norman | n/a | n/a | n/a | Verfiry that month end exchange rates have been loaded and communicated to the business, including Teeside and Global. Jobs kicks off @ 2am CST
22 | 4 | 4 | 4 | 4 | 4 | Month End Exchange Rate Load Verification | 600 |  |  | 4 |  |  | 1 |  | RFTBFF00 | Workday | Glen Norman | n/a | Rayees | n/a | Post job will kick off right after calculation is complete.
23 | 4 |  |  |  |  | Upload EPSC Allocations to SAP-FI | 315 |  | N | 4 |  | 1 | 1 |  | ZFU_COMMON _FB01 / Variant : IA_00315_001 | Receive File from Steve Dunbar | Glen Norman |  |  |  | No dependency for assessments/ Business Units focal points are to resolve posting errors (ie, errant cost center/project/trading partners, etc)
24 | 4 |  |  |  |  | Upload EIS Allocations SAP-FI | 316 |  | N |  | 4 | 1 | 1 |  | ZFU_COMMON _FB01 / Variant : IA_00316_001 | Receive File from Bill Meyers | Glen Norman |  |  |  | No dependency for assessments/ Business Units focal points are to resolve posting errors (ie, errant cost center/project/trading partners, etc)
25 | 4 |  |  |  |  | Clear BDC Session Errors |  |  | N |  | 4 | 1 | 1 |  | SM35 | Errors kick out to BDC | Business Units | Karen Choyce | n/a | n/a
26 |  |  |  |  | 4 | Create WBS Element Groups for GPG Allocations |  |  | N |  | 4 | 1 | 1 |  | CJSG | End of Month | Business Units | Karen Choyce | n/a | n/a | Name GPG01 - Is used in a lot of allocation cycles. Must be right.
26 | 4 |  |  |  |  | Corp: Actual Assessments (A) |  |  | N |  | 4 | 1 | 2 |  | KSU5 | Assessments Ready | Corp Acct: Dawn Derr | Chad Nichols | n/a | n/a | Cycles: CO0001, CO0011 NO Interface dependencies
27 | 4 |  |  |  |  | Corp: Actual Assessments (B) |  |  | N |  | 4 | 1 | 2 |  | KSU5 | JE's to CCtrs Done | Corp Acct: Dawn Derr | Dawn Derr | n/a | n/a | Cycles: CO0ACT, COAA11, COAOPS, COEITT
28 |  |  | 4 |  |  | OEC: Actual Assessment |  |  |  |  | 4 |  | 2 |  | KSU5 / Cycle: 983G&A | JE's to CCtrs Done | COE- Controlling |  |  |  | Maintained by Wayne Tencer; Currently run by COE.
29 | 4 |  |  |  |  | Execute FI - CO Reconciliation (Actual) |  |  | N |  | 4 | 1 | 2 |  | KALC | Corp & OEC G&A Actual Assess done | COE- Controlling | Karen Choyce | n/a | n/a
30 |  |  | 4 | 4 | 4 | Labor Distribution - True Up | 281 |  |  |  | 4 |  | 2 |  | ZFI281_LABOR_DIST | Last day of month | Joel Velders | Chris Thai | n/a | n/a
31 |  |  | 4 | 4 | 4 | CATS Transfer | 281 |  |  |  | 4 |  | 2 |  | CAT5 | 2nd Workday of Month | COE- Project Systems | Chris Thai | n/a | n/a
32 | 4 |  |  |  |  | Execute FI - CO Reconciliation (Actual) |  |  | N |  | 4 | 1 | 2 |  | KALC | Cats Transfer | COE- Controlling | Karen Choyce | n/a | n/a
33 | 4 | 4 | 4 | 4 |  | EC-CS Valuation |  |  |  |  | 4 |  | 3 |  | CXCD |  | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
34 | 4 | 4 | 4 | 4 |  | EC-CS Rollup |  |  | N |  | 4 | 2 | 3 |  | CXCD |  | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
35 | 4 | 4 | 4 | 4 |  | Send Data to Corporate Hyperion | 362 |  | N |  | 4 | 2 | 3 |  | ZGL_IF_HYPERION / Var: ONLINE_RUN |  | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin |  | Hyperion Data loaded @ 8am CST
36 |  | 4 |  |  |  | ATES Interface | 543 |  | Y |  | 4 | 2 | 3 |  | ZCO_IF_543_ATES_INBOUND | London Training Recharge Complete | London COE- Cont | n/a | James Britton | n/a | SKF residual allocation postings rely on ATES interface
37 |  | 4 |  |  |  | SKF Postings for residual allocation for 0342 | 503 |  | N |  | 4 | 2 | 3 |  | ZCO_SKF_POST_503 | ATES Interface posted | London COE- Cont | n/a | James Britton | n/a
38 |  | 4 |  |  |  | SKF Postings for residual allocation for 028D | 503 |  | N |  | 4 | 2 | 3 |  | ZCO_SKF_POST_503 | ATES Interface posted | London COE- Cont | n/a | James Britton | n/a
39 |  | 4 |  |  |  | SKF Postings for secondary allocation |  |  | Y |  | 4 | 2 | 3 |  |  | File Received | London COE- Cont | n/a | James Britton | n/a
40 |  |  | 4 | 4 |  | Contractor True-Up | ??? |  |  |  | 4 |  | 3 |  |  | CATS Txfrs complete | COE- Project Systems
41 |  |  |  |  | 4 | Execute Fixed Labor Distribution/Assessments |  |  |  |  | 4 |  | 3 |  | KSU5 | True Up Posted | COE- Controlling
42 |  |  |  |  | 4 | Execute Automated SKF posting program for GPG |  |  |  |  | 4 |  | 3 |  | ZSKCP | Execute Fixed Labor Distribution/Assessments | COE- Controlling
43 |  |  |  |  | 4 | Execute GPG Assessments - Benefits, Taxes, & Incidentals |  |  |  |  | 4 |  | 3 |  | KSU5 | Execute Automated SKF posting program for GPG | COE- Controlling |  |  |  | For ENA Company Code 0012 Also.
44 |  |  |  |  | 4 | Execute GPG Distributions Incidentals |  |  |  |  | 4 |  | 3 |  | KSV5 | Execute GPG Assessments - Benefits, Taxes, & Incidentals | COE- Controlling |  |  |  | For ENA Company Code 0012 Also.
45 |  |  |  |  | 4 | Execute GPG Assessments Residuals |  |  |  |  | 4 |  | 3 |  | KSU5 | Execute GPG Distributions Incidentals | COE- Controlling |  |  |  | For ENA Company Code 0012 Also.
46 |  |  |  |  | 4 | Run FERC Std Cost Adj |  |  |  |  | 4 |  | 3 |  | FERO | GPG Assessments Completed | COE-Financial |  |  |  | FERC Standard Cost Run in Test to verify all F Cost Centers are Zero.
47 |  |  | 4 |  |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU EE&CC | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
48 |  |  | 4 |  |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU CALME | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
49 |  |  | 4 |  |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU SO CONE | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
50 |  |  | 4 |  |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU NEPCO | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
51 |  |  | 4 |  |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU OEC | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
52 |  |  | 4 |  |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU APACHI | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
53 |  |  | 4 |  |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU INDIA | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
54 |  |  |  | 4 |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU EBS | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
55 |  |  |  | 4 |  | PS-Overhead Allocation |  |  |  |  | 4 |  | 3 |  | CJ45: BU GPG | True Up Posted | COE- Project Systems | n/a | n/a |  | Final CATS transfer and true-up must be posted.
55 | 4 | 4 | 4 | 4 | 4 | Execute Accrual/Deferral Documents & Reversals |  |  | N |  | 4 | 2 | 3 |  | FBS1 | JE's Complete | COE- Financial | Karen Choyce | Rayees Moizuddin
56 | 4 |  |  |  |  | Post Sales & Use Tax Accruals |  |  |  |  | 4 |  | 3 |  | ZAP525 | Entries Complete | COE- Tax | n/a | n/a | n/a | Carol Brantz
ALL GENERAL & ADMINISTRATIVE P&L POSTINGS MUST BE COMPLETED BY 8am CST, WORKDAY 4
57 | 4 | 4 | 4 | 4 |  | EC-CS Valuation |  |  |  |  | 4 |  | 4 |  | CXCD |  | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
58 | 4 | 4 | 4 | 4 |  | EC-CS Rollup |  |  | N |  | 4 | 2 | 4 |  | CXCD |  | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
59 | 4 | 4 | 4 | 4 |  | Send Data to Corporate Hyperion | 362 |  | N |  | 4 | 2 | 4 |  | ZGL_IF_HYPERION / Var: ONLINE_RUN |  | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin |  | Hyperion Data loaded @ 8am CST
60 | 4 | 4 | 4 | 4 |  | Close P&L accounts for G&A |  |  |  |  | 4 | 2 | 4 |  | OB52 | 8am CST | COE- Financial | Karen Choyce | James Britton
61 |  |  | 4 |  |  | PS Interest Calculation |  |  |  |  | 4 |  | 4 |  | CJZ1: BU CALME | P&L Accounts Closed | COE- Project Systems | n/a | n/a
62 |  |  | 4 |  |  | PS Interest Calculation |  |  |  |  | 4 |  | 4 |  | CJZ1: BU SO CONE | P&L Accounts Closed | COE- Project Systems | n/a | n/a
63 |  |  | 4 |  |  | PS Interest Calculation |  |  |  |  | 4 |  | 4 |  | CJZ1: BU APACHI | P&L Accounts Closed | COE- Project Systems | n/a | n/a
64 |  |  | 4 |  |  | PS Interest Calculation |  |  |  |  | 4 |  | 4 |  | CJZ1: BU INDIA | P&L Accounts Closed | COE- Project Systems | n/a | n/a
65 |  |  | 4 |  |  | PS Interest Calculation |  |  |  |  | 4 |  | 4 |  | CJZ1: BU GPG | P&L Accounts Closed | COE- Project Systems | n/a | n/a
66 |  |  | 4 |  |  | JVA Reclass of Realized Gains/Losses - Foreign Currency |  |  |  |  | 4 |  | 4 |  | GJ90 | Close P&L accounts for G&A | COE- Joint Venture | n/a | n/a |  | Use for all "Fully Configured JV companies and "Partially Configured JV Companies. Executed individually for EACH JVA (full & partial) company
67 |  |  | 4 |  |  | JVA Pre-cutback Equity Change Management |  |  |  |  | 4 |  | 4 |  | GJEC | JVA Reclass of Realized Gains/Losses - Foreign Currency | COE- Joint Venture | n/a | n/a
68 |  |  | 4 |  |  | Prior Period Equity Adjustment |  |  |  |  | 4 |  | 4 |  | GJ19 | JVA Pre-cutback Equity Change Management | COE- Joint Venture | n/a | n/a |  | This program needs to be run for "Fully Configured JVA companies only"
69 |  |  | 4 |  |  | JV Cutback |  |  |  |  | 4 |  | 4 |  | GJCB | Prior Period Equity Adjustment | COE- Joint Venture | n/a | n/a |  | This program needs to be run for "Fully Configured JVA companies only"
70 |  | 4 |  |  |  | EUR Actual Assessment I for Residual Allocation for 0342 |  |  | N |  | 4 | 1 | 4 |  | KSU5 Cycle EE001 | G&A Accounts closed | London COE- Cont | n/a | James Britton | n/a
71 |  | 4 |  |  |  | EUR Actual Assessment I for Residual Allocation for 028D |  |  | N |  | 4 | 1 | 4 |  | KSU5 Cycle EE004 | G&A Accounts closed | London COE- Cont | n/a | James Britton | n/a
72 |  |  | 4 |  |  | Distribution - General (Argentina) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle DSAR01 | OH Complete | COE- Controlling
73 |  |  | 4 |  |  | Assessment - CC to OH Order (EECC to BU) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle DEOVHD | OH Complete | COE- Controlling | n/a | n/a
74 |  |  | 4 |  |  | Assessment - CC to OH Order (APACHI) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle AA_OH | Cycle DEOVHD complete | COE- Controlling | n/a | n/a
75 |  |  | 4 |  |  | Assessment - CC to OH Order (CALME) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle CALMOH | Cycle DEOVHD complete | COE- Controlling | n/a | n/a
76 |  |  | 4 |  |  | Assessment - CC to OH Order (EECC OH) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle EECCOH | Cycle DEOVHD complete | COE- Controlling | n/a | n/a
77 |  |  | 4 |  |  | Assessment - CC to OH Order (INDIA) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle INDAOH | Cycle DEOVHD complete | COE- Controlling | n/a | n/a
78 |  |  | 4 |  |  | Assessment - CC to OH Order (OEC) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle OEC_OH | Cycle DEOVHD complete | COE- Controlling | n/a | n/a
79 |  |  | 4 |  |  | Assessment - CC to OH Order (SO CONE) |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle SC_OH | Cycle DEOVHD complete | COE- Controlling | n/a | n/a
80 |  |  |  |  | 4 | Execute SKF Upload program for ENA |  |  |  |  | 4 |  | 4 |  | ZCO_530 |  | COE- Controlling
81 |  |  |  |  | 4 | Execute ENA Assessments |  |  |  |  | 4 |  | 4 |  | KSU5 |  | COE- Controlling
82 |  |  |  |  | 4 | Unlock R-Cost Centers |  |  |  |  | 4 |  | 4 |  | ZCCLOCK |  | COE- Controlling |  |  |  | Program: Lock_R_CC
83 |  |  |  |  | 4 | Settle OH orders (1st group) |  |  |  |  | 4 |  | 4 |  | K08G:OH_ORDERS_1 |  | COE- Controlling
84 |  |  |  |  | 4 | Settle OH orders (2nd group) |  |  |  |  | 4 |  | 4 |  | K08G:OH_ORDERS_2 |  | COE- Controlling
85 |  |  |  |  | 4 | Lock R-Cost Centers |  |  |  |  | 4 |  | 4 |  | ZCCLOCK |  | COE- Controlling |  |  |  | Program: Lock_R_CC
86 |  |  | 4 | 4 |  | Settlement of OH Orders |  |  |  |  | 4 |  | 4 |  | KO8G: OHO1 | CC to OH Order cycles complete | COE- Controlling | n/a | n/a
87 | 4 | 4 |  |  |  | Internal Order Settlement - CAP1 |  |  | N |  | 4 | 1 | 4 |  | KO8G: CAP1 | JE's Complete | COE- Controlling | n/a | James Britton | n/a
88 |  | 4 |  |  |  | Internal Order Settlement - CAP1 Line Item Settlement |  |  |  |  | 4 | 1 | 4 |  | KO8G: CAP1 W/ LI | JE's Complete | COE- Controlling | n/a | Nuala Bennetts | n/a
89 | 4 | 4 |  |  |  | Internal Order Settlement - AEO1 Support Orders |  |  | N |  | 4 | 1 | 4 |  | KO8G Var: EEEPOLSUP | JE's Complete | London COE- Cont | n/a | James Britton | n/a
90 |  | 4 |  |  |  | EUR Actual Assessments Support CCrts London |  |  | N |  | 4 | 1 | 4 |  | KSU5 Cycles EE002 | Capital & Support Orders settled | London COE- Cont | n/a | James Britton | n/a
91 |  | 4 |  |  |  | EUR Actual Assessments Commercial CCrts London |  |  |  |  | 4 |  | 4 |  | KSU5 Cycles EE003 | Cycle EE003 complete | London COE- Cont
92 |  | 4 |  |  |  | EUR Actual Assessments Generic CCtrs Frankfurt |  |  |  |  | 4 |  | 4 |  | KSU5 Cycles EE005 | Cycle EE002 complete | London COE- Cont
93 |  | 4 |  |  |  | Internal Order Settlement - EPOL Commerical Settlements |  |  | N |  | 4 | 1 | 4 |  | KO8G Var: EEEPOLCOM | EUR Act Assess III | London COE- Cont | n/a | James Britton | n/a
94 |  | 4 |  |  |  | Internal Order Settlement - AEO1, Multiple |  |  |  |  | 4 | 1 | 4 |  | KO8G Var: EEMULTI | Non-EPOL settlement 2 complete | London COE- Cont | n/a | James Britton | n/a
95 |  | 4 |  |  |  | Internal Order Settlement - AEO1, Single Order |  |  |  |  | 4 | 1 | 4 |  | KO8G Var: EEOTHER | Multiple Order Settlement complete | London COE- Cont | n/a | James Britton | n/a
96 |  | 4 |  |  |  | EUR Actual Assessments Support CCtrs Frankfurt |  |  |  |  | 4 |  | 4 |  | KSU5 Cycles EE006 | Single Order Settlement complete | London COE- Cont
97 | 4 |  |  |  |  | Run Intercompany Interest | 415 |  | Y |  | 4 | 2 | 4 |  | ZGL_IF_415_MSA_INTEREST/ Z415 | JE's done | COE- Financial | Karen Choyce | Anne Hicks/ Sean Connor | n/a | INTERIM PROCESS UNTIL 7/1/00 - ? What is Corp Process?+V57
98 |  | 4 | 4 |  |  | Post GAAP adjustments for assets/Periodic Posting |  |  |  |  | 4 |  | 4 |  | ASKB |  | COE- Assets/IM | n/a | Nuala Bennetts
99 | 4 | 4 | 4 | 4 | 4 | Lock Program for PS Update |  |  |  |  | 4 |  | 4 |  |  |  | COE- Project Systems
100 | 4 | 4 | 4 | 4 | 4 | PS Settlement |  |  | N |  | 4 | 1 | 4 |  | CJ8G | JE's Complete | COE- Project Systems | Regina Hawley | Nuala Bennetts |  | This will expand as we add variants.
101 |  |  |  |  | 4 | Unlock R-Cost Centers |  |  |  |  | 4 |  | 4 |  | ZCCLOCK |  | COE- Controlling |  |  |  | Program: Lock_R_CC
102 |  |  |  |  | 4 | Execute FAR Order Settlement |  |  |  |  | 4 |  | 4 |  | K08G: FAR_ORDERS | PS Settlement Complete | COE- Controlling
103 |  |  |  |  | 4 | Lock R-Cost Centers |  |  |  |  | 4 |  | 4 |  | ZCCLOCK |  | COE- Controlling |  |  |  | Program: Lock_R_CC
104 | 4 | 4 | 4 | 4 | 4 | Execute Depreciation Run II |  |  | N |  | 4 |  | 4 |  | AFAB | Periodic posting complete | COE- Assets/IM | Regina Hawley | Nuala Bennetts |  | Execute by Company Code
105 | 4 | 4 | 4 | 4 | 4 | Post Depreciation |  |  | N |  | 4 |  | 4 |  | SM35 | Deprec Run Complete | COE- Assets/IM | Regina Hawley | Nuala Bennetts |  | Execute BDC Session(s) "RABUCHxx"
106 |  |  |  |  | 4 | Execute Composite Depreciation | 50 |  |  |  | 4 |  | 4 |  | ZAKOMP01 | Deprec Run Complete | COE- Assets/IM
107 |  |  |  |  | 4 | Execute Composite Depreciation | 51 |  |  |  | 4 | 1 | 4 |  | ZAKOMP02 | Deprec Run Complete | COE- Assets/IM
108 |  |  |  |  | 4 | Copy File to Access File |  |  |  |  | 4 | 4 | 4 |  |  | Deprec Run Complete | COE- Assets/IM
109 |  |  |  |  | 4 | Unlock R-Cost Centers |  |  |  |  | 4 |  | 4 |  | ZCCLOCK |  | COE- Controlling |  |  |  | Program: Lock_R_CC
110 |  |  |  |  | 4 | Distribution-GPG |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle ? | Depreciation Posted |  |  |  |  | Pending Development-Lee Baker
111 |  |  |  |  | 4 | Assessment-GPG |  |  |  |  | 4 |  | 4 |  | KSU5 Cycle ? | Distribution Complete |  |  |  |  | Pending Development-Lee Baker
112 |  |  |  |  | 4 | Lock R-Cost Centers |  |  |  |  | 4 |  | 4 |  | ZCCLOCK | Assessment Complete | COE- Controlling |  |  |  | Program: Lock_R_CC
113 |  |  |  |  | 4 | FERC Std Cost Adj |  |  |  |  | 4 |  | 4 |  | FERO | All Costs transferred | COE-Financial |  |  |  | Verify all F Cost Centers are Zero
114 |  |  |  |  | 4 | FERC Flow of Cost Trace-Test |  |  |  |  | 4 |  | 4 |  | FERO | FERC Std Cost Adj | COE-Financial |  |  |  | Traces all CO Objects to see if they are assigned a FERC assignment - Run until run is clean of errors. Fix any errors.
115 |  |  |  |  | 4 | FERC Flow of Cost Trace-Real |  |  |  |  | 4 |  | 4 |  | FERO | FERC Std Cost Adj | COE-Financial |  |  |  | Traces all CO Objects to see if they are assigned a FERC assignment - Run until run is clean of errors not in test mode.
116 |  |  |  |  | 4 | FERC Post Traced Costs |  |  |  |  | 4 |  | 4 |  | FERO | FERC Flow of Cost | COE-Financial |  |  |  | Post Traced Costs to FERC accounts via JE.
117 |  |  |  |  | 4 | FERC Direct Post |  |  |  |  | 4 |  | 4 |  | FERO | FERC Trace Posted | COE-Financial |  |  |  | Post Direct Post accounts to FERC accounts via JE
118 |  |  |  |  | 4 | Validate FERC accounts to Natural Accounts |  |  |  |  | 4 |  | 4 |  |  | FERC Direct Post | COE-Financial |  |  |  | If not correct analyze and contact representative and fix error.
119 | 4 | 4 | 4 | 4 | 4 | Transfer Assets to PCA |  |  | N |  | 4 | 1 | 4 |  | 1KEI | Post Depreciation Complete | COE- Controlling | n/a | Rayees Moizuddin
120 | 4 | 4 |  |  |  | AA Reconciliation Analysis (Inventory) |  |  | N |  | 4 | 1 | 4 |  | Outside SAP | Post Depreciation Complete | Business Units | Regina Hawley | Nuala Bennetts |  | REPORT CURRENTLY NOT IN PRODUCTION
121 | 4 | 4 | 4 | 4 | 4 | Run Internal Order Balance Report |  |  | N |  | 4 | 2 | 4 |  | Report OR01 | Orders Settled | COE- Controlling | n/a | James Britton |  | All Internal Order Balances should equal $0
122 | 4 | 4 | 4 | 4 | 4 | Execute FI - CO Reconciliation -Final run |  |  | N |  | 4 | 1 | 4 |  | KALC | Orders Settled | COE- Controlling | n/a | James Britton | n/a
123 | 4 | 4 | 4 | 4 | 4 | Intercompany Processing |  |  |  |  | 4 | 2 | 4 |  | Outside SAP | FI/CO rec Complete | Business Units |  | Mario Woznica |  | VAT Tax & review
124 | 4 | 4 | 4 | 4 | 4 | SPL to TIS Interface Test Files | 436 |  | N |  | 4 | 5 | 4 |  | ZAMGAINLOSS/ZAMTB/ZFITB | End of Day | COE- Financial | n/a | n/a | n/a | ZFITB-ABC; ZAMTB-DEFGI, ZAMGAINLOSS-H
125 |  |  |  |  | 4 | Execute Order Summarization |  |  | N |  | 4 | 5 | 4 |  | SART: Order Summarization | Orders Settled | COE- Controlling | n/a | n/a | n/a | 1. Hierachy: Z_FAR_01 2. Summarization: selected 3. Year & Months Input current year and months being processed. 4. Background: selected
ALL AR TRANSACTIONS (INCL CASH APP) MUST BE COMPLETE by 6pm CST, WORKDAY 5
126 | 4 | 4 | 4 | 4 | 4 | EC-CS valuation |  |  |  |  | 4 | 2 | 5 |  | CXCD | JE's Complete | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
127 | 4 | 4 | 4 | 4 | 4 | EC-CS rollup |  |  | N |  | 4 | 2 | 5 |  | CXCD | JE's Complete | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
128 | 4 | 4 | 4 | 4 | 4 | Send Data to Corporate Hyperion | 362 |  | N |  | 4 | 2 | 5 |  | ZGL_IF_HYPERION / Var: ONLINE_RUN | JE's Complete | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
129 | 4 | 4 | 4 | 4 | 4 | Trial Balance Comp Codes Data Load |  |  | N |  | 4 |  | 5 |  | OB52 / PPV TEMP |  | COE- Financial | n/a | Rayees Moizuddin
130 | 4 | 4 | 4 | 4 | 4 | Calculate Balance Sheet Readjustment |  |  | N |  | 4 | 1 | 5 |  | F.5D | Close A/R | COE- Controlling | n/a | n/a | n/a
131 | 4 | 4 | 4 | 4 | 4 | Transfer Payables-Receivables to PCA |  |  | N |  | 4 | 1 | 5 |  | 1KEK | Calculate Balance Sheet Readjustment | COE- Controlling | n/a | n/a | n/a
132 |  | 4 |  |  |  | Reconcile VAT reports to G/L Accounts |  |  |  |  | 4 |  | 5 |  | Outside SAP | Close A/R | Raj Patel | n/a | Sean Connor | n/a
133 |  | 4 |  |  |  | Process VAT clearing |  |  |  |  | 4 | 4 | 5 |  | Outside SAP | Close A/R | Raj Patel | n/a | Sean Connor | n/a
134 | 4 | 4 | 4 | 4 | 4 | Close A/R |  |  | N |  | 4 | 1 | 5 |  | OB52 | Cash Processing Complete | COE- Financial | n/a | Sean Connor | n/a
135 | 4 | 4 | 4 | 4 | 4 | EC-CS valuation |  |  | N |  | 4 | 2 | 6 |  | CXCD | JE's Complete | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
136 | 4 | 4 | 4 | 4 | 4 | EC-CS rollup |  |  | N |  | 4 | 2 | 6 |  | CXCD | JE's Complete | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
137 | 4 | 4 | 4 | 4 | 4 | Send Data to Corporate Hyperion | 362 |  | N |  | 4 | 2 | 6 |  | ZGL_IF_HYPERION / Var: ONLINE_RUN | JE's Complete | COE- EC Consolidations | Karen Choyce | Rayees Moizuddin
ALL FI POSTINGS MUST BE COMPLETE BY 8 AM CST, WORKDAY 7
138 | 4 | 4 | 4 | 4 | 4 | Close ALL FI postings, end users |  |  |  |  | 4 |  | 7 |  | OB52 | Close Postings | COE- Financial | n/a | n/a | n/a
139 | 4 | 4 | 4 |  |  | Open Item Currency Revaluation - TC to LC (all co's except JVA) |  |  |  |  | 4 |  | 7 |  | F.05 / Var TC TO LC NO JV | Close Postings | COE- Financial | n/a | n/a | n/a | Used for all new companies for 1/1/2000 (Including Brazil) Use Evaluation Method "ENRN"
140 |  |  | 4 |  |  | Open Item Currency Revaluation - TC to LC3 (Non Brazil) (except JVA) |  |  |  |  | 4 |  | 7 |  | F.05 / Var TC LC3 NBR NJV | Close Postings | COE- Financial | n/a | n/a | n/a | Used for companies with LC3 configured (Hard Currency - Non Brazil) Use Evaluation method "ENRN"
141 |  |  | 4 |  |  | Open Item Currency Revaluation - TC to LC3 (Brazil) |  |  |  |  | 4 |  | 7 |  | F.05 / Var TC TO LC3 BR | Close Postings | COE- Financial | n/a | n/a | n/a | Used for companies with LC3 configured (Hard Currency - Non Brazil) Use Evaluation method "ENBR"
142 | 4 | 4 | 4 |  |  | Bal Sheet Currency Revaluation - TC to LC |  |  |  |  | 4 |  | 7 |  | F.06 / Var TC TO LC NO JV | Close Postings | COE- Financial | n/a | n/a | n/a | Used for all new companies for 1/1/2000 (Including Brazil) Use Evaluation Method "ENRN"
143 |  |  | 4 |  |  | Balance Sheet Currency Revaluation - TC to LC3 (Non Brazil) |  |  |  |  | 4 |  | 7 |  | F.06 / Var TC LC3 NBR NJV | Close Postings | COE- Financial | n/a | n/a | n/a | Used for companies with LC3 configured (Hard Currency - Non Brazil) Use Evaluation method "ENRN"
144 |  |  | 4 |  |  | Balance Sheet Currency Revaluation - TC to LC3 (Brazil) |  |  |  |  | 4 |  | 7 |  | F.06 / Var TC TO LC3 BR | Close Postings | COE- Financial | n/a | n/a | n/a | Used for companies with LC3 configured (Hard Currency - Non Brazil) Use Evaluation method "ENBR" Exch rate type "R"
145 |  |  | 4 |  |  | JVA Open Item Currency Revaluation - TC to LC |  |  |  |  | 4 |  | 7 |  | GJ91 / Var XXXX JVA | Close Postings | Joint Venture | n/a | n/a | n/a | Use for all "Fully Configured JV companies and "Partially Configured JV Companies - Use Evaluation method "ENRN". Executed individually for EACH JVA (full & partial) company
146 |  |  | 4 |  |  | JVA Non-Open Item Currency Revaluation - TC to LC |  |  |  |  | 4 |  | 7 |  | GJNO / Var XXXX JVA | Close Postings | Joint Venture | n/a | n/a | n/a | Use for all "Fully Configured JV companies and "Partially Configured JV Companies - Use Evaluation method "ENRN". Executed individually for EACH JVA (full & partial) company
147 |  | 4 |  |  |  | PCA Revaluation, Ledger 8a |  |  | N |  | 4 | 3 | 7 |  | GWUL / Var XXXX Reval | All postings done & all transfers performed | COE- Controlling | n/a | n/a | n/a | XXXX in variant for companies :138,809,28d,872,167,65f,1x4,20x,30s
148 |  | 4 | 4 |  | 4 | Currency Translation Special Ledger Z2 |  |  |  |  | 4 |  | 7 |  | GWUL / Var ? | Close Postings | COE- Financial | n/a | n/a | n/a | Run Company by Company.
149 | 4 | 4 | 4 | 4 | 4 | Close all FI Accounts |  |  |  |  | 4 |  | 7 |  | OB52 | PCA Revaluation | COE- Financial | n/a | n/a | n/a
150 | 4 | 4 | 4 | 4 | 4 | EC-CS Valuation |  |  |  |  | 4 |  | 7 |  | CXCD | FI Closed | COE- EC Consolidations | Karen Choyce
151 | 4 | 4 | 4 | 4 | 4 | EC-CS Rollup |  |  | N |  | 4 | 3 | 7 |  | CXCD | FI Closed | COE- EC Consolidations | Karen Choyce
152 | 4 | 4 | 4 | 4 | 4 | Send data to Corporate Hyperion | 362 |  | Y |  | 4 | 5 | 7 |  | ZGL_IF_HYPERION / Var: ONLINE_RUN | ECCS Process Done | COE- EC Consolidations | n/a | n/a | n/a
153 | 4 | 4 | 4 | 4 | 4 | SPL to TIS Interface | 436 |  | N |  | 4 | 5 | 7 |  | ZAMGAINLOSS/ZAMTB/ZFITB | Processing Complete | COE- Financial | n/a | n/a | n/a | Check File "A" for comma delimiters pushing amounts out. ZFITB-ABC; ZAMTB-DEFGI, ZAMGAINLOSS-H
154 | 4 | 4 | 4 | 4 | 4 | Assets to TIS Interface | 439 |  |  |  | 4 |  | 7 |  | ZECCS_IF_439_SAP_TO_TIS | TIS Process | COE- Financial | n/a | n/a | n/a | Variant - 1A_00439_001
155 | 4 | 4 | 4 | 4 | 4 | ECCS to TIS Interface | 444 |  |  |  | 4 |  | 7 |  | ZECCS_IF_444_SAP_TO_TIS | Send data to ECCS | COE- EC Consolidations | n/a | n/a | n/a | Variant - 1A_00444_001, 1A_00444_002, 1A_00444_003
156 | 4 | 4 | 4 | 4 | 4 | TIS Process |  |  | N |  | 4 | 5 | 8 |  | Outside SAP | Receive SAP File | Tax Department | n/a | Rayees Moizuddin | n/a
157 | 4 | 4 | 4 | 4 | 4 | Open FI tax accounts |  |  |  |  | 4 |  | 8 |  | OB52 | ReceiveTIS files | COE- Financial | n/a | n/a | n/a
158 | 4 | 4 | 4 | 4 | 4 | Post Tax Entry from TIS | 442 |  | N |  | 4 | 5 | 8 |  | ZFU_COMMON _FB01 Var:IA_00442_XXX | ReceiveTIS files | COE- Financial | n/a | Rayees Moizuddin
159 | 4 | 4 | 4 | 4 | 4 | Close FI tax accounts |  |  | N |  | 4 | 2 | 8 |  | OB52 | TIS Processing Done | COE- Financial | n/a | n/a | n/a
160 |  |  |  |  | 4 | Open FERC Accounts |  |  | N |  | 4 | 2 | 8 |  | OB52 | TIS Processing Done | COE- Financial | n/a | n/a | n/a
161 |  |  |  |  | 4 | Reverese Direct post before taxes. |  |  |  |  | 4 | 2 | 8 |  | FERO | Accounts Open | COE- Financial
162 |  |  |  |  | 4 | Post Direct post after taxes. |  |  |  |  | 4 | 2 | 8 |  | FERO | Reversal Complete | COE- Financial
163 |  |  |  |  | 4 | Close FERC accounts |  |  | N |  | 4 | 2 | 8 |  | OB52 | TIS Processing Done | COE- Financial | n/a | n/a | n/a
164 |  |  |  |  | 4 | Validate FERC to Natural Accounts. |  |  |  |  | 4 | 2 | 8 |  |  | FERC Posted | COE- Financial |  |  |  | If not correct analyze and contact representative and fix error.
165 |  |  |  |  | 4 | FERC Drill Down |  |  |  |  | 4 | 2 | 8 |  | FERO | Validation Complete | COE- Financial
166 |  | 4 | 4 |  | 4 | Currency Translation Special Ledger Z2 |  |  |  |  | 4 |  | 8 |  | GWUL / Var ? | Close Postings | Special Ledger | n/a | n/a | n/a | Run Company by Company.
167 | 4 | 4 | 4 | 4 | 4 | ECCS Load JE's from TIS | 445 |  |  |  | 4 |  | 8 |  | ZECCS_445_LOAD_JOURNAL_ENTRIES | ReceiveTIS files | COE- EC Consolidations | n/a | n/a | n/a | Variant - 1A_00445_001
168 | 4 | 4 | 4 | 4 | 4 | EC-CS Valuation |  |  |  |  | 4 |  | 8 |  | CXCD | FI Closed | COE- EC Consolidations | Karen Choyce | Geraint
169 | 4 | 4 | 4 | 4 | 4 | EC-CS Rollup |  |  | N |  | 4 | 3 | 8 |  | CXCD | TIS Files posted. | COE- EC Consolidations | n/a | Rayees Moizuddin |  | Rollup Z-SL2CS
170 | 4 | 4 | 4 | 4 | 4 | Send data to Corporate Hyperion | 362 |  | Y |  | 4 | 5 | 8 |  | ZGL_IF_HYPERION | 7th wkdy ECCS done | COE- EC Consolidations | n/a | n/a | n/a
171 | 4 | 4 | 4 | 4 | 4 | Execute Accrual/Deferral Documents & Reversals |  |  | N |  | 4 | 2 | 9 |  | FBS1 | JE's Complete | COE- Financial | Karen Choyce | Rayees Moizuddin
172 |  | 4 | 4 |  |  | Direct Cash Flow Extract/Load | 450 |  |  |  | 4 |  | 10 |  | ZFI_IF_DIRECT_CASHFLOW_ EXTRACT | ECCS Processing Complete | London COE- Cont | n/a | Rayees Moizuddin
173 |  | 4 | 4 |  |  | Prepare VAT returns | [5 empty] | 12 | 15 |  | Outside SAP |  | Rayees Moizuddin | n/a | Sean Connor
174 |  | 4 | 4 |  |  | Send VAT returns to tax for processing | [5 empty] | 12 | 15 |  | Outside SAP |  | Mohammed Khan | n/a | Sean Connor
Note on U6: ESA: Allen Ueckert
Note on U12: ESA:Igor Miotti
Note on U16: ESA: Dilma
Note on U19: OEC : Jim Davoli
Note on U49: OEC : Jim Davoli
Note on U74: OEC : Jim Davoli
Note on U75: OEC : Jim Davoli
Note on U76: OEC : Jim Davoli
Note on U117: OEC : Jim Davoli
Note on U121: OEC : Jim Davoli
Note on U122: OEC : Jim Davoli
Note on U136: OEC : Jim Davoli
Note on U137: OEC : Jim Davoli
Note on U195: OEC : Jim Davoli

## Contacts for Business Units
Bus. Unit | Area | Contact | Phone Number | Pager Number | Mobile | Home
CORP | GL | Elaine Schield | 713-853-5476
CORP | ECCS/AR/GL | Karen Choyce | 713-853-6420
CORP | CO | Dawn Derr | 713-853-7775
CORP | AM | Regina Hawley | 713-853-3535
CORP | Intercompany | Linda Armas | 713-646-7012
Europe-Lon | COE: CO | James Britton | 44-171 9707110 | 44-766 6537729 | 44-777 1947997 | 44-777 1947997
Europe-Lon |  | Justin East | 44-171 9707145 | 44-766 6537707 | 44-786 7906393 | 44-786 7906393
Europe-Lon | COE: GL | Sean Connor | 44-171 3166512 | 44-766 6537739 | 44-7803 685488 | 44-7803 685488
Europe-Lon | ECCS | Eileen Flanagan | 44-171 97035342 | 44-766-6535342
Europe-Lon |  | Sanjeev Talwar | 44-171 9707761
Europe-Lon | Interco | Rayees Moizuddin | 44-171 3166697 | 44-766 6529136 | 44-788 1501356 | 44-788 1501356
Europe-Lon | COE: FI/CO | Craig Brown | 44-171 9767665 | 44-766 6537725
Europe-Lon |  | Caroline Lothian | 44-171 3166687 | 44-766 6537725
Europe-Lon | AM/PS | Nuala Bennetts | 44-171 3166567
Europe-Oslo |  | Berit Lokken
NEPCO | All SAP | Patricia Dunn | 425-415-3026 | patricia@nepco.com
NEPCO | GL,PS,CO,OH | Kim Coates | 425-415-3096 | kimc@nepco.com
NEPCO | AR, AM | Ron Perry | 425-415-3133 | ronp@nepco.com
NEPCO | AM/PS | Connie Marr | 425-415-2863 | conniem@nepco.com
NEPCO | Project Ctls | Greg Penoyer | 425-415-3165 | gregp@nepco.com
NEPCO | PS | Pat Sweeney | 425-415-3077 | patricks@nepco.com
NEPCO | AP / AR | Rowena Baterbonia | 425-415-3038 | rowenab+E49@nepco.com
NEPCO | MM |  | 425-415-3126 | gregt@nepco.com
NEPCO | MM,AP |  | 425-415-3083 | dougl@nepco.com
NEPCO | HR |  | 425-415-3164 | mikei@nepco.com
NEPCO | HR |  | 425-415-3140 | keng@nepco.com
NEPCO | HR |  | 425-415-3178 | robinj@nepco.com
ESA | Costing Sheet/ECCS | Allen Ueckert | 713-646-7183
ESA-BZ | PS/AM | Igor Miotto | 55 115 5031250 |  | 55 11 9233 7448
ESA-BZ | AP | Claudia Brun
ESA-BZ | AP | Dilma Lopes | 55 11 5503 1248 |  | 55 11 9233 7489
ESA | Trial Bal Co's | Allen Ueckert | 713-646-7183
ESA-ARG | PS | Luis Juarros | 54-11-4891-3626
ESA-ARG |  | Marisa Pardellas | 54-11-4891-3622
ESA-BZ | JE's | Odair Ribeiro | 55 11 5503 1235 |  | 55 11 9233 7477
ESA-BZ |  | Harold Inman
ESA-BZ |  | Julie Ramos
ESA-BZ |  | Ariel Bruch
ESA-BZ |  | Kent Castleman
ESAM | ECCS | Darryl Free | 713-646-7599
EI | Costing Sheet | Rainier Cockrell | 713-646-7124
EI |  | Aaron Mackey | 713-646-7239
EI | FI/CO | Cindy Kater | 713-646-7481
EI HQ | Site Mgr | Paul Finken | 713-853-3529
EI HQ | FI/CO/ECCS | Traci Rainbow | 713-646-6459
EI HQ | PS | Shilpa Kadakia | 713-853-6374
EECC | Site Mgr/GL/ECCS | Wanda LaBaume | 713-345-5622
EECC | G/L | Tushar Kadakia | 713-345-8020
EECC | PS | Mark Levine | 713-853-4219
EECC | ECCS | Blake Walker | 713-646-6169
EGEP | FI/CO/ECCS | Pamela Rush | 713-853-5104
EGEP | FI/CO/ECCS | Howard Selzer | 713-853-3484
EGEP | FI/CO/ECCS | Jim Davoli | 713-853-1640 | 1-877-499-0259
CALME | Costing Sheet/ECCS | Thao Nguyen | 713-646-7501
CALME | ECCS | Agatha Tran | 713-646-7278
CALME | ECCS | Mei-Ling Kaster | 713-646-6419
APACHI | ECCS | Carol Howes | 713-646-7133
APACHI | FI/CO/ECCS | Paula Parrish | 713-646-7505
APACHI | ECCS | Patrick Dominguez | 713-345-5728
OEC | Costing Sheet/ECCS | Chaundra Perry | 713-345-5296 | 877-242-4268
FI/CO/PS
| ECCS | Wayne Tencer | 713-345-5217
INDIA | ECCS | Robert D Smith | 713-646-7883
EBS | ECCS | Jin Lucy | 713-345-9339
ENGF | ECCS | Bill Doran | 713-345-7662
ENGF | ECCS | Tricia Shannon | 713-853-6961
Singapore |  | Tiong Hock Lim - Director
Singapore |  | Meryl Tew - Manager
EI | JVA | Rick Ayala
EI | PS | Raj Una | 713-853-3458
Labor | FI/CO Labor | Dave Reeves | 713-853-9033
ESA | FI/CO Costing | Braden Sewell
ESA | JVA | Tim Williams
ESA |  | Kim Lesley | 55 11 5503 1313 | 55 11 9198 9707
ESA |  | Gustavo Bertocchi
EECC | PS | Kevin Gibson | 713-853-3287
EECC | AP | Angela Backstrom | 713-853-9500

## Other Contacts
GROUP | Area | Contact | Phone Number | Pager Number | Mobile
COE | COE | Corp Helpline | 713-345-4727
COE | ? | Brandee Sanborn | 713-853-4512
COE | ? | Duane Fritz | 713-853-0698
COE | ECCS | Eric Sherman | 713-853-7594
COE | MM | Vince Mack | 713-853-5282
COE | AM/IM/PS | Marian Bryant | 713-853-7714
COE | Technical | Diem Pham | 713-853-7514
TAX | TIS/EDS | Kathy Fink | 713-853-7665
TAX | TIS/EDS | Deborah Heath | 713-853-5033
TAX | Corp Tax | Kerrie Smith | 713-853-1907
TAX | TIS/EDS | Kelly McCain | 713-853-4719
CORP CONSOL | Hyperion | Jan Johnson | 713-853-3260
CORP CONSOL | Hyperion | Cynthia Safford | 713-853-1651
CORP CONSOL | Hyperion | Johnson Leo | 713-853-7165
CORP CONSOL | Hyperion | Gary Peng | 713-853-6841
CORP CONSOL | Hyperion | Mark Ferguson | 713-853-3186
CORP CONSOL | Hyperion | Gilda Bartz | 713-853-5102
MSA |  | Pam Brejcha
MSA |  | Debbie Yates

## Bus Unit FI Co Codes
CORP | EUROPE | NEPCO | EECC | CALME | APACHI | SO CONE | INDIA | EGEP | OEC