## Sheet2 (hidden)
TVA Peaking Plant
Issues/Savings
Issue
EECC increased current estimate
Fuel cost during start up not included
Tax Handling Fee to LLC for arms length transaction .25% not included in plan
Savings Recognized
| New Albany | Caledonia | Brownsville | Total
Decrease Environmental permitting | -310000 | -300000 | -233000 | -843000
Decrease Legal expense | -550000 | -550000 | -350000 | -1450000
Decrease Development | -200000 | -200000 | -200000 | -600000
Total Savings | -1060000 | -1050000 | -783000 | -2893000

## NA Mquip (hidden)
New Albany
Major Equipment Detail
Refurbishment with DLN Units 1-6
(includes commission) |  | 26785396
| Spare Parts | 5214604
32000000
Dow Unit
| Purchase & spares | 1347000
| Dissassembly | 500000
| Commission 10% | 134700
1981700
4 Kepco Units (original)
| Purchase | 27502700
| Commission IBC(10%) | 2700000
| Commission Natole | 900000
| Less Steam Turbine | -700000 | Allocate to 2000
| Disassemble & move to Kunsan Port | 1307660
| Less Steam Turbine | -200500 | Allocate to 2000
| Freight Reimbursement to IBC | 1274025
| Less Steam Turbine | -100000 | Allocate to 2000
| Commission (7%) | 89181.75
32773066.75
1 Kepco Unit (new set)
| 1 of 4 Purchase price | 6875000
| Disassembly & shipping | 500000
| Commission | 0
7375000
Unidentified |  | 0 | Spare parts to be reconciled per Miller
Total IBC items |  | 74129766.75
Transformers etc |  | 10870000
Grand Total Major Equipment |  | 84999766.75

## EECC (hidden)
EECC RECONCILIATION
| Control | Current
| Budget | Estimate |  | Net Increase
Brownsville | 395276 | 587051 |  | 191775
0
Caledonia | 395276 | 620100 |  | 224824
New Albany | 395276 | 641831 |  | 246555
Fulton | 395276 | 225000 | a | -170276
Total | 1581104 | 2073982 |  | 492878
a) Sunk Cost

## To Update (hidden)
To Update:
1 | Save file as new name
2 | Go to Summary tab
in cell "Q4" drop in date of Project Tracking report used as backup
3 | Go to LLC tab
unhide all columns
update actuals for applicable month
check totals
tie budget and current estimate to report from week before; explain any changes on summary tab
make sure that sum of Actuals to Date Total Project + Estimate to Complete + variance = Current Estimate amount
4 | Go to Summary tab
update variance explanations to current estimate

## Summary
ENRON CAPITAL & TRADE RESOURCES
Energy Services |  |  |  |  | Report Date: |  |  | 2025-09-26 22:22
Project 2000
COST SUMMARY ($ thousands) |  |  |  |  | Expenditures to date: |  |  | As of 12/31/1999
Revision # 41
Actuals
Construction Costs |  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance | %
Excluding Financing Fee | MW | as of 7/22/99 | As of 12/31/1999 | As of 12/31/1999 |  | As of 12/31/1999 | from CE | Complete
Wilton Center, IL | 608 | 242553.1648 | 162878.046 | 92784.3676 |  | 255662.4136 | -13109.2488 | 63.71%
Gleason, TN | 509 | 173405.3296 | 106623.6321 | 67665.3599 |  | 174288.992 | -883.6625 | 61.18%
Wheatland, IN | 470 | 161382.9531 | 96465.2966 | 64680.507 |  | 161145.8035 | 237.1496 | 59.86%
TOTAL PROJECTS | 1587 | 577341.4475 | 365966.9746 | 225130.2345 |  | 591097.2092 | -13755.7617 | 61.91%
Target $$/MW |  | 363.7942 |  |  |  | 372.462
Actuals
Financing Costs |  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance
Project |  | as of 7/22/99 | As of 12/31/1999 | As of 12/31/1999 |  | As of 12/31/1999 | from CE
Wilton Center, IL |  | 1500 | 0 | 1500 |  | 1500 | 0
Calvert City, KY |  | 1500 | 0 | 1500 |  | 1500 | 0
Wheatland, IN |  | 1500 | 0 | 1500 |  | 1500 | 0
TOTAL PROJECTS |  | 4500 | 0 | 4500 |  | 4500 | 0
Backup Sites |  |  | Actuals
|  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete
Project |  | 1999-09-30 | As of 12/31/1999 | As of 12/31/1999 |  | As of 12/31/1999
Plano, IL |  |  | 299.5243 |  |  | 299.5243
Calvert City |  | 1513 | 1401.0854 | 111.9146 |  | 1513
Petersburg, IN |  |  | 15.1 |  |  | 15.1
TOTAL PROGRAM |  | 1513 | 1715.7097 | 111.9146 |  | 1827.6243
Changes to Current Estimate Explanations
All Plants | Weekly | Recalculated Interest During Construction ( 6.50%) and Commitment Fee (35 BPS)
All Plants | 1999-07-22 | Change in scope with addition of Union Labor
Current Estimate vs Actual Variance Explanations (000s)
Wilton Center, IL | -207.06 | EECC Development Costs incurred prior to 6/1/99 that is not included in the budget
| -11394.513 | Increase in Nepco Construction Costs (includes unaprroved scope changes)-Review Scope Change Tab for further details
| -1832 | Increase Turbines - Scope Change
| -37.448 | Increase Transformers -Scope Change
| -3000 | Additional Gas Interconnect Costs
| -30.8181 | Misc, $25 land over budget
| -239.6299 | Increase Development , $116 related to GLC consulting costs
| -191.0129 | Cost related to Enron Generation Company, Standard & poors, RW Beck and AES Corp
| -252.2085 | Everest Legal Costs
| 4408.072 | Use of Contingency ( Contingency is now zero)
| -116.2485 | Insurance payment more than Budget
| -216.3817 | Water Interconnect, budgeted at zero
| -13109.2486 | Over Original Budget -including unapproved Nepco scope changes
Gleason, TN | -32.2033 | EECC Development Costs incurred prior to 6/1/99 that is not included in the budget
| -2829.6996 | Increase in Nepco Construction Costs (includes unaprroved scope changes)-Review Scope Change Tab for further details
| -1743.101 | Increase Turbines - Scope Change
| -8 | Increase in Transformer Costs
| -1500 | Increase in TVA interconnect Costs - Redesign burden
| -191.0129 | Cost related to Enron Generation Company, Standard & poors, RW Beck and AES Corp
| -252.2085 | Everest Legal
| 5423.498 | Use of Contingency ( Contingency is now zero)
| 250 | Other -1/2 of redsign costs to change project to Gleason
| -882.7272 | Under Original Budget -including unapproved Nepco scope changes
| -1615.799 | Additional Scope Change not included in Nepco's Current Forecast - Review Scope Change Tab for further details
| -2498.5262 | Over Original Budget -including unapproved Nepco scope changes
Wheatland, IN | -159.2332 | EECC Development Costs incurred prior to 6/1/99 that is not included in the budget
| -1930.9686 | Increase in Nepco Construction Costs (includes unaprroved scope changes)-Review Scope Change Tab for further details
| -297.801 | Increase Turbines - Scope Change
| -78.48 | Increase Transformers -Scope Change
| -347.9439 | Increase in Land Acquisition costs
| -195.0408 | Cost related to Enron Generation Company, Standard & Poors, RW Beck and AES Corp
| -252.2085 | Everest Legal
| 174.6734 | Increase Interest During Construction
| 3324.1521 | Use of Contingency ( Contingency is now zero)
| 237.1497 | Under Original Budget
| -3405.648 | Additional Scope Change not included in Nepco's Current Forecast - Review Scope Change Tab for further details
| -3168.4983 | Over Original Budget -including unapproved Nepco scope changes
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/2000_Weekly_Report___011100.xls'#$Summary

## Wilton
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [62 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/2000_Weekly_Report___011100.xls'#$Wilton
Wilton Center, IL | [7 empty] | 510 |  | MW | [48 empty] | 2025-09-26 22:22 |  |  |  | Revision # 41
| 608 | [14 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated
[7 empty] | Expense / | ECT |  | Increase / |  | ECT |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL |  | (Increase)
|  | Vendor | Responsibility | Enron Contact | Certainty |  | Capital | Control Budget |  | (Savings) |  | Current Estimate |  | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 | 1999-06-30 | 1999-07-31 | 1999-08-31 |  | 1999-09-30 |  | 1999-10-31 |  | 1999-11-30 |  | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[8 empty] | #REF! |  |  |  | as of 7/22/99 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase -GE 7ea (8) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 140040940 |  | 6800000 |  |  |  | 32884800 | [5 empty] | 18310527 | 6800000 | 5225143.44 | 6152847 |  | 6924847 |  | 6924847 |  | 6924847 |  | 24688143.63 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 121636002.07 |  | 1832000 |  | 20236937.93 |  | 141872940 |  | -1832000
| Other |  |  |  |  | ECT | Capital | 93330000 |  | 0 |  | 192000 | [11 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 192000 |  | 192000 |  | 0
0
| Subtotal GE | [6 empty] | 93330000 |  | 0 |  | 140232940 |  | 6800000 |  | 0 |  | 32884800 |  | 0 |  | 0 |  | 18310527 | 6800000 | 5225143.44 | 6152847 |  | 6924847 |  | 6924847 |  | 6924847 |  | 24688143.63 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 121636002.07 |  | 1832000 |  | 20428937.93 |  | 142064940 |  | -1832000
| SPARE PARTS | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 5878600 |  | 0 |  | 1250000 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | -74270.4 | 7480 |  | 0 |  | 1774814.4 |  | 0 |  | 1774814.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4732838.4 |  | 37448 |  | 1183209.6 |  | 5916048 |  | -37448
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT | Capital | [51 empty] | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT | Capital | [51 empty] | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT | Capital | [51 empty] | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [46 empty] | 0 |  | 0 |  | 0
[6 empty] | ECT | [52 empty] | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[59 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [6 empty] | 0 |  | 0 |  | 5878600 |  | 0 |  | 1250000 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | -74270.4 | 7480 |  | 0 |  | 1774814.4 |  | 0 |  | 1774814.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4732838.4 |  | 37448 |  | 1183209.6 |  | 5916048 |  | -37448
| TOTAL MAJOR EQUIPMENT | [6 empty] | 93330000 |  | 0 |  | 146111540 |  | 6800000 |  | 1250000 |  | 32884800 |  | 0 |  | 0 |  | 18310527 | 6800000 | 5150873.04 | 6160327 |  | 6924847 |  | 8699661.4 |  | 6924847 |  | 26462958.03 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 126368840.47 |  | 1869448 |  | 21612147.53 |  | 147980988 |  | -1869448
NEPCO SITE CONSTRUCTION COSTS
[14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
General Provisions
| EQUIPMENT & SMALL TOOL |  |  |  |  | Nepco | Capital |  |  |  |  | 1538981 | [20 empty] | 11510 |  | 43198 | [19 empty] | 54708 |  | 622546 |  | 2106819 |  | 2161527 |  | -622546
| FIELD STAFF |  |  |  |  | Nepco | Capital |  |  |  |  | 1608142 | [20 empty] | 87721 |  | 87521 | [19 empty] | 175242 |  | 1750527 |  | 3183427 |  | 3358669 |  | -1750527
| TEMP FACILITIES & INDIRECT SUPPORT |  |  |  |  | Nepco | Capital |  |  |  |  | 1028779 | [20 empty] | 261 |  | 227470 | [19 empty] | 227731 |  | 740439 |  | 1541487 |  | 1769218 |  | -740439
| INDIRECT SUPPLIES |  |  |  |  | Nepco | Capital |  |  |  |  | 648235 | [20 empty] | 21574 |  | 36207 | [19 empty] | 57781 |  | 22349 |  | 612803 |  | 670584 |  | -22349
| PAYROLL BURDENS |  |  |  |  | Nepco | Capital |  |  |  |  | 8261165 | [20 empty] | 247412 |  | 20085 | [19 empty] | 267497 |  | -4462177 |  | 3531491 |  | 3798988 |  | 4462177
| HO PROJ MGMT/SUPPORT |  |  |  |  | Nepco | Capital |  |  |  |  | 109122 | [20 empty] | 37545 |  | 3444 | [19 empty] | 40989 |  | 0 |  | 68133 |  | 109122 |  | 0
| BUSINESS EXPENSES |  |  |  |  | Nepco | Capital |  |  |  |  | 745651 | [20 empty] | 128235 |  | 63844 | [19 empty] | 192079 |  | 153796 |  | 707368 |  | 899447 |  | -153796
| FIELD NON-PROD LABOR |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 256827 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 27859 |  | 7268 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 35127 |  | 411324 |  | 633024 |  | 668151 |  | -411324
| INDIRECT ENGR LABOR |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 3697897 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 107400 |  | 4264 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 111664 |  | -3509933 |  | 76300 |  | 187964 |  | 3509933
| DIRECT PROJECT ENGR |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 302496 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 192524 |  | 75508 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 268032 |  | 126023 |  | 160487 |  | 428519 |  | -126023
| FREIGHT & TAXES |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 274200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 47 |  | 67880 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 67927 |  | 204598 |  | 410871 |  | 478798 |  | -204598
| VENDOR REPS |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 65000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 65000 |  | 65000 |  | 0
| CONTINGENCY |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 104121 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 78186 |  | 182307 |  | 182307 |  | -78186
| RESERVES | [5 empty] | Capital | 0 |  | 0 |  | 164248 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -164248 |  | 0 |  | 0 |  | 164248
[7 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[7 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL General Provisions | [5 empty] | Capital | 0 |  | 0 |  | 18804864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862088 | 0 | 636689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1498777 | 0 | -4026570 | 0 | 13279517 | 0 | 14778294 | 0 | 4026570
BOP Procurement
| PIPE, VALVES, SPEC, & HANGERS |  |  |  |  | Nepco | [5 empty] | 410304 | [22 empty] | 10115 | [19 empty] | 10115 |  | 25887 |  | 426076 |  | 436191 |  | -25887
| CONDUIT & WIRE |  |  |  |  | Nepco | [5 empty] | 556642 | [22 empty] | 32997 | [19 empty] | 32997 |  | 127284 |  | 650929 |  | 683926 |  | -127284
| BUS DUCT |  |  |  |  | Nepco | [5 empty] | 757350 | [22 empty] | 0 | [19 empty] | 0 |  | 324999 |  | 1082349 |  | 1082349 |  | -324999
| DRY XFORMERS & PANELS |  |  |  |  | Nepco | [5 empty] | 24750 | [22 empty] | 0 | [19 empty] | 0 |  | 175745 |  | 200495 |  | 200495 |  | -175745
| OIL FILLED XFORMERS |  |  |  |  | Nepco | [5 empty] | 222260 | [22 empty] | 0 | [19 empty] | 0 |  | 24284 |  | 246544 |  | 246544 |  | -24284
| MOTOR CONTROL CENTER |  |  |  |  | Nepco | [5 empty] | 138771 | [22 empty] | 0 | [19 empty] | 0 |  | 9600 |  | 148371 |  | 148371 |  | -9600
| SWITCHGEAR |  |  |  |  | Nepco | [5 empty] | 2785772 | [22 empty] | 239169 | [19 empty] | 239169 |  | -210929 |  | 2335674 |  | 2574843 |  | 210929
| CNTL PANELS & TRMNTN BOX |  |  |  |  | Nepco | [5 empty] | 94088 | [42 empty] | 0 |  | 14198 |  | 108286 |  | 108286 |  | -14198
| ELECTRICAL DEVICES |  |  |  |  | Nepco | [5 empty] | 4268 | [22 empty] | 447 | [19 empty] | 447 |  |  |  | 3821 |  | 4268 |  | 0
| LIGHT POLE & LIGHT FIXTURES |  |  |  |  | Nepco | [5 empty] | 171146 | [42 empty] | 0 |  | 5520 |  | 176666 |  | 176666 |  | -5520
| ELEC HEAT TRACE & TEST |  |  |  |  | Nepco | [5 empty] | 22947 | [42 empty] | 0 |  |  |  | 22947 |  | 22947 |  | 0
| SPECIAL SYSTEMS |  |  |  |  | Nepco | [5 empty] | 115116 | [42 empty] | 0 |  | 10000 |  | 125116 |  | 125116 |  | -10000
| FIELD MOUNTED INSTRUMENTS |  |  |  |  | Nepco | [5 empty] | 97500 | [42 empty] | 0 |  | 5148 |  | 102648 |  | 102648 |  | -5148
| STACK MONITORING |  |  |  |  | Nepco | [5 empty] | 393568 | [42 empty] | 0 |  | 10412 |  | 403980 |  | 403980 |  | -10412
| CNTL VALVES & MISC EQUIPMENT |  |  |  |  | Nepco | [5 empty] | 59392 | [42 empty] | 0 |  | 12986 |  | 72378 |  | 72378 |  | -12986
| TUBING, TRAV & STANDS |  |  |  |  | Nepco | [5 empty] | 21728 | [42 empty] | 0 |  | 2052 |  | 23780 |  | 23780 |  | -2052
| DCS |  |  |  |  | Nepco | [5 empty] | 207975 | [20 empty] | 3301 | [21 empty] | 3301 |  | 34630 |  | 239304 |  | 242605 |  | -34630
| PUMPS |  |  |  |  | Nepco | [5 empty] | 96500 | [42 empty] | 0 |  | 427000 |  | 523500 |  | 523500 |  | -427000
| CONDENSER & AUX EQUIPMENT |  |  |  |  | Nepco | [5 empty] | 18000 | [42 empty] | 0 |  | 57253 |  | 75253 |  | 75253 |  | -57253
| FUEL GAS FILTER |  |  |  |  | Nepco | [5 empty] | 105600 | [22 empty] | 63890 | [19 empty] | 63890 |  |  |  | 41710 |  | 105600 |  | 0
| PRESSURE REDUCE STAT |  |  |  |  | Nepco | [5 empty] | 373700 | [42 empty] | 0 |  |  |  | 373700 |  | 373700 |  | 0
| MINOR SKID MOUNTED SYSTEMS |  |  |  |  | Nepco | [5 empty] | 0 | [42 empty] | 0 |  | 300000 |  | 300000 |  | 300000 |  | -300000
| TANKS NON-PRESSURIZE |  |  |  |  | Nepco | [5 empty] | 37000 | [42 empty] | 0 |  | 15000 |  | 52000 |  | 52000 |  | -15000
| TOTAL BOP Procurement | [5 empty] | Capital | 0 |  | 0 |  | 6714377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3301 | 0 | 346618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349919 | 0 | 1371069 | 0 | 7735527 | 0 | 8085446 | 0 | -1371069
Construction
| SITE PREPARATION/IMPROVEMENTS - S | [10 empty] | 2332995 | [22 empty] | 949522 | [19 empty] | 949522 |  | 875969 |  | 2259442 |  | 3208964 |  | -875969
| UNDERGROUND ELECTRICAL - L | [10 empty] | 804321 | [22 empty] | 725 | [19 empty] | 725 |  | 1084069 |  | 1887665 |  | 1888390 |  | -1084069
| UNDERGROUND ELECTRICAL - M | [10 empty] | 497417 | [22 empty] | 133215 | [19 empty] | 133215 |  | 80511 |  | 444713 |  | 577928 |  | -80511
| UNDERGROUND ELECTRICAL - S | [10 empty] | 30000 | [22 empty] | 0 | [19 empty] | 0 |  |  |  | 30000 |  | 30000 |  | 0
| UNDERGROUND PIPING - L | [10 empty] | 693467 | [22 empty] | 6350 | [19 empty] | 6350 |  | 1053423 |  | 1740540 |  | 1746890 |  | -1053423
| UNDERGROUND PIPING - M | [10 empty] | 453000 | [22 empty] | 103285 | [19 empty] | 103285 |  | 93098 |  | 442813 |  | 546098 |  | -93098
| UNDERGROUND PIPING - S | [10 empty] | 25000 | [22 empty] | 0 | [19 empty] | 0 |  |  |  | 25000 |  | 25000 |  | 0
| CONCRETE - L | [10 empty] | 2264637 | [22 empty] | 0 | [19 empty] | 0 |  | -2264637 |  | 0 |  | 0 |  | 2264637
| CONCRETE - M | [10 empty] | 1150462 | [22 empty] | 508620 | [19 empty] | 508620 |  | 105899 |  | 747741 |  | 1256361 |  | -105899
| CONCRETE - S | [33 empty] | 644530 | [19 empty] | 644530 |  | 3160764 |  | 2516234 |  | 3160764 |  | -3160764
| SPECIAL CONCRETE - L | [10 empty] | 189905 | [22 empty] | 0 | [19 empty] | 0 |  | 247305 |  | 437210 |  | 437210 |  | -247305
| SPECIAL CONCRETE - M | [10 empty] | 77621 | [22 empty] | 4214 | [19 empty] | 4214 |  | 6960 |  | 80367 |  | 84581 |  | -6960
| STRUCTURAL STEEL - L | [10 empty] | 144409 | [22 empty] | 0 | [19 empty] | 0 |  | 163822 |  | 308231 |  | 308231 |  | -163822
| STRUCTURAL STEEL - M | [10 empty] | 327314 | [22 empty] | 85468 | [19 empty] | 85468 |  | 7250 |  | 249096 |  | 334564 |  | -7250
| ARCHITECTURAL -S | [10 empty] | 330460 | [22 empty] | 0 | [19 empty] | 0 |  |  |  | 330460 |  | 330460 |  | 0
| BUILDINGS -S | [10 empty] | 808591 | [22 empty] | 0 | [19 empty] | 0 |  |  |  | 808591 |  | 808591 |  | 0
| A/G PIPING - L | [10 empty] | 848398 | [22 empty] | 0 | [19 empty] | 0 |  | 904682 |  | 1753080 |  | 1753080 |  | -904682
| A/G PIPING - S | [10 empty] | 10000 | [42 empty] | 0 |  | 5000 |  | 15000 |  | 15000 |  | -5000
| A/G ELECTRICAL - L | [10 empty] | 1655614 | [42 empty] | 0 |  | 2163113 |  | 3818727 |  | 3818727 |  | -2163113
| A/G ELECTRICAL - S | [10 empty] | 90000 | [42 empty] | 0 |  | 24000 |  | 114000 |  | 114000 |  | -24000
| INSTRUMENTATION - L | [10 empty] | 571702 | [42 empty] | 0 |  | 643062 |  | 1214764 |  | 1214764 |  | -643062
| INSULATION & PAINTING -S | [10 empty] | 931641 | [42 empty] | 0 |  | 7819 |  | 939460 |  | 939460 |  | -7819
| MECHANICAL EQUIPMENT - L | [10 empty] | 3098577 | [42 empty] | 0 |  | 3908375 |  | 7006952 |  | 7006952 |  | -3908375
| MECHANICAL EQUIPMENT - S | [10 empty] | 3134576 | [22 empty] | 134000 | [19 empty] | 134000 |  | 165000 |  | 3165576 |  | 3299576 |  | -165000
| PLANT STARTUP - L | [10 empty] | 627429 | [42 empty] | 0 |  | 315713 |  | 943142 |  | 943142 |  | -315713
| PLANT STARTUP - M | [10 empty] | 241000 | [42 empty] | 0 |  | -35000 |  | 206000 |  | 206000 |  | 35000
| PLANT STARTUP - S | [10 empty] | 0 | [42 empty] | 0 |  | 42450 |  | 42450 |  | 42450 |  | -42450
| UNION ADDER ESTIMATE ERROR | [10 empty] | -1225177 | [42 empty] | 0 |  | 1225177 |  | 0 |  | 0 |  | -1225177
[59 empty] | 0 |  | 0 |  | 0
| TOTAL Construction | [10 empty] | 20113359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2569929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2569929 | 0 | 13983824 | 0 | 31527254 | 0 | 34097183 | 0 | -13983824 | 0
Switchyard
| SWITCHYARD | [10 empty] | 5312100 | [22 empty] | 28388 | [19 empty] | 28388 |  | 24659 |  | 5308371 |  | 5336759 |  | -24659
| TOTAL SWITCHYARD | [10 empty] | 5312100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28388 | 0 | 24659 | 0 | 5308371 | 0 | 5336759 | 0 | -24659
[55 empty] | 28388 |  |  | 0 |  | 0 |  | 0
| Change Orders | [10 empty] | 0 | [22 empty] | 41000 | [19 empty] | 41000 | 0 | 0 | 0 | 0 | 0 | 41000 | 0 | -41000
| Backcharges | [10 empty] | 0 | [22 empty] | 531 | [19 empty] | 531 | 0 | 0 | 0 | 0 | 0 | 531 | 0 | -531
| Nepco % Cash (difference between prior | [10 empty] | 0 | [20 empty] | 8573073 |  | 7093919 | [19 empty] | 15666992 |  | 0 | 0 | -15666992 | 0 | 0 | 0 | 0
month actual and current month % of Cash Curves)
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [6 empty] | 0 |  | 0 |  | 50944700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9438462 | 0 | 10717074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20155536 | 0 | 11352982 | 0 | 42183677 | 0 | 62339213 | 0 | -11394513 | 0
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 935200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 77933.3333 | 77933.35 |  | 77933 |  | 77933.33 |  | 82933.33 |  | 77933.34 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 472599.6833 |  | 5000 |  | 467600.3167 |  | 940200 |  | -5000
| NEPCO |  |  |  |  | NEPCO | Capital | 0 |  | 0 |  | 2824800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 235400 | 235400 |  | 235399 |  | 235399 |  | 235399 |  | 235398 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1412395 |  | 0 |  | 1412405 |  | 2824800 |  | 0
| BASE FEE |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 3066700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3066700 |  | 3066700 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
| TOTAL OVERHEADS & FEES | [6 empty] | 0 |  | 0 |  | 6826700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 313333.3333 | 313333.35 |  | 313332 |  | 313332.33 |  | 318332.33 |  | 313331.34 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1884994.6833 |  | 5000 |  | 4946705.3167 |  | 6831700 |  | -5000
ADDERS OUTSIDE EECC SCOPE | [6 empty] | Capital
| Sound Mitigation |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 9479079 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 815280 | 2025875.7 | 0 |  | 0 |  | 1894103.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4735259.5 |  | 0 |  | 4743819.5 |  | 9479079 |  | 0
| Evaporative Coolers |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Roads & Ditches |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Drainage |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| On-Site Well/Water System |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
| TOTAL ADDERS | [6 empty] | 0 |  | 0 |  | 9479079 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 815280 | 2025875.7 | 0 |  | 0 |  | 1894103.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4735259.5 |  | 0 |  | 4743819.5 |  | 9479079 |  | 0
ECT PROJECT COSTS
85881594.91
MOBILIZATION OF O&M
| Mobilization Fee |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 908786 |  | 908786 |  | 0
| EI Hourly billing | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [6 empty] | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 908786 |  | 908786 |  | 0
RESALE HANDLING FEES (.25%) | [5 empty] | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
WATER INTERCONNECT | [5 empty] | ECT | Capital | 400000 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 216381.67 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 216381.67 |  | 0 |  | 0 |  | 216381.67 |  | -216381.67
SALES TAX ON EQUIPMENT | [5 empty] | ECT | Capital | 0 |  | 0 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 0
SPARE PARTS | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1253881 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1253881 |  | 1253881 |  | 0
LAND ACQUISITION
| Land Option |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 28500 |  | 0 |  | 0 |  | 0 |  | 20000 |  | 0 |  | 8500 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28500 |  | 0 |  | 0 |  | 28500 |  | 0
| Title Commitment |  |  |  |  | ECT | Capital |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ECT | Capital |  |  |  |  | 2251500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1446361 |  | 0 | 0 | 821965.14 | 0 |  | 0 |  | 1000 |  | 7992 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2277318.14 |  | 25818 |  | 0 |  | 2277318.14 |  | -25818.14
| Closing Costs |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [46 empty] | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [6 empty] | 0 |  | 0 |  | 2280000 |  | 0 |  | 0 |  | 0 |  | 20000 |  | 1446361 |  | 8500 | 0 | 821965.14 | 0 |  | 0 |  | 1000 |  | 7992 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2305818.14 |  | 25818 |  | 0 |  | 2305818.14 |  | -25818.14
ENVIRONMENTAL PERMITTING
| Air Permitting | [5 empty] | Expense | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Groundwater | [5 empty] | Expense | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Expense |  |  | 0 |  | 400000 |  | 0 |  | 0 |  | 0 |  | 8000 |  | 24712 |  | 71081 | 13261.65 | 39577.43 | 11821.22 |  | 11746.18 |  | 19877.66 |  | 29832.4 |  | 39859.51 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 269769.05 |  | 0 |  | 130230.95 |  | 400000 |  | 0
0
| Subtotal Environmental Permitting | [6 empty] | 0 |  | 0 |  | 400000 |  | 0 |  | 0 |  | 0 |  | 8000 |  | 24712 |  | 71081 | 13261.65 | 39577.43 | 11821.22 |  | 11746.18 |  | 19877.66 |  | 29832.4 |  | 39859.51 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 269769.05 |  | 0 |  | 130230.95 |  | 400000 |  | 0
POWER INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 50050 |  | 160615.6 |  | 8227.76 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 218893.36 |  | 0 |  | 781106.64 |  | 1000000 |  | 0
GAS INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  | 3500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3000000 |  | 6500000 |  | 6500000 |  | -3000000
Startup Fuel
| Power Sales | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost | [5 empty] | Capital | 0 |  | 0 |  | 1500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1500000 |  | 1500000 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [6 empty] | 0 |  | 0 |  | 1500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1500000 |  | 1500000 |  | 0
INSURANCE DURING CONSTR | [6 empty] | Capital | 0 |  | 0 |  | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 266248.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 266248.5 |  | 0 |  | 0 |  | 266248.5 |  | -116248.5
CAPITALIZED SALARIES | [6 empty] | Capital | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 29401.83 | 13770.85 | 7745.74 | 6275.69 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 57194.11 |  | 0 |  | 142805.89 |  | 200000 |  | 0
DEVELOPMENT EXPENSES
| Salaries | [5 empty] | Expense | 200000 |  | 0 |  | 35000 |  | 0 |  | 0 |  | 22604 |  | 0 |  | 7949 |  | 0 |  | 0 | 0 |  | 6591.41 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37144.41 |  | 2144 |  | 0 |  | 37144.41 |  | -2144.41
| Travel Expenses | [5 empty] | Expense | 0 |  | 50000 |  | 45000 |  | 0 |  | 1236 |  | 9770 |  | 5706 |  | 9652 |  | 3504 | 5185.43 | 3598.69 | 3892.71 |  | 6342.74 |  | 1599.42 |  | 3506.18 |  | 5695.65 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 59688.82 |  | 6683 |  | 0 |  | 59688.82 |  | -14688.82
| Consulting - GLC | [5 empty] | Expense | 0 |  | 24235 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 37759.78 |  | 42194.99 |  | 35999.89 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 115954.66 |  | 79955 |  | 0 |  | 115954.66 |  | -115954.66
| Other | [5 empty] | Expense | 400000 |  | -356935 |  | 134593 |  | 0 |  | 0 |  | 46735 |  | 21114 |  | 1899 |  | 8288 | 84262.75 | 10838.34 | 0 |  | 20657.14 |  | 8465.74 |  | 2127.81 |  | 4850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 209237.78 |  | 106842 |  | 32197.22 |  | 241435 |  | -106842
| Enron Generation Company Costs | [31 empty] | 83333.33 |  | 107679.56 | [19 empty] | 191012.89 |  | 0 |  | 0 |  | 191012.89 |  | -191012.89
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [23 empty] | 127279.45 | 49930.79 | 29848.78 | [27 empty] | 207059.02 |  | 207060 |  | 0.98 |  | 207060 |  | -207060
| TOTAL DEVELOPMENT EXPENSE | [6 empty] | 600000 |  | -282700 |  | 214593 | 0 | 0 | 0 | 1236 | 0 | 79109 | 0 | 26820 | 0 | 19500 | 0 | 11792 | 216727.63 | 64367.82 | 33741.49 |  | 33591.29 |  | 47824.94 | 0 | 131162.31 | 0 | 154225.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820097.58 | 0 | 402684 | 0 | 32198.2 | 0 | 852295.78 | 0 | -637702.78
LEGAL EXPENSES
| Vinson & Elkins | [5 empty] | Expense | 0 |  | 294489 |  | 206751 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 605 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 605 |  | 0 |  | 206146 |  | 206751 |  | 0
| Everst Legal Expense | [33 empty] | 252208.46 | [19 empty] | 252208.46 |  | 0 |  | 0 |  | 252208.46 |  | -252208.46
| Other | [5 empty] | Expense | 500000 |  | -300000 |  | 50000 |  | 0 |  | 0 |  | 0 |  | 10000 |  |  |  |  | 0 | 21422.91 | 0 |  | 75 |  | 6749.05 |  | 4454.98 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 42701.94 |  | 0 |  | 7298.06 |  | 50000 |  | 0
[10 empty] | 5511 | [44 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [6 empty] | 500000 | 0 | 0 | 0 | 256751 |  | 0 |  | 0 |  | 0 |  | 10000 |  | 0 |  | 605 | 0 | 21422.91 | 0 |  | 75 |  | 6749.05 |  | 4454.98 |  | 252208.46 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 295515.4 |  | 0 |  | 213444.06 |  | 508959.46 |  | -252208.46
INTEREST DURING CONSTRUCTION (6.5%) | [6 empty] | Capital | 10922239 |  | 47687 |  | 12619063.0291 |  | 340000 |  | 46410 |  | 139384 |  | 227439 |  | 231444 |  | 419367 | 378615.0109 | 426069.8241 | 463711.3754 |  | 505639.6857 |  | 568176 |  | 663422.2939 |  | 873819.3253 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5283497.5152 |  | 0 |  | 7335565.5139 |  | 12619063.0291 |  | 0
ECT TOTAL Project Costs | [11 empty] | 24783074.0291 | 0 | 340000 | 0 | 47646 | 0 | 218493 | 0 | 292259 | 0 | 1722017 | 0 | 540746.83 | 622375.1409 | 1381148.8641 | 515549.7754 |  | 551052.1557 |  | 693677.65 | 0 | 997479.5839 | 0 | 1810970.3253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9733415.3252 | 0 | 3428502 | 0 | 19298018.2539 | 0 | 29031433.5791 | 0 | -4248359.55 | 0
CONTINGENCY | [6 empty] | Capital | 5395729 |  | 67851 |  | 4408071.75 | [12 empty] | 0 | [29 empty] | 0 | 2030320 | -4408072 | 2030320 | 0 | 2030320 | 0 | 2030320 | 4408071.75
GRAND TOTAL (without Financing Fees & SWAP) | [11 empty] | 242553164.7791 | 0 | 7140000 | 0 | 1297646 | 0 | 33103293 | 0 | 292259 | 0 | 1722017 | 0 | 18851273.83 | 8237655.1409 | 8871230.9375 | 6989210.1254 |  | 7789231.1557 |  | 11600775.18 | 0 | 17679120.9139 | 0 | 39304333.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162878045.9786 | 2030320 | 12247860 | 2030320 | 92784367.6006 | 2030320 | 255662413.5791 | 2030320 | -13109248.8
$/Kw | [60 empty] | 420497.3908
INTEREST SWAP | [6 empty] | Capital | 0 |  | 44922.91 |  | -6078 | [7 empty] | -21556.4 |  | 66478.91 |  | -51000 | [30 empty] | -6077.49 |  | 0 |  | 0 |  | -6077.49 |  | 0
Franchise tax | [11 empty] | 0 | [9 empty] | 0 |  | 100 |  |  | 279 |  | 10 |  |  |  | 800 | [21 empty] | 1189 |  | 0 |  | 0 |  | 1189 |  | 0
Current FIT | [11 empty] | -56499 | [9 empty] | -56500 |  | -34 | -69954 | -22011 | -959 |  | -3 |  | 52217 |  | -52497 | [21 empty] | -149741 |  |  |  | 0 |  | -149741
Grand Total Including SWAP & Financial Fees | [11 empty] | 242490587.7791 | 0 | 7140000 | 0 | 1297646 | 0 | 33103293 | 0 | 270702.6 | 0 | 1731995.91 | 0 | 18800339.83 | 8167701.1409 | 8849219.9375 | 6988530.1254 |  | 7789238.1557 |  | 11652992.18 | 0 | 17627423.9139 | 0 | 39304333.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162723416.4886 | 2030320 | 12247860 | 2030320 | 92015031.2906 | 2030320 | 255507784.0891 | 2030320 | -13109248.8
Plano, IL
CAPITALIZED SALARIES | [6 empty] | Expense | 0 |  | 220000 | [7 empty] | 19728.93 |  | 0 |  |  |  | 12698.23 |  | 5725.45 |  |  | 591.45 | [5 empty] | 1242.3 | [19 empty] | 39986.36 |  |  |  | 0 |  | 39986.36 |  | 0
DEVELOPMENT EXPENSES | [6 empty] | Expense | 0 |  | 30000 | [5 empty] | 1342.96 |  | 28915.95 |  | 19328.23 |  | 567.63 |  | 68418.82 | [30 empty] | 118573.59 |  |  |  | 0 |  | 118573.59 |  | 0
LEGAL EXPENSES | [6 empty] | Expense | 0 |  | 35000 |  |  |  | 52133 | [7 empty] | 1331.32 | [32 empty] | 53464.32 |  |  |  | 0 |  | 53464.32 |  | 0
LAND | [6 empty] | Expense | 0 |  | 20000 |  |  |  | 87500 | [40 empty] | 87500 |  |  |  | 0 |  | 87500 |  | 0
0
TOTAL-Plano, IL | [7 empty] | 0 |  | 305000 |  | 0 |  | 139633 |  | 1342.96 |  | 48644.88 |  | 19328.23 | 0 | 1898.95 | 0 | 81117.05 | 0 | 5725.45 | 0 |  | 591.45 |  | 0 | 0 | 0 | 0 | 1242.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299524.27 |  |  |  | 0 |  | 299524.27 |  | 0
TOTAL ILLIONIS PLANT COSTS | [7 empty] | #REF! |  | #REF! |  | 242490587.7791 | 0 | 7279633 | 0 | 1298988.96 | 0 | 33151937.88 | 0 | 290030.83 | 0 | 1733894.86 | 0 | 18881456.88 | 8167701.1409 | 8854945.3875 | 6988530.1254 |  | 7789829.6057 |  | 11652992.18 | 0 | 17627423.9139 | 0 | 39305575.9953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163022940.7586 | 2030320 | 12247860 | 2030320 | 92015031.2906 | 2030320 | 255807308.3591 | 2030320 | -13109248.8
Note on R9: acopela: 6/2/99 Per DD budget was changed 6/11/99 Per Shealy Budget changed
Note on BN9: acopela: includes $2,024,000 CO#1

## Calvert City
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [62 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/2000_Weekly_Report___011100.xls'#$Calvert City
Calvert City, KY | [9 empty] | 510 |  | MW | [46 empty] | 2025-09-26 22:22 |  |  |  | Revision # 41
| 509 | [16 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated
[8 empty] | Expense / |  | ECT |  | Increase / |  | ECT |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  |  | Capital |  | Control Budget |  | (Savings) |  | Current Estimate |  | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 | 1999-07-31 | 1999-08-31 | Tran.to Gleason | 1999-09-30 | 1999-10-31 | 1999-11-30 | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[10 empty] | #REF! |  |  |  | as of 7/22/99 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase - WH501FD (2) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 12224800 |  | 31276400 |  | 3107550 |  | 0 |  | 3107250 |  | 6240218.71 |  | 0 | 0 | 393210.9 | -56349430 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -0.39 |  | 0 |  | 0.39 |  | 0 |  | 0
| TURBINE UNITS, Purchase - WH501F (1) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 17151750 |  | 12474000 |  | 0 | [7 empty] | 0 | 0 | 0 | -29625750 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Disassemble |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Freight Commission |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE REFURBISHMENT |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 93330000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 107199.47 | 0 | -107199 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.47 |  | 0 |  | 0 |  | 0.47 |  | -0.47
[59 empty] | 0 |  |  |  | 0
| Subtotal Westinghouse | [8 empty] | 93330000 |  | 0 |  | 0 |  | 29376550 |  | 43750400 |  | 3107550 |  | 0 |  | 3107250 |  | 6240218.71 |  | 0 | 107199.47 | 393210.9 | -86082379 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.08 |  | 0 |  | 0.39 |  | 0.47 |  | -0.47
| SPARE PARTS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 293460.55 | 883701.65 | -1177162 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.2 |  | 0 |  | 0 |  | 0.2 |  | -0.2
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [44 empty] | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT |  | Capital | [50 empty] | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT |  | Capital | [50 empty] | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT |  | Capital | [50 empty] | 0 |  | 0 |  | 0
[6 empty] | ECT | [52 empty] | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[59 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 293460.55 | 883701.65 | -1177162 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.2 |  | 0 |  | 0 |  | 0.2 |  | -0.2
| TOTAL MAJOR EQUIPMENT | [8 empty] | 93330000 |  | 0 |  | 0 |  | 29376550 |  | 43750400 |  | 3107550 |  | 0 |  | 3107250 |  | 6240218.71 |  | 0 | 400660.02 | 1276912.55 | -87259541 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.28 |  | 0 |  | 0.39 |  | 0.67 |  | -0.67
NEPCO SITE CONSTRUCTION COSTS
| CONSTRUCTION DIRECTS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONSTRUCTION INDIRECTS |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| NEPCO PURCHASED BOP EQUIPMENT |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENGINEERING |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| START-UP |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LANDSCAPING |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| WATER WELLS |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SWITCHYARD |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [5 empty] | 0 | [34 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UNION ADDER/OTHER |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| DRY TRANSFORMS AND PANELS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 5KV & 600 V SWITCHGEAR AND MCC'S |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 15 KV SWITCHGEAR |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONTROL PANELS/TERMINATION BOXES |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| DCS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UPS SYSTEM |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| DC SYSTEM |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIELD MOUNTED INSTRUMENTS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STACK MONITORING |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONTROL VALVES |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| BRIDGE CRANE |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MINOR MECHANICAL EQUIPMENT |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COMBUSTION TURBINE GENERATOR |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PRESSURE REDUCING STATION |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| WATER WASH SKID |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIELD/SHOP FAB VESSELS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PUMPS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[59 empty] | 0 |  | 0 |  | 0
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 77483.3333 | 77483.33 | -232450 | 77483.34 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.0033333 |  | 0 |  | 0 |  | 0.0033333 |  | -0.0033333
| NEPCO |  |  |  |  | NEPCO |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 236725 | 236725 | -710172 | 236722.33 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.33 |  | 0 |  | 0 |  | 0.33 |  | -0.33
| BASE FEE |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other -1/2 of redsign costs to change project to Gleason | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 250000 |  | 0 |  | 0 |  | 250000 |  | -250000
0
| TOTAL OVERHEADS & FEES | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 314208.3333 | 314208.33 | -942622 | 314205.67 | 0 | 0 | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 250000.3333 |  | 0 |  | 0 |  | 250000.3333 |  | -250000.3333
ADDERS OUTSIDE EECC SCOPE | [7 empty] | Capital
| PIPING | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ELECTRICAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIVIL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSTRUMENTATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ADDERS | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CONSTRUCTION
| SITE PREPARATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SITE IMPROVEMENTS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UNDERGROUND ELECTRICAL (LAB & MATL) | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UNDERGROUND PIPING (LAB & MATL) | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONCRETE | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GROUT & SPECIAL COATINGS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STRUCTURAL STEEL (LAB & MATL) | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ARCHITECTURAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SUBCONTRACT ERECTED BUILDINGS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ABOVE GROUND PIPING | [6 empty] | Capital | [52 empty] | 0 |  | 0
| MATERIAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SUBCONTRACT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ABOVE GROUND ELECTRICAL | [6 empty] | Capital | [52 empty] | 0 |  | 0
| MATERIAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SUBCONTRACT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSTRUMENTATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSULATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PAINTING | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COMBUSTION TURBINE/GENERATOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MAJOR MECHANICAL EQUIPMENT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SWITCHYARD | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL CONSTRUCTION | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT PROJECT COSTS
ENGINEERING
| ENGINEERING-DIRECT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENGINEERING-CONTRACT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| EQUIP RENTAL, FUEL, SMALL TOOLS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INDIRECT CONSTRUCTION LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OVERHEAD | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GENERAL PROVISIONS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PRORATABLE, ALLOWANCES | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STARTUP, TRAINING, MANUALS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONSTRUCTION MANAGEMENT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ENGINEERING | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MOBILIZATION OF O&M
| Mobilization Fee |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| EI Hourly billing | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
RESALE HANDLING FEES (.25%) | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
WATER INTERCONNECT | [5 empty] | ECT |  | Capital |  | 400000 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SALES TAX ON EQUIPMENT | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SPARE PARTS | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
LAND ACQUISITION
| Land Option |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000 |  | 0 |  | 0 |  | 6000 |  | -6000
| Title Commitment |  |  |  |  | ECT |  | Capital | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ECT |  | Capital | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | -369041 | 369040.52 | 294743.68 | 6000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 300743.2 |  | 0 |  | 0 |  | 300743.2 |  | -300743.2
| Closing Costs |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [44 empty] | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000 | 0 | 0 | -369041 | 369040.52 | 294743.68 | 6000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 306743.2 |  | 0 |  | 0 |  | 306743.2 |  | -306743.2
ENVIRONMENTAL PERMITTING
| Air Permitting -ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23801.2 |  | 35510.12 | 39859.1 | 0 | -69419 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 29751.42 |  | 0 |  | 0 |  | 29751.42 |  | -29751.42
| Groundwater - ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4183.38 |  | 10970 | 9001.6 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 24154.98 |  | 0 |  | 0 |  | 24154.98 |  | -24154.98
| Groundwater - NS | [6 empty] | Expense |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 6160.28 |  | 12971 |  | 0 |  | 154424.35 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 173555.63 |  | 0 |  | 0 |  | 173555.63 |  | -173555.63
| Other-NS | [6 empty] | Expense |  |  |  | 0 |  | 0 |  | 0 |  | 500 |  | 36910.7 |  | 19390 |  | 6648.63 |  | 44225.2 |  | 0 | 13721.51 | 7968.98 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 129365.02 |  | 0 |  | 0 |  | 129365.02 |  | -129365.02
| Other -ENSR | [6 empty] | Expense |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13095 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13095 |  | 0 |  | 0 |  | 13095 |  | -13095
| Other | [12 empty] | 0 | [14 empty] | 100 |  | 0 | 9500 | [22 empty] | 9600 |  | 0 |  | 0 |  | 9600 |  | -9600
0
| Subtotal Environmental Permitting | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 500 |  | 43070.98 |  | 32361 |  | 6648.63 |  | 239729.13 |  | 46480.12 | 62682.21 | 7968.98 | -69419 | 9500 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 379522.05 |  | 0 |  | 0 |  | 379522.05 |  | -379522.05
ELECTRICAL INTERCONNECTION
| Facilities Study | [5 empty] | Capital |  | 0 |  | 60000 |  | 60000 | 0 |  | 0 |  |  |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7500 |  | 0 |  | 0 |  | 7500 | 0 | -7500
| System Impact Study | [5 empty] | Capital |  | 7500 |  | 27500 |  | 35000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Work Order Cost | [5 empty] | Capital |  | 1992500 |  | 207500 |  | 2200000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[59 empty] | 0 |  | 0
| Subtotal Electrical Interconnection | [7 empty] | 2000000 |  | 295000 |  | 2295000 | 0 |  | 0 |  | 0 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7500 |  | 0 |  | 0 |  | 7500 | 0 | -7500
GAS INTERCONNECTION | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Startup Fuel
| Power Sales | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
INSURANCE DURING CONSTR | [7 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CAPITALIZED SALARIES | [7 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 4234.96 |  | 20999.1 |  | 10759.47 | 6023.47 | 6145.77 | -48163 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -0.23 |  | 0 |  | 0.23 |  | 0 |  | 0
DEVELOPMENT EXPENSES
| Salaries | [6 empty] | Expense |  | 200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21983.72 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 14449 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 36432.72 |  | 0 |  | 0 |  | 36432.72 |  | -36432.72
| Travel Expenses | [6 empty] | Expense |  | 0 |  | 50000 |  | 0 |  | 0 |  | 135 |  | 2870.91 |  | 7328.25 |  | 2780.87 |  | 15078.35 |  | 11429.61 | 15496.73 | 12735.73 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 67855.45 |  | 0 |  | 0 |  | 67855.45 |  | -67855.45
| Consulting - Calpine | [6 empty] | Expense |  | 0 |  | 24235 |  | 0 |  | 0 |  | 0 |  | 24235 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 48335.34 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 72570.34 |  | 0 |  | 0 |  | 72570.34 |  | -72570.34
| Other | [6 empty] | Expense |  | 400000 |  | -356935 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2287.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10697.29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12984.79 |  | 0 |  | 0 |  | 12984.79 |  | -12984.79
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [26 empty] | 83611.75 | 49930.8 | 30286.69 | -133542 | [23 empty] | 30287.24 |  |  |  | 0 |  | 30287.24 |  | -30287.24
| TOTAL DEVELOPMENT EXPENSE | [8 empty] | 600000 |  | -282700 |  | 0 | 0 | 0 | 0 | 135 | 0 | 49089.63 | 0 | 7328.25 | 0 | 2780.87 | 0 | 17365.85 | 0 | 95041.36 | 65427.53 | 43022.42 | -70757.66 | 0 | 0 | 10697.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220130.54 | 0 | 0 | 0 | 0 | 0 | 220130.54 | 0 | -220130.54 | 0
LEGAL EXPENSES
| Andrews & Kurth | [6 empty] | Expense |  | 0 |  | 294489 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9963.17 |  | 0 |  | 3785 |  | 0 | 33367.16 | 0 | -14302.18 | 0 | 28608.51 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 61421.66 |  | 0 |  | 0 |  | 61421.66 |  | -61421.66
| Middleton & Reutlinger | [6 empty] | Expense |  | 500000 |  | -310271.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 76235.1 |  | 51621.39 |  | 16078.18 | 16050.89 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 159985.56 |  | 0 |  | 0 |  | 159985.56 |  | -159985.56
| Ogden Newell & Welch | [10 empty] | 5511 |  | 0 | [11 empty] | 5510.85 |  | 10271.2 | [26 empty] | 15782.05 |  | 0 |  | 0 |  | 15782.05 |  | -15782.05
| TOTAL LEGAL EXPENSE | [8 empty] | 500000 | 0 | -10271.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 9963.17 |  | 76235.1 |  | 60917.24 |  | 26349.38 | 49418.05 | 0 | -14302.18 | 0 | 28608.51 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 237189.27 |  | 0 |  | 0 |  | 237189.27 |  | -237189.27
INTEREST DURING CONSTRUCTION (6.5%) | [7 empty] | Capital |  | 10922239 |  | 47687 |  | 0 |  | 704264 |  | 320324 |  | 477081 |  | 425796 |  | 378280 |  | 557261 |  | 481371.225 | 488494.4432 | 500068.5242 | -4332940.1924 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT TOTAL Project Costs | [13 empty] | 0 | 0 | 704264 | 0 | 320959 | 0 | 569241.61 | 0 | 475448.42 | 0 | 468179.56 | 0 | 896272.32 | 0 | 666001.555 | 672045.7032 | 557205.6942 | -4904623.0324 | 378540.52 | 323352.19 | 16697.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1143584.83 | 0 | 0 | 0 | 0.23 | 0 | 1143585.06 | 0 | -1143585.06 | 0
CONTINGENCY | [7 empty] | Capital |  | 5395729 |  | 67851 |  | 0 | [40 empty] | 0 | 2030320 | 0 | 2030320 | 0 | 2030320 | 0 | 2030320 | 0
GRAND TOTAL (without Financing Fees & SWAP) | [13 empty] | 0 | 0 | 30080814 | 0 | 44071359 | 0 | 3684291.61 | 0 | 475448.42 | 0 | 3575429.56 | 0 | 7136491.03 | 0 | 666001.555 | 1386914.0565 | 2148326.5742 | -93106786.0324 | 692746.19 | 323352.19 | 16697.29 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401085.4433 | 2030320 | 0 | 2030320 | 0.62 | 2030320 | 1401086.0633 | 2030320 | -1401086.0633
$/Kw | [60 empty] | 590051.1933
INTEREST SWAP | [7 empty] | Capital |  | 0 |  | 44922.91 |  | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
FINANCIAL FEES | [13 empty] | 0 | [7 empty] | 0 |  | 0 |  | 0 | [28 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
Franchise Tax | [25 empty] | 100 | [28 empty] | 100
Current FIT | [13 empty] | 0 | [9 empty] | -82061 |  | -1963 |  | -32859 | -22657 |  |  | -144358 | -13821 | -99352 | [20 empty] | -397071 |  |  |  | 0 |  | -397071 |  | 397071
Grand Total Including SWAP & Financial Fees | [13 empty] | 0 | 0 | 30080814 | 0 | 44071359 | 0 | 3684291.61 | 0 | 475448.42 | 0 | 3493368.56 | 0 | 7134628.03 | 0 | 633142.555 | 1364257.0565 | 2148326.5742 | -93106786.0324 | 548388.19 | 309531.19 | -82654.71 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1004114.4433 | 2030320 | 0 | 2030320 | 0.62 | 2030320 | 1004015.0633 | 2030320 | -1004015.0633 | 0
Note on AD195: acopela: Legal Expenses incurred 1998 under the 2000 peaker work order. Reclass to expense 5/99

## Gleason
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [64 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/2000_Weekly_Report___011100.xls'#$Gleason
Gleason, TN | [9 empty] | 510 |  | MW | [48 empty] | 2025-09-26 22:22 |  |  |  | Revision # 41
| 509 | [16 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated
[8 empty] | Expense / |  | ECT |  | Increase / |  | ECT |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  |  | Capital |  | Control Budget |  | (Savings) |  | Current Estimate |  | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 |  | 1999-07-31 | 1999-08-31 | Tran.from Calvert | 1999-09-30 | 1999-10-31 | 1999-11-30 |  | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[10 empty] | as of 7/22/99 |  |  |  | as of 7/22/99 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase - WH501FD (2) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 62145000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 56349430 | 0 | 1282310 | 144155 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 57775895 |  | 528601 |  | 4897706 |  | 62673601 |  | -528601
| TURBINE UNITS, Purchase - WH501F (1) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 31185000 |  | 0 |  | 0 |  | 0 | [7 empty] | 0 |  | 0 | 0 | 29625750 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 29625750 |  | 1214500 |  | 2773750 |  | 32399500 |  | -1214500
| TURBINE UNITS, Disassemble |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Freight Commission |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE REFURBISHMENT |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 93330000 |  | 0 |  | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 107199 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 107199 |  | 0 |  | 142801 |  | 250000 |  | 0
[61 empty] | 0 |  |  |  | 0
| Subtotal Westinghouse | [8 empty] | 93330000 |  | 0 |  | 93580000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 86082379 | 0 | 1282310 | 144155 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 87508844 |  | 1743101 |  | 7814257 |  | 95323101 |  | -1743101
| SPARE PARTS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 5885811 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 1177162 | 0 | 0 | 58500 |  | 1765743.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3001405.3 |  | 0 |  | 2884405.7 |  | 5885811 |  | 0
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [42 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT |  | Capital | [48 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT |  | Capital | [48 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT |  | Capital | [48 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
[6 empty] | ECT | [50 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 8000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8000 |  | 0 |  | 0 |  | 8000 |  | -8000
[61 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [8 empty] | 0 |  | 0 |  | 5885811 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1177162 | 0 | 0 | 58500 |  | 1773743.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3009405.3 |  | 0 |  | 2884405.7 |  | 5893811 |  | -8000
| TOTAL MAJOR EQUIPMENT | [8 empty] | 93330000 |  | 0 |  | 99465811 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 87259541 | 0 | 1282310 | 202655 |  | 1773743.3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 90518249.3 |  | 1743101 |  | 10698662.7 |  | 101216912 |  | -1751101
NEPCO SITE CONSTRUCTION COSTS
[16 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
General Provisions
| EQUIPMENT & SMALL TOOL |  |  |  |  | Nepco |  | Capital | [5 empty] | 1493638 | [20 empty] | 11452 | [21 empty] | 11452 |  |  |  | 1482186 |  | 1493638 |  | 0
| FIELD STAFF |  |  |  |  | Nepco |  | Capital | [5 empty] | 1449432 | [20 empty] | 43084 | [21 empty] | 43084 |  |  |  | 1406348 |  | 1449432 |  | 0
| TEMP FACILITIES & INDIRECT SUPPORT |  |  |  |  | Nepco |  | Capital | [5 empty] | 510345 | [20 empty] | 12159 | [21 empty] | 12159 |  |  |  | 498186 |  | 510345 |  | 0
| INDIRECT SUPPLIES |  |  |  |  | Nepco |  | Capital | [5 empty] | 537850 | [20 empty] | 19967 | [21 empty] | 19967 |  |  |  | 517883 |  | 537850 |  | 0
| PAYROLL BURDENS |  |  |  |  | Nepco |  | Capital | [5 empty] | 6815905 | [20 empty] | 81333 | [21 empty] | 81333 |  |  |  | 6734572 |  | 6815905 |  | 0
| HO PROJ MGMT/SUPPORT |  |  |  |  | Nepco |  | Capital | [5 empty] | 114599 | [20 empty] | 12404 | [21 empty] | 12404 |  |  |  | 102195 |  | 114599 |  | 0
| BUSINESS EXPENSES |  |  |  |  | Nepco |  | Capital | [5 empty] | 716745 | [20 empty] | 95392 | [21 empty] | 95392 |  |  |  | 621353 |  | 716745 |  | 0
| FIELD NON-PROD LABOR |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 60432 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 14212 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 14212 |  |  |  | 46220 |  | 60432 |  | 0
| INDIRECT ENGR LABOR |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 2475371 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 60494 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 60494 |  |  |  | 2414877 |  | 2475371 |  | 0
| DIRECT PROJECT ENGR |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 437957 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 58714 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 58714 |  |  |  | 379243 |  | 437957 |  | 0
| FREIGHT & TAXES |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 288340 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 11607 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 11607 |  |  |  | 276733 |  | 288340 |  | 0
| VENDOR REPS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 50000 |  | 50000 |  | 0
| CONTINGENCY |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
| RESERVES | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
[8 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
[8 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0
| TOTAL General Provisions | [6 empty] | Capital |  | 0 |  | 0 |  | 14950614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420818 | 0 | 0 | 0 | 14529796 | 0 | 14950614
BOP Procurement
| PIPE, VALVES, SPEC, & HANGERS |  |  |  |  | Nepco | [7 empty] | 200485 | [42 empty] | 0 |  |  |  | 200485 |  | 200485 |  | 0
| CONDUIT & WIRE |  |  |  |  | Nepco | [7 empty] | 360237 | [42 empty] | 0 |  |  |  | 360237 |  | 360237 |  | 0
| BUS DUCT |  |  |  |  | Nepco | [7 empty] | 1090200 | [42 empty] | 0 |  |  |  | 1090200 |  | 1090200 |  | 0
| DRY XFORMERS & PANELS |  |  |  |  | Nepco | [7 empty] | 24750 | [42 empty] | 0 |  |  |  | 24750 |  | 24750 |  | 0
| OIL FILLED XFORMERS |  |  |  |  | Nepco | [7 empty] | 317000 | [42 empty] | 0 |  |  |  | 317000 |  | 317000 |  | 0
| MOTOR CONTROL CENTER |  |  |  |  | Nepco | [7 empty] | 115847 | [42 empty] | 0 |  |  |  | 115847 |  | 115847 |  | 0
| SWITCHGEAR |  |  |  |  | Nepco | [7 empty] | 1602655 | [20 empty] | 84021 | [21 empty] | 84021 |  |  |  | 1518634 |  | 1602655 |  | 0
| CNTL PANELS & TRMNTN BOX |  |  |  |  | Nepco | [7 empty] | 6285 | [42 empty] | 0 |  |  |  | 6285 |  | 6285 |  | 0
| ELECTRICAL DEVICES | [12 empty] | 6795 | [42 empty] | 0 |  |  |  | 6795 |  | 6795 |  | 0
| LIGHT POLE & LIGHT FIXTURES | [12 empty] | 83824 | [42 empty] | 0 |  |  |  | 83824 |  | 83824 |  | 0
| ELEC HEAT TRACE & TEST |  |  |  |  | Nepco | [7 empty] | 11569 | [42 empty] | 0 |  |  |  | 11569 |  | 11569 |  | 0
| SPECIAL SYSTEMS |  |  |  |  | Nepco | [7 empty] | 113232 | [42 empty] | 0 |  |  |  | 113232 |  | 113232 |  | 0
| FIELD MOUNTED INSTRUMENTS |  |  |  |  | Nepco | [7 empty] | 76358 | [42 empty] | 0 |  |  |  | 76358 |  | 76358 |  | 0
| STACK MONITORING |  |  |  |  | Nepco | [7 empty] | 516000 | [42 empty] | 0 |  |  |  | 516000 |  | 516000 |  | 0
| CNTL VALVES & MISC EQUIPMENT |  |  |  |  | Nepco | [7 empty] | 37965 | [42 empty] | 0 |  |  |  | 37965 |  | 37965 |  | 0
| TUBING, TRAV & STANDS |  |  |  |  | Nepco | [7 empty] | 19322 | [42 empty] | 0 |  |  |  | 19322 |  | 19322 |  | 0
| DCS |  |  |  |  | Nepco | [7 empty] | 123375 | [42 empty] | 0 |  |  |  | 123375 |  | 123375 |  | 0
| ASH TRANSFER EQUIPMENT |  |  |  |  | Nepco | [7 empty] | 0 | [42 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| PUMPS |  |  |  |  | Nepco | [7 empty] | 129500 | [42 empty] | 0 |  |  |  | 129500 |  | 129500 |  | 0
| CONDENSER & AUX EQUIPMENT |  |  |  |  | Nepco | [7 empty] | 30000 | [42 empty] | 0 |  |  |  | 30000 |  | 30000 |  | 0
| FUEL GAS FILTER |  |  |  |  | Nepco | [7 empty] | 67500 | [42 empty] | 0 |  |  |  | 67500 |  | 67500 |  | 0
| STEAM WATER SEPARATOR |  |  |  |  | Nepco | [7 empty] | 0 | [42 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| PRESSURE REDUCE STAT |  |  |  |  | Nepco | [7 empty] | 210500 | [42 empty] | 0 |  |  |  | 210500 |  | 210500 |  | 0
| STEAM TURBINE |  |  |  |  | Nepco | [7 empty] | 0 | [42 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| TANKS NON-PRESSURIZE |  |  |  |  | Nepco | [7 empty] | 20500 | [42 empty] | 0 |  |  |  | 20500 |  | 20500 |  | 0
| TOTAL BOP Procurement | [6 empty] | Capital |  | 0 |  | 0 |  | 5163899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84021 | 0 | 0 | 0 | 5079878 | 0 | 5163899
Construction
| SITE PREPARATION/IMPROVEMENTS - S | [12 empty] | 2221753 | [20 empty] | 204588 | [21 empty] | 204588 |  |  |  | 2017165 |  | 2221753 |  | 0
| UNDERGROUND ELECTRICAL - L | [12 empty] | 363263 | [42 empty] | 0 |  |  |  | 363263 |  | 363263 |  | 0
| UNDERGROUND ELECTRICAL - M | [12 empty] | 272375 | [42 empty] | 0 |  |  |  | 272375 |  | 272375 |  | 0
| UNDERGROUND ELECTRICAL - S | [12 empty] | 0 | [42 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| UNDERGROUND PIPING - L | [12 empty] | 288919 | [42 empty] | 0 |  |  |  | 288919 |  | 288919 |  | 0
| UNDERGROUND PIPING - M | [12 empty] | 175031 | [42 empty] | 0 |  |  |  | 175031 |  | 175031 |  | 0
| UNDERGROUND PIPING - S | [12 empty] | 0 | [42 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| CONCRETE - L | [12 empty] | 1115290 | [42 empty] | 0 |  |  |  | 1115290 |  | 1115290 |  | 0
| CONCRETE - M | [12 empty] | 751110 | [42 empty] | 0 |  |  |  | 751110 |  | 751110 |  | 0
| SPECIAL CONCRETE - L | [12 empty] | 79043 | [42 empty] | 0 |  |  |  | 79043 |  | 79043 |  | 0
| SPECIAL CONCRETE - M | [12 empty] | 43500 | [42 empty] | 0 |  |  |  | 43500 |  | 43500 |  | 0
| STRUCTURAL STEEL - L | [12 empty] | 81962 | [42 empty] | 0 |  |  |  | 81962 |  | 81962 |  | 0
| STRUCTURAL STEEL - M | [12 empty] | 217350 | [42 empty] | 0 |  |  |  | 217350 |  | 217350 |  | 0
| ARCHITECTURAL -S | [12 empty] | 199748 | [42 empty] | 0 |  |  |  | 199748 |  | 199748 |  | 0
| BUILDINGS -S | [12 empty] | 390000 | [42 empty] | 0 |  |  |  | 390000 |  | 390000 |  | 0
| A/G PIPING - L | [12 empty] | 290527 | [42 empty] | 0 |  |  |  | 290527 |  | 290527 |  | 0
| A/G PIPING - S | [12 empty] | 0 | [42 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| A/G ELECTRICAL - L | [12 empty] | 890472 | [42 empty] | 0 |  |  |  | 890472 |  | 890472 |  | 0
| A/G ELECTRICAL - S | [12 empty] | 125000 | [42 empty] | 0 |  |  |  | 125000 |  | 125000 |  | 0
| INSTRUMENTATION - L | [12 empty] | 247404 | [42 empty] | 0 |  |  |  | 247404 |  | 247404 |  | 0
| INSTRUMENTATION - S | [12 empty] | 75000 | [42 empty] | 0 |  |  |  | 75000 |  | 75000 |  | 0
| INSULATION & PAINTING -S | [12 empty] | 564947 | [42 empty] | 0 |  |  |  | 564947 |  | 564947 |  | 0
| MECHANICAL EQUIPMENT - L | [12 empty] | 1754309 | [42 empty] | 0 |  |  |  | 1754309 |  | 1754309 |  | 0
| MECHANICAL EQUIPMENT - S | [12 empty] | 1667825 | [42 empty] | 0 |  |  |  | 1667825 |  | 1667825 |  | 0
| PLANT STARTUP - L | [12 empty] | 582059 | [42 empty] | 0 |  | -198000 |  | 384059 |  | 384059 |  | 198000
| PLANT STARTUP - M | [12 empty] | 0 | [42 empty] | 0 |  | 148000 |  | 148000 |  | 148000 |  | -148000
| PLANT STARTUP - S | [12 empty] | 0 | [42 empty] | 0 |  | 50000 |  | 50000 |  | 50000 |  | -50000
[57 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
[61 empty] | 0 |  | 0 |  | 0
| TOTAL Construction | [12 empty] | 12396887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204588 | 0 | 0 | 0 | 12192299 | 0 | 12396887 | 0
Switchyard
| SWITCHYARD | [12 empty] | 9230000 | [44 empty] | 2829700 |  | 12059700 |  | 12059700 |  | -2829700
| TOTAL SWITCHYARD | [12 empty] | 9230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2829700 | 0 | 12059700 | 0 | 12059700 |  | -2829700
| Nepco % Complete | [12 empty] | 0 | [20 empty] | 5344604.56 | [21 empty] | 5344604.56 |  |  |  | -5344605 |  | -0.44 |  | 0.44
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [8 empty] | 0 |  | 0 |  | 41741400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054031.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6054031.56 | 0 | 2829700 | 0 | 38517068 | 0 | 44571099.56 | 0 | -2829699.56
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 929800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 232450 | 0 | 77483.34 | 77483.33 |  | 77483.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 464900 |  | 0 |  | 464900 |  | 929800 |  | 0
| NEPCO |  |  |  |  | NEPCO |  | Capital |  | 0 |  | 0 |  | 2840700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 710172 | 0 | 236722.33 | 236722.33 |  | 236722 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1420338.66 |  | 0 |  | 1420361.34 |  | 2840700 |  | 0
| BASE FEE |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 3066700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3066700 |  | 3066700 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other -1/2 of redsign costs to change project to Gleason | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | -250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -250000 |  | 0 |  | 0 |  | -250000 |  | 250000
0
| TOTAL OVERHEADS & FEES | [8 empty] | 0 |  | 0 |  | 6837200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 942622 | 0 | 314205.67 | 314205.66 |  | 64205.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1635238.66 |  | 0 |  | 4951961.34 |  | 6587200 |  | 250000
ADDERS OUTSIDE EECC SCOPE | [7 empty] | Capital
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ADDERS | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT PROJECT COSTS
ENGINEERING
| ENGINEERING-DIRECT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENGINEERING-CONTRACT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| EQUIP RENTAL, FUEL, SMALL TOOLS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INDIRECT CONSTRUCTION LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OVERHEAD | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GENERAL PROVISIONS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PRORATABLE, ALLOWANCES | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STARTUP, TRAINING, MANUALS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONSTRUCTION MANAGEMENT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ENGINEERING | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MOBILIZATION OF O&M
| Mobilization Fee |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 908786 |  | 908786 |  | 0
| EI Hourly billing | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [8 empty] | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 908786 |  | 908786 |  | 0
RESALE HANDLING FEES (.25%) | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
WATER INTERCONNECT | [5 empty] | ECT |  | Capital |  | 400000 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SALES TAX ON EQUIPMENT & Materials | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 675000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 675000 |  | 675000 |  | 0
SPARE PARTS | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 1247007 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1247007 |  | 1247007 |  | 0
LAND ACQUISITION
| Land Option |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Title Commitment |  |  |  |  | ECT |  | Capital | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ECT |  | Capital | [5 empty] | 369041 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 369041 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 369041 |  | 0 |  | 0 |  | 369041 |  | 0
| Closing Costs |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [46 empty] | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [8 empty] | 0 |  | 0 |  | 369041 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 369041 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 369041 |  | 0 |  | 0 |  | 369041 |  | 0
ENVIRONMENTAL PERMITTING
| Air Permitting -ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 69419 | [17 empty] | 69419 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 69419 |  | 0 |  | 0 |  | 69419 |  | 0
| Groundwater - ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 0 | [18 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Groundwater - NS | [6 empty] | Expense |  |  |  | 0 |  | 0 | [18 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other-NS | [6 empty] | Expense |  |  |  | 0 |  | 0 | [18 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other -ENSR | [6 empty] | Expense |  |  |  | 0 |  | 0 | [18 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [12 empty] | 470581 | [18 empty] | 190571.4 |  | 264856.32 | [21 empty] | 455427.72 |  | 0 |  | 15153.28 |  | 470581 |  | 0
0
| Subtotal Environmental Permitting | [8 empty] | 0 |  | 0 |  | 540000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 69419 | 190571.4 | 0 | 264856.32 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 524846.72 |  | 0 |  | 15153.28 |  | 540000 |  | 0
ELECTRICAL INTERCONNECTION - TVA"S side of fence
| Facilities Study | [5 empty] | Capital |  | 0 |  | 60000 |  | 60000 | 60000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 7500 | 0 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 15000 |  | 0 |  | 45000 |  | 60000 |  | 0
| System Impact Study | [5 empty] | Capital |  | 7500 |  | 27500 |  | 35000 | 35000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 35000 |  | 35000 |  | 0
| Work Order Cost | [5 empty] | Capital |  | 1992500 |  | 207500 |  | 2200000 | 2105000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 10517.87 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 10517.87 |  | 1500000 |  | 3594482.13 |  | 3605000 |  | -1500000
[61 empty] | 0 |  | 0 |  | 0
| Subtotal Electrical Interconnection | [7 empty] | 2000000 |  | 295000 |  | 2295000 | 2200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 18017.87 | 0 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25517.87 |  | 1500000 |  | 3674482.13 |  | 3700000 |  | -1500000
GAS INTERCONNECTION | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 1100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1100000 |  | 1100000 |  | 0
Startup Fuel * Power
| Power Sales | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost/Power Revenue | [6 empty] | Capital |  | 0 |  | 0 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [8 empty] | 0 |  | 0 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 0
INSURANCE DURING CONSTR | [7 empty] | Capital |  | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 200935.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 200935.25 |  | 0 |  | 0 |  | 200935.25 |  | -935.25
CAPITALIZED SALARIES | [7 empty] | Capital |  | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 52170.4 | 2851 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 55021.4 |  | 0 |  | 144978.6 |  | 200000 |  | 0
DEVELOPMENT EXPENSES
| Salaries | [6 empty] | Expense |  | 200000 |  | 0 |  | 100000 |  | 0 | [14 empty] | 13179.81 |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13179.81 |  | 0 |  | 86820.19 |  | 100000 |  | 0
| Travel Expenses | [6 empty] | Expense |  | 0 |  | 50000 |  | 150000 |  | 0 | [15 empty] | 67146.1 | 2410.51 | 7333.62 | 10298.6 |  | 11236.54 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 98425.37 |  | 0 |  | 51574.63 |  | 150000 |  | 0
| Consulting - Calpine | [6 empty] | Expense |  | 0 |  | 24235 |  | 24235 |  | 0 | [15 empty] | 17043.53 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 17043.53 |  | 0 |  | 7191.47 |  | 24235 |  | 0
| Other | [6 empty] | Expense |  | 400000 |  | -356935 |  | 125765 |  | 0 | [14 empty] | 5904 | 2286 |  | 11540.01 | 19587.28 |  | 34420.93 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 73738.22 |  | 0 |  | 52026.78 |  | 125765 |  | 0
| Enron Generation Comp Costs | [33 empty] | 83333.33 |  | 107679.57 | [19 empty] | 191012.9 |  |  |  | 0 |  | 191012.9 |  | -191012.9
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [30 empty] | 32203.28 | [24 empty] | 32203.28 |  | 0 |  | 0 |  | 32203.28 |  | -32203.28
| TOTAL DEVELOPMENT EXPENSE | [8 empty] | 600000 |  | -282700 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19083.81 | 118678.91 | 2410.51 | 18873.63 | 113219.21 | 0 | 153337.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425603.11 | 0 | 0 | 0 | 197613.07 | 0 | 623216.18 | 0 | -223216.18 | 0
LEGAL EXPENSES
| Legal | [6 empty] | Expense |  | 0 |  | 294489 |  | 500000 |  | 0 |  | 0 | [12 empty] | 3543 | 14302.18 | 13885.7 | 27414.72 | 13907.58 |  | 7634.37 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 80687.55 |  | 0 |  | 419312.45 |  | 500000 |  | 0
| Everest Legal | [6 empty] | Expense |  | 500000 |  | -310271.2 |  | 0 |  | 0 |  | 0 | [14 empty] | 0 | 0 | 0 |  | 252208.46 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 252208.46 |  | 0 |  | 0 |  | 252208.46 |  | -252208.46
[12 empty] | 5511 |  | 0 | [42 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [8 empty] | 500000 | 0 | -10271.2 | 0 | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3543 | 14302.18 | 13885.7 | 27414.72 | 13907.58 |  | 259842.83 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 332896.01 |  | 0 |  | 419312.45 |  | 752208.46 |  | -252208.46
INTEREST DURING CONSTRUCTION (6.5%) | [7 empty] | Capital |  | 10922239 |  | 47687 |  | 11103663.5962 | [17 empty] | 4332940 | 505668.93 | 517447.9227 | 557933.4232 |  | 574337.9453 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6488328.2212 |  | 0 |  | 4615335.375 |  | 11103663.5962 |  | 0
ECT TOTAL Project Costs | [13 empty] | 17743497.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22626.81 | 4956551.49 | 715387.54 | 563736.2727 | 949916.5332 | 0 | 1188453.0653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8396671.7112 | 0 | 0 | 0 | 9823185.775 | 0 | 18219857.4862 | 0 | -476359.89 | 0
CONTINGENCY | [7 empty] | Capital |  | 5395729 |  | 67851 |  | 5423498 | [42 empty] | 0 |  | -5423498 | 2030320 | 0 | 2030320 | 0 | 2030320 | 5423498
SWAP | [13 empty] | -6077 | [17 empty] | -6077 | [24 empty] | -6077 | [5 empty] | -6077 |  | 0
GRAND TOTAL (without Financing Fees & SWAP) | [13 empty] | 173405329.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22626.81 | 93152637.49 | 715387.54 | 2178269.8127 | 7520808.7532 | 0 | 3033901.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106623632.1012 | 0 | 649303 | 2030320 | 67665359.945 | 2030320 | 174288992.0462 | 2030320 | -883662.45
$/Kw
Current FIT | [13 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 65 | [21 empty] | 65 |  |  |  | 0 |  | 65
0
Grand Total Including | [13 empty] | 173405329.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22626.81 | 93152637.49 | 715387.54 | 2178269.8127 | 7520873.7532 | 0 | 3033901.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106623697.1012 | 0 | 649303 | 2030320 | 67665359.945 | 2030320 | 174289057.0462 | 2030320 | -883662.45 | 0
Note on AD223: acopela: Legal Expenses incurred 1998 under the 2000 peaker work order. Reclass to expense 5/99

## Wheatland
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [65 empty] | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/2000_Weekly_Report___011100.xls'#$Wheatland
Wheatland, IN | [7 empty] | 510 |  | MW | [51 empty] | 2025-09-26 22:22 |  |  |  | Revision # 41
| 470 | [14 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated
[7 empty] | Expense / | ECT |  | Increase / |  | ECT |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  | Capital | Control Budget |  | (Savings) |  | Current Estimate |  | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 |  | 1999-07-31 |  | 1999-08-31 |  | 1999-09-30 |  | 1999-10-31 |  | 1999-11-30 |  | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[8 empty] | #REF! |  |  |  | as of 7/22/99 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999 |  | As of 12/31/1999
MAJOR EQUIPMENT
| TURBINE UNITS - WH501D5A (4) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 85821500 |  | 16673400 |  | 43401650 |  | 4291075 |  |  |  | 4291075 |  | 8617667 |  | 0 |  | 0 |  | 318420.9 |  | 0 |  | 0 |  | 39600 |  | 1077741.26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 78710629.16 |  | 297801 |  | 7408671.84 |  | 86119301 |  | -297801
| Other |  |  |  |  | ECT | Capital | 93330000 |  | 0 |  | 100000 | [13 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 100000 |  | 100000 |  | 0
0
| Subtotal Westinghouse | [6 empty] | 93330000 |  | 0 |  | 85921500 |  | 16673400 |  | 43401650 |  | 4291075 |  | 0 |  | 4291075 |  | 8617667 |  | 0 |  | 0 |  | 318420.9 |  | 0 |  | 0 |  | 39600 |  | 1077741.26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 78710629.16 |  | 297801 |  | 7508671.84 |  | 86219301 |  | -297801
| SPARE PARTS | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 3949654 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 197482.7 |  | 0 |  | 935 |  | 595253.1 |  | 0 |  | 1190506.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1984177 |  | 18700 |  | 1984177 |  | 3968354 |  | -18700
| TRANSFORMERS - Other Misc Charges | [10 empty] | 412400 | [15 empty] | 62400 |  | 350000 |  |  |  | 59780 | [23 empty] | 472180 |  | 59780 |  | 0 |  | 472180 |  | -59780
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT | Capital | [50 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT | Capital | [50 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT | Capital | [50 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [45 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
[6 empty] | ECT | [51 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[62 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [6 empty] | 0 |  | 0 |  | 4362054 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 259882.7 |  | 350000 |  | 935 |  | 655033.1 |  | 0 |  | 1190506.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2456357 |  | 78480 |  | 1984177 |  | 4440534 |  | -78480
| TOTAL MAJOR EQUIPMENT | [6 empty] | 93330000 |  | 0 |  | 90283554 |  | 16673400 |  | 43401650 |  | 4291075 |  | 0 |  | 4291075 |  | 8617667 |  | 0 |  | 259882.7 |  | 668420.9 |  | 935 |  | 655033.1 |  | 39600 |  | 2268247.46 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 81166986.16 |  | 376281 |  | 9492848.84 |  | 90659835 |  | -376281
NEPCO SITE CONSTRUCTION COSTS
[14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
General Provisions
| EQUIPMENT & SMALL TOOL |  |  |  |  | Nepco | Capital |  |  |  |  | 1132835 | [23 empty] | 19960 | [21 empty] | 19960 |  | 0 |  | 1112875 |  | 1132835 |  | 0
| FIELD STAFF |  |  |  |  | Nepco | Capital |  |  |  |  | 1473926 | [23 empty] | 77323 | [21 empty] | 77323 |  | -87435 |  | 1309168 |  | 1386491 |  | 87435
| TEMP FACILITIES & INDIRECT SUPPORT |  |  |  |  | Nepco | Capital |  |  |  |  | 684595 | [23 empty] | 54748 | [21 empty] | 54748 |  | 0 |  | 629847 |  | 684595 |  | 0
| INDIRECT SUPPLIES |  |  |  |  | Nepco | Capital |  |  |  |  | 624805 | [23 empty] | 22150 | [21 empty] | 22150 |  | 0 |  | 602655 |  | 624805 |  | 0
| PAYROLL BURDENS |  |  |  |  | Nepco | Capital |  |  |  |  | 3989779 | [23 empty] | 123159 | [21 empty] | 123159 |  | -37260 |  | 3829360 |  | 3952519 |  | 37260
| HO PROJ MGMT/SUPPORT |  |  |  |  | Nepco | Capital |  |  |  |  | 107003 | [23 empty] | 10575 | [21 empty] | 10575 |  | 0 |  | 96428 |  | 107003 |  | 0
| BUSINESS EXPENSES |  |  |  |  | Nepco | Capital |  |  |  |  | 566132 | [23 empty] | 88926 | [21 empty] | 88926 |  | 0 |  | 477206 |  | 566132 |  | 0
| FIELD NON-PROD LABOR |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 121187 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 47401 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 47401 |  | 0 |  | 73786 |  | 121187 |  | 0
| INDIRECT ENGR LABOR |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 2713492 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 83850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 83850 |  | 0 |  | 2629642 |  | 2713492 |  | 0
| DIRECT PROJECT ENGR |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 313552 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 84553 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 84553 |  | 0 |  | 228999 |  | 313552 |  | 0
| FREIGHT & TAXES |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 326465 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14301 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14301 |  | 0 |  | 312164 |  | 326465 |  | 0
| VENDOR REPS |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 100000 |  | 100000 |  | 0
| CONTINGENCY |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 547484 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 547484 |  | 547484 |  | 0
| RESERVES | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[7 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[7 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL General Provisions | [5 empty] | Capital | 0 |  | 0 |  | 12701255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626946 | 0 | -124695 | 0 | 11949614 | 0 | 12576560 | 0 | 124695
| BOP Procurement | [56 empty] | 0
| PIPE, VALVES, SPEC, & HANGERS |  |  |  |  | Nepco | [5 empty] | 337160 | [45 empty] | 0 |  |  |  | 337160 |  | 337160 |  | 0
| CONDUIT & WIRE |  |  |  |  | Nepco | [5 empty] | 536263 | [45 empty] | 0 |  |  |  | 536263 |  | 536263 |  | 0
| BUS DUCT |  |  |  |  | Nepco | [5 empty] | 520000 | [45 empty] | 0 |  |  |  | 520000 |  | 520000 |  | 0
| DRY XFORMERS & PANELS |  |  |  |  | Nepco | [5 empty] | 30250 | [45 empty] | 0 |  |  |  | 30250 |  | 30250 |  | 0
| OIL FILLED XFORMERS |  |  |  |  | Nepco | [5 empty] | 243060 | [45 empty] | 0 |  |  |  | 243060 |  | 243060 |  | 0
| MOTOR CONTROL CENTER |  |  |  |  | Nepco | [5 empty] | 39943 | [45 empty] | 0 |  |  |  | 39943 |  | 39943 |  | 0
| SWITCHGEAR |  |  |  |  | Nepco | [5 empty] | 1696888 | [23 empty] | 115533 | [21 empty] | 115533 |  |  |  | 1581355 |  | 1696888 |  | 0
| CNTL PANELS & TRMNTN BOX |  |  |  |  | Nepco | [5 empty] | 102314 | [45 empty] | 0 |  |  |  | 102314 |  | 102314 |  | 0
| ELECTRICAL DEVICES |  |  |  |  | Nepco | [5 empty] | 5284 | [45 empty] | 0 |  |  |  | 5284 |  | 5284 |  | 0
| LIGHT POLE & LIGHT FIXTURES |  |  |  |  | Nepco | [5 empty] | 73900 | [45 empty] | 0 |  |  |  | 73900 |  | 73900 |  | 0
| ELEC HEAT TRACE & TEST |  |  |  |  | Nepco | [5 empty] | 33312 | [45 empty] | 0 |  |  |  | 33312 |  | 33312 |  | 0
| SPECIAL SYSTEMS |  |  |  |  | Nepco | [5 empty] | 118356 | [45 empty] | 0 |  |  |  | 118356 |  | 118356 |  | 0
| FIELD MOUNTED INSTRUMENTS |  |  |  |  | Nepco | [5 empty] | 66355 | [45 empty] | 0 |  |  |  | 66355 |  | 66355 |  | 0
| STACK MONITORING |  |  |  |  | Nepco | [5 empty] | 480000 | [45 empty] | 0 |  |  |  | 480000 |  | 480000 |  | 0
| CNTL VALVES & MISC EQUIPMENT |  |  |  |  | Nepco | [5 empty] | 31166 | [45 empty] | 0 |  |  |  | 31166 |  | 31166 |  | 0
| TUBING, TRAV & STANDS |  |  |  |  | Nepco | [5 empty] | 16008 | [45 empty] | 0 |  |  |  | 16008 |  | 16008 |  | 0
| DCS |  |  |  |  | Nepco | [5 empty] | 357625 | [45 empty] | 0 |  |  |  | 357625 |  | 357625 |  | 0
| PUMPS |  |  |  |  | Nepco | [5 empty] | 81500 | [45 empty] | 0 |  |  |  | 81500 |  | 81500 |  | 0
| CONDENSER & AUX EQUIPMENT |  |  |  |  | Nepco | [5 empty] | 50000 | [45 empty] | 0 |  |  |  | 50000 |  | 50000 |  | 0
| FUEL GAS FILTER |  |  |  |  | Nepco | [5 empty] | 70000 | [45 empty] | 0 |  |  |  | 70000 |  | 70000 |  | 0
| PRESSURE REDUCE STAT |  |  |  |  | Nepco | [5 empty] | 330500 | [45 empty] | 0 |  |  |  | 330500 |  | 330500 |  | 0
| MINOR SKID MOUNTED SYSTEMS |  |  |  |  | Nepco | [51 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| TANKS NON-PRESSURIZE |  |  |  |  | Nepco | [5 empty] | 20500 | [45 empty] | 0 |  |  |  | 20500 |  | 20500 |  | 0
| TOTAL BOP Procurement | [5 empty] | Capital | 0 |  | 0 |  | 5240384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115533 | 0 | 0 | 0 | 5124851 | 0 | 5240384 | 0 | 0
Construction
| SITE PREPARATION/IMPROVEMENTS - S | [10 empty] | 1021325 | [45 empty] | 0 |  |  |  | 1021325 |  | 1021325 |  | 0
| UNDERGROUND ELECTRICAL - L | [10 empty] | 490219 | [23 empty] | 3780 | [21 empty] | 3780 |  |  |  | 486439 |  | 490219 |  | 0
| UNDERGROUND ELECTRICAL - M | [10 empty] | 375128 | [23 empty] | 28611 | [21 empty] | 28611 |  |  |  | 346517 |  | 375128 |  | 0
| UNDERGROUND ELECTRICAL - S | [10 empty] | 30000 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 30000 |  | 30000 |  | 0
| UNDERGROUND PIPING - L | [10 empty] | 458520 | [23 empty] | 3169 | [21 empty] | 3169 |  |  |  | 455351 |  | 458520 |  | 0
| UNDERGROUND PIPING - M | [10 empty] | 193150 | [23 empty] | 17185 | [21 empty] | 17185 |  |  |  | 175965 |  | 193150 |  | 0
| UNDERGROUND PIPING - S | [10 empty] | 2100 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 2100 |  | 2100 |  | 0
| CONCRETE - L | [10 empty] | 895918 | [23 empty] | 3445 | [21 empty] | 3445 |  |  |  | 892473 |  | 895918 |  | 0
| CONCRETE - M | [10 empty] | 664866 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 664866 |  | 664866 |  | 0
| SPECIAL CONCRETE - L | [10 empty] | 94439 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 94439 |  | 94439 |  | 0
| SPECIAL CONCRETE - M | [10 empty] | 46881 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 46881 |  | 46881 |  | 0
| STRUCTURAL STEEL - L | [10 empty] | 26528 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 26528 |  | 26528 |  | 0
| STRUCTURAL STEEL - M | [10 empty] | 94700 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 94700 |  | 94700 |  | 0
| ARCHITECTURAL -S | [10 empty] | 70928 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 70928 |  | 70928 |  | 0
| BUILDINGS -S | [10 empty] | 625218 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 625218 |  | 625218 |  | 0
| A/G PIPING - L | [10 empty] | 351722 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 351722 |  | 351722 |  | 0
| A/G PIPING - S | [10 empty] | 0 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| A/G ELECTRICAL - L | [10 empty] | 1515431 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 1515431 |  | 1515431 |  | 0
| A/G ELECTRICAL - S | [10 empty] | 125000 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 125000 |  | 125000 |  | 0
| INSTRUMENTATION - L | [10 empty] | 251258 | [23 empty] | 308 | [21 empty] | 308 |  |  |  | 250950 |  | 251258 |  | 0
| INSTRUMENTATION - S | [10 empty] | 100000 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 100000 |  | 100000 |  | 0
| INSULATION & PAINTING -S | [10 empty] | 587792 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 587792 |  | 587792 |  | 0
| MECHANICAL EQUIPMENT - L | [10 empty] | 1038779 | [23 empty] | 3795 | [21 empty] | 3795 |  |  |  | 1034984 |  | 1038779 |  | 0
| MECHANICAL EQUIPMENT - S | [10 empty] | 2364616 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 2364616 |  | 2364616 |  | 0
| PLANT STARTUP - L | [10 empty] | 554393 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 554393 |  | 554393 |  | 0
| PLANT STARTUP - M | [10 empty] | 149250 | [23 empty] | 0 | [21 empty] | 0 |  |  |  | 149250 |  | 149250 |  | 0
| PLANT STARTUP - S | [10 empty] | 48600 | [23 empty] | 1050 | [21 empty] | 1050 |  |  |  | 47550 |  | 48600 |  | 0
[58 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| TOTAL Construction | [10 empty] | 12176761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61343 | 0 | 0 | 0 | 12115418 | 0 | 12176761 | 0 | 0 | 0
Switchyard
| SWITCHYARD | [10 empty] | 7824800 | [47 empty] | 2055664 |  | 9880464 |  | 9880464 |  | -2055664
| TOTAL SWITCHYARD | [10 empty] | 7824800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055664 | 0 | 9880464 | 0 | 9880464 | 0 | -2055664
| Nepco % Complete | [10 empty] | 0 | [23 empty] | 3651556.55 |  | 0 | [19 empty] | 3651556.55 |  |  |  | -3651557 |  | -0.45 |  | 0.45
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [6 empty] | 0 |  | 0 |  | 37943200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4455378.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4455378.55 | 0 | 1930969 | 0 | 35418790 | 0 | 39874168.55 | 0 | -1930968.55 | 0
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 929800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 77483.3333 |  | 77483.33 |  | 77483.33 |  | 77483.33 |  | 77483.34 |  | 77483.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 464899.9933 |  | 0 |  | 464900.0067 |  | 929800 |  | 0
| NEPCO |  |  |  |  | NEPCO | Capital | 0 |  | 0 |  | 2386700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 198891.6667 |  | 198891.67 |  | 198888.67 |  | 198888.67 |  | 198888.67 |  | 198899 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1193348.3467 |  | 0 |  | 1193351.6533 |  | 2386700 |  | 0
| BASE FEE |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 3066700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3066700 |  | 3066700 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[62 empty] | 0 |  |  |  | 0
| TOTAL OVERHEADS & FEES | [6 empty] | 0 |  | 0 |  | 6383200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 276375 |  | 276375 |  | 276372 |  | 276372 |  | 276372.01 |  | 276382.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1658248.34 |  | 0 |  | 4724951.66 |  | 6383200 |  | 0
ADDERS OUTSIDE EECC SCOPE | [6 empty] | Capital
| Other |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
| TOTAL ADDERS | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT PROJECT COSTS
MOBILIZATION OF O&M
| Mobilization Fee |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 908786 |  | 908786 |  | 0
| EI Hourly billing | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [6 empty] | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 908786 |  | 908786 |  | 0
RESALE HANDLING FEES (.25%) | [5 empty] | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
WATER INTERCONNECT | [5 empty] | ECT | Capital | 400000 |  | 100000 |  | 1500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 38083.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 38083.5 |  | 0 |  | 1461916.5 |  | 1500000 |  | 0
SALES TAX ON EQUIPMENT | [5 empty] | ECT | Capital | 0 |  | 0 |  | 50000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 50000 |  | 50000 |  | 0
SPARE PARTS | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1172731 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1172731 |  | 1172731 |  | 0
LAND ACQUISITION
| Land Option |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 42500 |  | 0 |  | 0 |  | 15000 |  | 10000 |  | 10000 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 42500 |  | 1000 |  | 1000 |  | 43500 |  | -1000
| Title Commitment |  |  |  |  | ECT | Capital |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ECT | Capital |  |  |  |  | 727500 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 932284.26 |  | 128659.6 |  | 8500 |  | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1074443.86 |  | 341944 |  | 0 |  | 1074443.86 |  | -346943.86
| Closing Costs |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [49 empty] | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [6 empty] | 0 |  | 0 |  | 770000 |  | 0 |  | 0 |  | 15000 |  | 10000 |  | 10000 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 932284.26 |  | 128659.6 |  | 8500 |  | 5000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1116943.86 |  | 342944 |  | 1000 |  | 1117943.86 |  | -347943.86
ENVIRONMENTAL PERMITTING
| Air Permitting | [5 empty] | Expense | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Groundwater | [5 empty] | Expense | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Expense |  |  | 0 |  | 450000 |  | 0 |  | 0 |  | 0 |  | 53840.69 |  | 82339.3 |  | 9930.43 |  | 32110.8 |  | 22234 |  | 64176.31 |  | 27327.91 |  | 8595.51 |  | 47810.12 |  | 11305.06 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 359670.13 |  | 0 |  | 90329.87 |  | 450000 |  | 0
| Subtotal Environmental Permitting | [6 empty] | 0 |  | 0 |  | 450000 |  | 0 |  | 0 |  | 0 |  | 53840.69 |  | 82339.3 |  | 9930.43 |  | 32110.8 |  | 22234 |  | 64176.31 |  | 27327.91 |  | 8595.51 |  | 47810.12 |  | 11305.06 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 359670.13 |  | 0 |  | 90329.87 |  | 450000 |  | 0
Power INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  | 5000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 10000 |  | 0 |  | 0 |  | 15000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25000 |  | 0 |  | 4975000 |  | 5000000 |  | 0
GAS INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 946000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 946000 |  | 0 |  | 554000 |  | 1500000 |  | 0
Startup Fuel
| Power Sales | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost | [5 empty] | Capital | 0 |  | 0 |  | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [6 empty] | 0 |  | 0 |  | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 0
INSURANCE DURING CONSTR | [6 empty] | Capital | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 175875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 175875 |  | 0 |  | 24125 |  | 200000 |  | 0
CAPITALIZED SALARIES | [6 empty] | Capital | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  |  |  | 0 |  | 3670.07 |  | 22738 |  | 14946.71 |  | 7606.71 |  | 10911.6 |  | 18233.16 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 78106.25 |  | 0 |  | 121893.75 |  | 200000 |  | 0
DEVELOPMENT EXPENSES
| Salaries | [5 empty] | Expense | 200000 |  | 0 |  | 30000 |  | 0 |  | 0 |  | 14497.18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14497.18 |  | 0 |  | 15502.82 |  | 30000 |  | 0
| Travel Expenses | [5 empty] | Expense | 0 |  | 50000 |  | 150000 |  | 0 |  | 1177.53 |  | 426.75 |  | 2729.26 |  | 1480.06 |  | 2752.75 |  | 11808.68 |  | 12739.96 |  | 11636.6 |  | 3911.51 |  | 3113.56 |  | 7537.43 |  | 3430.47 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 62744.56 |  | 0 |  | 87255.44 |  | 150000 |  | 0
| Consulting - Calpine | [5 empty] | Expense | 0 |  | 24235 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Expense | 400000 |  | -356935 |  | 220000 |  | 0 |  | 0 | [7 empty] | 2287.5 |  | 7317.49 |  | 20400 |  | 875 |  | 26869.6 |  | 11540.02 |  | 22846.65 |  | 28124.79 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 120261.05 |  | 0 |  | 99738.95 |  | 220000 |  | 0
| Enron Generation Comp Costs | [34 empty] | 83333.35 |  | 111707.46 | [19 empty] | 195040.81 |  | 0 |  | 0 |  | 195040.81 |  | -195040.81
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [24 empty] | 75487.01 |  | 65146.92 |  | 18599.24 | [27 empty] | 159233.17 |  | 159233 |  | 0 |  | 159233.17 |  | -159233.17
| TOTAL DEVELOPMENT EXPENSE | [6 empty] | 600000 |  | -282700 |  | 400000 | 0 | 0 | 0 | 1177.53 | 0 | 14923.93 | 0 | 2729.26 | 0 | 1480.06 | 0 | 5040.25 | 0 | 94613.18 | 0 | 98286.88 | 0 | 31110.84 | 0 | 30781.11 | 0 | 14653.58 | 0 | 113717.43 | 0 | 143262.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551776.77 | 0 | 159233 | 0 | 202497.21 | 0 | 754273.98 | 0 | -354273.98
LEGAL EXPENSES
| Vinson & Elkins | [5 empty] | Expense | 0 |  | 294489 |  | 200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 200000 |  | 200000 |  | 0
| Everest Legal | [36 empty] | 252208.46 | [19 empty] | 252208.46 |  | 0 |  | 0 |  | 252208.46 |  | -252208.46
| Other | [5 empty] | Expense | 500000 |  | -300000 |  | 200000 |  | 0 |  | 0 |  | 0 | [7 empty] | 0 |  | 15169.98 |  | 0 |  | 29399.49 |  | 20442.9 |  | 10582.42 |  | 68346.51 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 143941.3 |  | 0 |  | 56058.7 |  | 200000 |  | 0
[10 empty] | 5511 | [47 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [6 empty] | 500000 | 0 | 0 | 0 | 400000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 15169.98 |  | 0 |  | 29399.49 |  | 20442.9 |  | 10582.42 |  | 320554.97 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 396149.76 |  | 0 |  | 256058.7 |  | 652208.46 |  | -252208.46
INTEREST DURING CONSTRUCTION (6.5%) | [6 empty] | Capital | 10922239 |  | 47687 |  | 9897330 |  | 413818 |  | 239841 |  | 375473 |  | 374160 |  | 374175 |  | 479817 |  | 431577.4186 |  | 437225.4821 |  | 445286.6764 |  | 454783 |  | 462626.3155 |  | 491955.341 |  | 516340 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5497078.2336 |  | -174673.4245 |  | 4225578.3418 |  | 9722656.5755 |  | 174673.4245
ECT TOTAL Project Costs | [11 empty] | 23448847 | 0 | 413818 | 0 | 241018.53 | 0 | 405396.93 | 0 | 440729.95 | 0 | 471664.43 | 0 | 525025.68 | 0 | 573248.1086 | 0 | 580523.0521 | 0 | 551485.4264 | 0 | 1502808.93 | 0 | 634977.9055 | 0 | 710648.811 | 0 | 2133337.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9184683.5036 | 0 | 327503.5755 | 0 | 15043916.3718 | 0 | 24228599.8755 | 0 | -779752.8755 | 0
CONTINGENCY | [6 empty] | Capital | 5395729 |  | 67851 |  | 3324152.1 | [46 empty] | 2030320 | -3324152 | 2030320 | 0.1 | 2030320 | 0.1 | 2030320 | 3324152
GRAND TOTAL (without Financing Fees & SWAP) | [11 empty] | 161382953.1 | 0 | 17087218 | 0 | 43642668.53 | 0 | 4696471.93 | 0 | 440729.95 | 0 | 4762739.43 | 0 | 9142692.68 | 0 | 573248.1086 | 0 | 1116780.7521 | 0 | 1496281.3264 | 0 | 1780115.93 | 0 | 1566383.0055 | 0 | 5481999.371 | 0 | 4677967.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96465296.5536 | 2030320 | -689398.4245 | 2030320 | 64680506.9718 | 2030320 | 161145803.5255 | 2030320 | 237149.5745
$/Kw | [63 empty] | 342863.4118
INTEREST SWAP | [6 empty] | Capital | 0 |  | 44922.91 |  | -6078 | [7 empty] | -21556.4 |  | 66478.91 |  | -51000 |  | 0 | [31 empty] | -6077.49 |  | 0 |  | -0.51 |  | -6078 |  | 0
FINANCIAL FEES | [11 empty] | 0 | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | [31 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
Current FIT | [11 empty] | -54879 | [9 empty] | -67129 |  | 12250 |  | -26420 |  | -23945 | [5 empty] | 36835 |  | -36835 | [21 empty] | -105244 |  |  |  | 0 |  | -105244
Grand Total Including SWAP & Financial Fees | [11 empty] | 161321996.1 | 0 | 17087218 | 0 | 43642668.53 | 0 | 4696471.93 | 0 | 419173.55 | 0 | 4762089.34 | 0 | 9103942.68 | 0 | 546828.1086 | 0 | 1092835.7521 | 0 | 1496281.3264 |  | 1780115.93 |  | 1603218.0055 | 0 | 5445164.371 | 0 | 4677967.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96353975.0636 | 2030320 | -689398.4245 | 2030320 | 64680506.4618 | 2030320 | 161034481.5255 | 2030320 | 237149.5745 | 0
Petersburg, IN
LAND | [6 empty] | Expense | 0 |  | 220000 |  | 0 | [5 empty] | 15000 |  | 0 | [37 empty] | 15000 |  |  |  | 0 |  | 15000 |  | 0
CAPITALIZED SALARIES | [6 empty] | Expense | 0 |  | 30000 |  | 0 | [5 empty] | 0 | [39 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
ENVIRONMENTAL PERMITTING | [6 empty] | Expense | 0 |  | 35000 |  | 0 | [5 empty] | 0 |  | 100 | [37 empty] | 100 |  |  |  | 0 |  | 100 |  | 0
DEVELOPMENT EXPENSES | [6 empty] | Expense | 0 |  | 20000 |  | 0 | [45 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
LEGAL EXPENSES | [11 empty] | 0
TOTAL-Petersburg, In | [7 empty] | 0 |  | 305000 |  | 0 |  | 0 |  | 0 |  | 15000 |  | 100 | 0 | 0 | 0 | 0 | [33 empty] | 15100 |  |  |  | 0 |  | 15100 |  | 0
TOTAL INDIANA PLANT COSTS (w/o Financial Fees & SWAP) | [7 empty] | #REF! |  | #REF! |  | 161382953.1 | 0 | 17087218 | 0 | 43642668.53 | 0 | 4711471.93 | 0 | 440829.95 | 0 | 4762739.43 | 0 | 9142692.68 | 0 | 573248.1086 | 0 | 1116780.7521 | 0 | 1496281.3264 | 0 | 1780115.93 | 0 | 1566383.0055 | 0 | 5481999.371 | 0 | 4677967.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96480396.5536 | 2030320 | -689398.4245 | 2030320 | 64680506.9718 | 2030320 | 161160903.5255 | 2030320 | 237149.5745
TOTAL INDIANA PLANT COSTS | [7 empty] | #REF! |  | #REF! |  | 161321996.1 | 0 | 17087218 | 0 | 43642668.53 | 0 | 4711471.93 | 0 | 419273.55 | 0 | 4762089.34 | 0 | 9103942.68 | 0 | 546828.1086 | 0 | 1092835.7521 | 0 | 1496281.3264 | 0 | 1780115.93 | 0 | 1603218.0055 | 0 | 5445164.371 | 0 | 4677967.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96369075.0636 | 2030320 | -689398.4245 | 2030320 | 64680506.4618 | 2030320 | 161049581.5255 | 2030320 | 237149.5745

## Wilton - Nepco Scope Changes
| CHANGE ORDER LOG |  |  |  |  | Lincoln Center
Enron Engineering & Construction
ENA 2000 Peaker Projects
Change Order Number | Description | Originator | Date Initiated | Date Resolved | Owner Status | ENA Major Equipment | NEPCO Reimbursable | NEPCO / EECC Fixed Ovhd | Fixed Fee | TOTAL COST | ENA | Schedule Impact (Days) | Comments and Remarks
Approved
LINCOLN CENTER POWER PROJECT
IL-CO-000-N | Union Adder correction - not included in the memorialized letter. Additionally several million dollars to come, as Union contracts are being understood to include 30-40% in higher benefits and more restrictive work rules over Wheatland and Gleason. Final selection of Morrison and Meade not made until September. Change Order for the additional dollars is currently being worked on, will provide as soon as finished. | NEPCO | 1999-08-11 | 1999-08-11 | $1.2 Approved |  | 1225177 | 0 | 0 | 1225177 | 63385 | 0 | Adjustment for accelerated labor costs Unwarrented Home Office Overhead associated with a Union versus Merit workforce. Amount reduced by -1,161,792 of the original budget
Trend #1/CO #11 | Union Adder, increased Union work rules and added management costs | NEPCO |  |  |  |  | 1865140 |  |  | 1865140 | 1707436 |  | ENA takes exception to the Overhead Charge of $157,704
Trend #2/CO #12 | Union Adder, increased premium time and associated burdens | NEPCO |  |  |  |  | 2415377 |  |  | 2415377 | 0 |  | ENA takes exception with a 70 hours work schedule except in critical path activities. Considering the losss in productivity and the double time rate of pay associated with a 70 work schedule, ENA regards this a diminishing return situation that I sonly exacerbated when worked by the same crafts on an extended basis.
Trend #1/CO #13 | Union Adder, rate differential between actual and budgeted | NEPCO |  |  |  |  | 1992155 |  |  | 1992155 | 1258397 |  | ENA takes exception to the Overhead Charge of $733,758
IL-CO-001-N | Warranty Deduct | NEPCO | 1999-08-11 | 1999-08-11 | Issued for Approval |  | 0 | 0 | 0 | 0 |  | 0 | Included in signed agreement with ENA.
IL-CO-002-N | Increase centerline spacing from 125 ft to 145 ft. Change Order is currently being reworked by Nick Viscount and will be sent to Dave Kristich by 12/11/99 | NEPCO | 1999-08-11 |  | To Be Issued |  | 714015 | 0 | 0 | 714015 | 381799 | 0 | Qty's will be checked, corrected, and resubmitted
IL-CO-003-N IL -Co-004-N | Add evaporative coolers,associated piping and added larger CTG intake structure. Change Order #3 & 4 will be combined with a reduction of about a million dollars. Initial estimate included drilling of well by Nepco, ENA has paid directly. Change Order does not include the cost of the Evaporative Coolers. | NEPCO | 1999-08-11 |  | To Be Issued |  | 3249323 | 0 | 0 | 3249323 | 2125513 | 0 | Update CO to reflect current scope splits & designs
| Revised Change order will be sent to Dave Kristich by 12/11/99 | NEPCO | 1999-08-11 |  | To Be Issued |  | 560292 | 0 | 0 | 560292 | 0 | 0 | Update CO to reflect current scope splits & designs
IL-CO-005-N | Add larger stack with sound attenuation. Additional costs to install foundations, more complex installation for larger more complex stacks. Timing disconnect, design not completed till Aug/Sep, not incorporated into the Original Budget. Change Order is being revised with little change and Gavin Gaul will send to Dave Kristish ASAP. | NEPCO | 1999-08-11 | 1999-10-21 | Issued for Approval |  | 796634 | 0 | 0 | 796634 | 752337 | 0
IL-CO-006-N | Add redundant generator protective relaying. Requirement that came about from a Com Ed meeting in August. Change Order is being revised with little change and Gavin Gaul will send to Dave Kristich ASAP. | NEPCO | 1999-08-11 | 1999-10-21 | Issued for Approval |  | 156452 | 0 | 0 | 156452 | 156452 | 0
IL-CO-007-N | Redesign of switchyard | NEPCO | 1999-08-11 | 1999-08-11 | Issued for Approval |  | 0 | 0 | 0 | 0 |  | 0 | Included in signed agreement with ENA.
IL-CO-008-N | Required GTG laydown area. Stripped Janet Warren's property and replaced with stones. Should have been included in original budget but was left out. Change Order is being revised with little change and Gavin Gaul will send to Dave Kristich ASAP. | NEPCO | 1999-08-11 | 1999-10-21 | Issued for Approval |  | 496034 | 0 | 0 | 496034 | 486308 | 0
IL-CO-009-N | Generator breaker synchronization check relays. Com Ed interconnect scope change. Completed Change Order will be sent to Dave Kristich ASAP. | NEPCO | 1999-08-11 | 1999-10-21 | Issued for Approval |  | 38207 | 0 | 0 | 38207 | 36855 | 0
IL-CO-010-N | Instrumentation changes per M. Dickinson memo dated 7/29/99. GE Scope change required, reduced cost by including in Nepco's scope. Completed Change Order will be sent to Dave Kristich ASAP. | NEPCO | 1999-08-11 | 1999-10-21 | Issued for Approval |  | 67746 | 0 | 0 | 67746 | 61643 | 0
IL-CO-001-E | Pipeline gas interconnect study. Fred Mitro approved. | EECC | 1999-10-25 | 1999-10-25 | Approved |  | 0 | 5000 | 0 | 5000 | 5000 | 0
| Subtotal - Approved |  |  |  | Approved |  | 13576552 | 5000 | 0 | 13581552 | 7035125
| Subtotal - Issued for Approval |  |  |  | Issued for Approval |  | 0 | 0 | 0 | 0
| Subtotal - To Be Issued |  |  |  | To Be Issued |  | 0 | 0 | 0 | 0
| Subtotal - Cancelled |  |  |  | Cancelled |  | 0 | 0 | 0 | 0
Major Equipment
IL-CO-000-T | GE Turbines - Generator Protective Relays | ENA | 1999-02-19 | 1999-02-19 | Approved | 480000 | 0 | 0 | 0 | 480000 | 480000 | 0
IL-CO-001-T | GE Turbines - Change Order No. 1. Added the evaporative coolers and deleted the exhaust stacks from the Turbine contract. | ENA | 1999-09-13 | 1999-09-13 | Approved | 1832000 | 0 | 0 | 0 | 1832000 | 1832000 | 0
IL-CO-001-S | Braden Stacks | ENA | 1999-09-10 | 1999-09-10 | Approved | 9479079 | 0 | 0 | 0 | 9479079 | 9479079 | 0
| Subtotal - Approved |  |  |  | Approved | 11791079 | 0 | 0 | 0 | 11791079 | 11791079
| Subtotal - Issued for Approval |  |  |  | Issued for Approval | 0 | 0 | 0 | 0 | 0
| Subtotal - To Be Issued |  |  |  | To Be Issued | 0 | 0 | 0 | 0 | 0
| Subtotal - Cancelled |  |  |  | Cancelled | 0 | 0 | 0 | 0 | 0
Total Change Orders
[10 empty] | 25372631 | 18826204

## Gleason-Nepco Scope Changes
| CHANGE ORDER LOG |  |  |  |  | Gleason
Enron Engineering & Construction
ENA 2000 Peaker Projects
Change Order Number | Description | Originator | Date Initiated | Date Resolved | Owner Status | ENA Major Equipment | NEPCO Reimbursable | NEPCO / EECC Fixed Ovhd | Fixed Fee | TOTAL COST | Schedule Impact (Days) | Comments and Remarks
GLEASON POWER PROJECT
TN-CO-001-N | Acceleration of GTG2 and GTG3 erection - $1.6 million represents acceleration in schedule for Calvert, does not include Gleason change. Nepco is currently working on the Change Order to include the move to Gleason with the start date of June 1st. Nepco will provide Change Order as soon as finished. | NEPCO | 1999-07-28 |  | To Be Issued |  | 1615799 | 0 | 0 | 1615799 | TBD
TN-CO-002-N | Switchyard Scope Growth- July meeting w/TVA, advised us we needed to use two additional 500 kv breakers above and beyond what was used @ Brownsville. Approx. $1,000,000 - $1,500,000 represents the equipment costs. Nepco is currently working on the Change Order and will provide to ENA as soon as finished. Additionally, preliminary numbers coming from TVA represent an incremental $1,500,000 in communication requirements. | NEPCO | 1999-10-31 |  | To Be Issued |  | 2829700 | 0 | 0 | 2829700 | TBD
TN-CO-001-Td | Westinghouse 501F(d) - Change Order No. 1 | ENA | 1999-07-09 | 1999-07-09 | Approved | 436901 | 0 | 0 | 0 | 436901 | 0
TN-CO-002-Td | Westinghouse 501F(d) - Change Order No. 2 | ENA | 1999-09-22 | 1999-09-22 | Approved | 900 | 0 | 0 | 0 | 900 | 0
TN-CO-001-Tc | Westinghouse 501F(c) - Change Order No. 1 | ENA | 1999-09-20 | 1999-09-20 | Approved | 1099800 | 0 | 0 | 0 | 1099800 | 0
TN-CO-002-Tc | Westinghouse 501F(c) - Compressor Water Wash | ENA | 1999-09-22 | 1999-09-22 | Approved | 16100 | 0 | 0 | 0 | 16100 | 0
TN-CO-002-Tc | Westinghouse 501F(c) - Water Inj Heat Trace | ENA | 1999-09-22 | 1999-09-22 | Approved | 29800 | 0 | 0 | 0 | 29800 | 0
TN-CO-003-Tc | Westinghouse 501F(c) - Bird Screen on Inlet Filter | ENA | 1999-09-22 | 1999-09-22 | Approved | 22900 | 0 | 0 | 0 | 22900 | 0
TN-CO-003-Tc | Westinghouse 501F(c) - Storage Charges | ENA | 1999-09-22 | 1999-09-22 | Approved | 39315 | 0 | 0 | 0 | 39315 | 0
| Subtotal - Approved |  |  |  | Approved | 1645716 | 0 | 0 | 0 | 1645716
| Subtotal - Issued for Approval |  |  |  | Issued for Approval | 0 | 0 | 0 | 0 | 0
| Subtotal - To Be Issued |  |  |  | To Be Issued | 0 | 4445499 | 0 | 0 | 4445499
| Subtotal - Cancelled |  |  |  | Cancelled | 0 | 0 | 0 | 0 | 0
| Total Change Orders - GLEASON |  |  |  | Total | 1645716 | 4445499 | 0 | 0 | 6091215
NEPCO reimbursable costs reviewed
ENA has APPROVED | [6 empty] | 0
Change Order To Be Issued | [6 empty] | 4445499
Increase in Forecast that is not a scope change | [6 empty] | 0

## Wheatland -Nepco Scope Changes
| CHANGE ORDER LOG |  |  |  |  | Wheatland
Enron Engineering & Construction
ENA 2000 Peaker Projects
Change Order Number | Description | Originator | Date Initiated | Date Resolved | Owner Status | ENA Major Equipment | NEPCO Reimbursable | NEPCO / EECC Fixed Ovhd | Fixed Fee | TOTAL COST | Schedule Impact (Days) | Comments and Remarks
WHEATLAND POWER PROJECT
IN-CO-001-N | Schedule Acceleration - Unit #3 by June 1 and #4 by June 9th. Nepco is working to achieve full load by June 1st or earlier. Will provide detailed Change Order when complete. | NEPCO | 1999-08-16 |  | To Be Issued |  | 3405348 | 0 | 0 | 3405348 | TBD
IN-CO-002-N | Switchyard Scope Growth - Allows for dual interconnect capabilities. Additional Cinergy, IPL requirements, diesel, extra tower, does not include full set of spare breakers due to ENA design. Nepco is working on details to the Change Order and will provide Dave Kristich when finished. | NEPCO | 1999-10-31 |  | To Be Issued |  | 2055664 | 0 | 0 | 2055664 | TBD
IN-CO-000-T | Westinghouse Turbines - Org. Price Adjustment | ENA | 1999-07-01 | 1999-07-01 | Approved | -100000 | 0 | 0 | 0 | -100000 | 0
IN-CO-001-T | Westinghouse Turbines - Change Order No. 1 | ENA | 1999-07-07 | 1999-07-07 | Approved | 353801 | 0 | 0 | 0 | 353801 | 0
IN-CO-002-T | Westinghouse Turbines - Change Order No. 2 | ENA | 1999-08-26 | 1999-08-26 | Approved | -22200 | 0 | 0 | 0 | -22200 | 0
| Subtotal - Approved |  |  |  | Approved | 231601 | 0 | 0 | 0 | 231601
| Subtotal - Issued for Approval |  |  |  | Issued for Approval | 0 | 0 | 0 | 0 | 0
| Subtotal - To Be Issued |  |  |  | To Be Issued | 0 | 5461012 | 0 | 0 | 5461012
| Subtotal - Cancelled |  |  |  | Cancelled | 0 | 0 | 0 | 0 | 0
| Total Change Orders - WHEATLAND |  |  |  | Total | 231601 | 5461012 | 0 | 0 | 5692613
NEPCO reimbursable costs reviewed
ENA has APPROVED | [6 empty] | 0
Change Order To Be Issued | [6 empty] | 5461012
Increase in Forecast that is not a scope change | [6 empty] | 0

## Nepco Summary
Comparison of Actuals to Payment based on Cash Curves
Wilton
|  | 1999-05-01 | 1999-06-01 | 1999-07-01 | 1999-08-01 | 1999-09-01 | 1999-10-01 | 1999-11-01 | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01 | 2000-08-01
| Forecasted Monthly Cost | 14.024 | 57.518 | 86.16 | 175.037 | 244.47 | 2454.091 | 7201.369 | 11765.741 | 13662.535 | 10563.122 | 5404.108 | 3274.711 | 2750.626 | 773.387 | 0 | 0
| Cumulative Monthly Cost | 14.024 | 71.542 | 157.702 | 332.739 | 577.209 | 3031.3 | 10232.669 | 21998.41 | 35660.945 | 46224.067 | 51628.175 | 54902.886 | 57653.512 | 58426.899 | 58426.899 | 58426.899
| Cumulative Percent | 0.02% | 0.1224% | 0.2699% | 0.5695% | 0.9879% | 5.188% | 17.51% | 37.65% | 61.04% | 79.11% | 88.36% | 93.97% | 98.68% | 100% | 100% | 100%
| Actuals by Month | 1999-10-01: 865.389; 1999-11-01: 3623.545
| Actuals to Date |  |  |  |  | 0 | 865.389 | 4488.934 | 4488.934 | 4488.934 | 4488.934 | 4488.934 | 4488.934 | 4488.934 | 4488.934 | 4488.934 | 4488.934
[6 empty] | 0% | 1.481% | 7.683% | 7.683% | 7.683% | 7.683% | 7.683% | 7.683% | 7.683% | 7.683% | 7.683% | 7.683%
Gleason
| Forecasted Monthly Cost |  |  | 25.337 | 65.208 | 169.726 | 1006.954 | 4786.807 | 6212.153 | 7622.536 | 7064.893 | 5584.038 | 3429.411 | 2821.781 | 1980.434 | 970.073 | 2.05
| Cumulative Monthly Cost | 0 | 0 | 25.337 | 90.545 | 260.271 | 1267.225 | 6054.032 | 12266.185 | 19888.721 | 26953.614 | 32537.652 | 35967.063 | 38788.844 | 40769.278 | 41739.351 | 41741.401
| Cumulative Percent | 0.02% | 0% | 0.0607% | 0.2169% | 0.6235% | 3.036% | 14.5% | 29.39% | 47.65% | 64.57% | 77.95% | 86.17% | 92.93% | 97.67% | 100% | 100%
| Actuals by Month | 1999-09-01: 0; 1999-10-01: 709.427; 1999-11-01: 1919.807
| Actuals to Date |  |  |  |  | 0 | 709.427 | 2629.234 | 2629.234 | 2629.234 | 2629.234 | 2629.234 | 2629.234 | 2629.234 | 2629.234 | 2629.234 | 2629.234
[6 empty] | 0% | 1.7% | 6.299% | 6.299% | 6.299% | 6.299% | 6.299% | 6.299% | 6.299% | 6.299% | 6.299% | 6.299%
Wheatland
| Forecasted Monthly Cost | 0 | 0 | 33 | 105.708 | 113.539 | 674.691 | 3528.01 | 5746.785 | 7528.088 | 6944.889 | 5046.001 | 3298.928 | 2936.617 | 1317.172 | 665.24 | 4.1
| Cumulative Monthly Cost | 0 | 0 | 33 | 138.708 | 252.247 | 926.938 | 4454.948 | 10201.733 | 17729.821 | 24674.71 | 29720.711 | 33019.639 | 35956.256 | 37273.428 | 37938.668 | 37942.768
| Cumulative Percent | 0% | 0% | 0.08697% | 0.3656% | 0.6648% | 2.443% | 11.74% | 26.89% | 46.73% | 65.03% | 78.33% | 87.02% | 94.76% | 98.24% | 99.99% | 100%
| Actuals by Month | 1999-09-01: 0; 1999-10-01: 803.822; 1999-11-01: 1497.095
| Actuals to Date |  |  |  |  | 0 | 803.822 | 2300.917 | 2300.917 | 2300.917 | 2300.917 | 2300.917 | 2300.917 | 2300.917 | 2300.917 | 2300.917 | 2300.917
[6 empty] | 0% | 2.119% | 6.064% | 6.064% | 6.064% | 6.064% | 6.064% | 6.064% | 6.064% | 6.064% | 6.064% | 6.064%
TOTALS
| Forecasted Monthly Cost | 14.024 | 57.518 | 144.497 | 345.953 | 527.735 | 4135.736 | 15516.186 | 23724.679 | 28813.159 | 24572.904 | 16034.147 | 10003.05 | 8509.024 | 4070.993 | 1635.313 | 6.15
| Cumulative Monthly Cost | 14.024 | 71.542 | 216.039 | 561.992 | 1089.727 | 5225.463 | 20741.649 | 44466.328 | 73279.487 | 97852.391 | 113886.538 | 123889.588 | 132398.612 | 136469.605 | 138104.918 | 138111.068
| Cumulative Percent | 0.01015% | 0.0518% | 0.1564% | 0.4069% | 0.789% | 3.784% | 15.02% | 32.2% | 53.06% | 70.85% | 82.46% | 89.7% | 95.86% | 98.81% | 100% | 100%
| Actuals by Month |  |  |  |  | 0 | 2378.638 | 7040.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actuals to Date |  |  |  |  | 0 | 2378.638 | 9419.085 | 9419.085 | 9419.085 | 9419.085 | 9419.085 | 9419.085 | 9419.085 | 9419.085 | 9419.085 | 9419.085
[6 empty] | 0% | 1.722% | 6.82% | 6.82% | 6.82% | 6.82% | 6.82% | 6.82% | 6.82% | 6.82% | 6.82% | 6.82%
[6 empty] | Amount Paid |  | 19947.872 | 30664.946
|  |  | Difference between Payment and Prior Month Actuals |  |  |  |  | 10528.787 | 21245.861