## Sheet1
ENRON TRANSPORTATION SERVICES
2000 Goals and Objectives
Presented to the Enron Board of Directors
Continue Florida Gas expansion by completing Phase IV construction, obtaining favorable
Preliminary Determination and Environmental Impact Statement on Phase V and receiving
market support for Phase VI. Obtain final FERC certificate for Northern Border's Project 2000
and place in service Transwestern's Gallup Expansion by the 2nd quarter.
Phase IV completed necessary construction to initiate testing for FP&L on time and under budget.
Phase V statement received on November 21, 2000.
Phase VI negotiations continue for market support. However, there is some market uncertainty as a
result of El Paso's sale of their planned line into Florida to Duke.
Northern Border's Project 2000 FERC certificate has been obtained.
Transwestern's Gallup Expansion went into service on May 1, 2000.
Close accretive acquisitions of $100 million and $150 million respectively for EOTT and Northern Border.
NBPL purchased Bighorn Gas Gathering, EMS Gas Gathering, interests in Fort Union Gathering and
Lost Creek Gas Gathering. Also in progress, Powder River Basin expansion of Bighorn Gas Gathering.
EOTT ?
Divest of Enron's Clean Fuels business.
We have worked closely with Corporate Development and ETS Business Development to solicit and
and provide data to potential interested parties for all or part of the Clean Fuels facilities. Discussions
were held with several companies. The book value of these assets is $220 million, and no one
was interested in purchasing any of these assets for more than a nominal value. As a result, all offers or
potential offers would have resulted in a substantial write-off for Enron.