## Sheet1
ENRON CLEAN FUELS
FINANCE & ACCOUNTING
DEPARTMENTAL GOALS FOR 2000
Goal |  | Goal | Stretch | Status
1. Complete the development of the Mont Belvieu cost process |  | 2000-06-30 | 2000-04-30 | The cost analysis for the natural gas business is substantially
complete. Normal Butane and one other product are expected
to be complete in the second quarter. All will be completed this
year. We will set up a demonstration for J. Prentice.
2. Negotiate with taxing & appraisal authorities to ensure ad valorem |  |  |  | The valuation of Clean Fuels' facilities is not complete yet, but
| taxes for all three facilities is below $2.3 million. | $2.3MM | $2.1MM | it appears that we will meet this goal assuming no material
impact from the Morgan's Point protest.
3. Coordinate Clean Fuels' smooth transition to SAP, including: |  |  |  | This process is going fairly well, but is demanding more time
| * Participation in design process | 2000-07-01 | 2000-07-01 | than originally expected. T. Meers is acting in a coordinating
| * Clean up & conversion of MSA data | 2000-06-30 | 2000-05-30 | role for Clean Fuels. I am involved with various accounting
| * Adequate training | 2000-07-31 | 2000-07-15 | issues for GPG. Sign-off with exceptions has taken place
| * Implementation | 2000-07-01 | 2000-07-01 | and training schedules are being developed. Data clean up
| * Report development | 2000-12-31 | 2000-09-30 | is on schedule for conversion in May/June.
4. Manage earnings to Plan levels. Contribute to meeting earnings |  |  |  | First quarter earnings were at targeted level and we were able
| through innovation, efficiencies and other appropriate | IBIT | IBIT | to manage costs to provide upside for second quarter. Current
| financial/accounting efforts. | $(13.3)MM | >$(13.3MM) | Estimate forecasts that we will hit our annual target if margins
hold.
5. Continue to work with ENA to eliminate intercompany imbalances |  |  |  | The elimination of intercompany balances is part of the SAP
| and implement Corp. policy with SAP | 2000-09-30 | 2000-07-30 | clean up. Our records are in good shape; however some
imbalances remain because ENA subsidiary systems
disagree with booked amounts. We are working toward a
solution when SAP comes up by enforcing Corporate policy.
Goal |  | Goal | Stretch | Status
6. Collect any outstanding insurance claims and submit any new claims |  |  |  | 11/97 MTBE Outage claim was finalized in 1999. We have
| within aggressive time frames. |  |  | been calling regularly, but don't expect proceeds until late 2nd
quarter or 3rd quarter at earliest. Majority of previous claims
have been collected. Worked with the plant on the 12/99
outage and boiler failure. It does not appear that there will be a
claim on the earlier outage and we are still evaluating the later
event.
7. Provide data and financial analyses internally and externally, when |  |  |  | We have provided support and analysis on several special
| appropriate, to support various plant initiatives. |  |  | projects for the two plants, including possible syngas production
at Pasadena and MTBE stranded cost recovery.
8. Strengthen planning procedures & models to provide earlier review |  |  |  | Cash forecasting models are being enhanced. In addition,
| and better coordination between Accounting & Operations |  |  | the preliminary Plan calendar calls for an early reconciliation
effort between M. Diedrich and Operations. Expectations are
for enhanced cooperation between the two groups.
9. Develop more "user friendly" Capital Expenditure Report |  | 2000-04-30 | 2000-03-31 | Several drafts have been looked at. The latest was issued as
March's report, but several questions remain. Working with
D. Pratt on this.
10. Manage my department, within budget, at below approved headcount. |  |  |  | On target.