## 2001Work
Project Number | Project Name | Active or Inactive | Study Type | Est Level A or B | P/L | Requestor | Planner Initials | Customer | Date Project Received | Estimated Completion Date | Date of Reponse | Level A Cost Est. Amount | Project Description and Comments on Status | Level B Cost Est. Amount | Engr Release Date | Work Order | Bid Release Date | Project Let Date | Construction Start Date | In-Service Date | Other Comments (Eng. & Constr.)
West01001 | Burdett OFS Processing Bypass | I | O | A | NNG | John Sturn | GR |  | 2001-04-25 |  | 2001-05-18 |  | Provide a level A cost estimate for a control valve installation to divert Burdett line gas aay from Bushton processing plant.
West01002 | PowerTex Lateral Acquisition | I | P | A | NNG | Mike Stage | EF |  | 2001-02-05 | 2001-02-09 | 2001-02-09 |  | Provide capacity analysis and compression requirements of PowerTex lateral off of NNG for consideration of acquisition.
West01003 | Oneok Bushton Processing Plant Shutdown | I | O |  | NNG | Steve January | EF |  | 2000-12-27 | 2001-01-15 | 2001-01-28 |  | Provide technical support to determine gas quality to Market zone in event of Bushton processing shutdown. Results would require curtailment of 200 MMcfd production in Anadarko Region to prevent liquid formation in Market Zone.
West01004 | 2000 FERC 567 Filing | I | M |  | TW | Bret Fritch | EF |  | 2001-04-23 |  | 2001-05-15 |  | Prepare volume and design data for FERC filing report for the year 2000
West01005 | INGAA | I | M |  | TW | T. Boss/INGAA | GR | INGAA | 2001-05-07 |  | 2001-06-08 |  | Data requested to indicate capacity reduction due to pipe line inspection (hydrostatic, inline inspection and direct assessment testing) on the TW system.
West01006 | Topock Lateral | I | P | A | TW | Jeff Fawcett/Kim Watson | GR |  |  |  | 2001-06-01 |  | Provide pressures and flows at key delivery points based on various assumptions.
West01007 | Beaver Co. #11 | A | P | B | NNG | Steve Weller | GR | Duke | 2001-05-10 | 2001-06-27 |  |  | Provide a level B estimate for facility modifications required to allow Duke to increase deliveries into NNG.
West01008 | Hodgeman Co., Kansas Tap | A | P | B | NNG | Steve Herber | GR | Producer | 2001-06-07 | 2001-06-29 | 2001-07-16 | 20000 | Provide a level B estimate for a new tap and side valve for 5 MMcfd in Hodgeman Co., Kansas | 60000
West01009 | Spraberry | A | O |  | NNG | Penny McCarren | GR |  | 2001-06-12 | 2001-06-26 |  |  | Look at impact on throughput if units #6, 7, 11 and 12 are placed in PHFFU.
West01010 | Emergency Response Program | A | M |  | TW/FGT | Houston Planning Team | GR | GC/Operations |  | 2001-07-15 |  |  | Develop procedure for responding to a pipeline emergency.
West01011 | TW/ Agave 25 mmcf/d interconnect at discharge side of Atoka-2. | A | P | A | TW | Kim Watson | MA | Agave | 2001-06-04 | 2001-06-12 | 2001-06-12 |  | A level A scope /cost to tie Agave's Aid State to Atoka-2 Discharge.
West01012 | TW/ Agave 100 mmcf/d interconnect | A | P | A | TW | Kim Watson | MA | Agave | 2001-06-04 | 2001-06-12 | 2001-06-12 |  | Tie Agave new Line to TW-36" mainline near Atoka-2/ 24" mainline in Eddy County, NM.
West01013 | TW / Onoek existing interconnect in Ward Co,TX | A | P | B | TW | Kevin Hyatt | MA | Oneok | 2001-05-15 | 2001-07-01 |  |  | Make the existing interconnect bi-directional
West01014 | TW/ Conoco in Lea Co.,NM | A | P | A | TW | Michelle Loaky | MA | Conoco | 2001-06-13 | 2001-06-20 | 2001-06-20 |  | Oneok is installing a 12" Ultrasonic measurement. TW is installing EFM.
West01015 | Calypso pipeline | A | P |  | ENRON | Alice Weekley | MA | Enron Global Marketing LLC | 2001-02-01 |  |  |  | FERC filing requirements for 97 miles of 24" from LNG plant in Bahama to Florida.
West01016 | NNG/ Dynergy at Eunice | A | P | A | NNG | Steve Herber | MA | Dynergy | 2001-06-01 | 2001-05-15 | 2001-05-22 |  | Loop the existing 3.5 miles of 6" with 8".
West01017 | TW/ Questar 130 mmcf/d interconnect | I | P | A | TW | Kevin Hyatt | MA | Questar | 2001-05-01 | 2001-05-16 | 2001-05-16 |  | A level A cost to tie Questar to TW in Kingman, AZ.
West01018 | TW/ PNM Power Plant in Belen, NM (70 mmc/d) | I | P | A | TW | Lorraine Lindberg | MA | PNM | 2001-03-02 | 2001-05-13 | 2001-05-13 |  | Lay 1.5 mile of pipe to deliver up to 70 mmcf/d to PNM plant.
West01019 | NGPL Eddy I/C Bi-directional | A | P | A | TW | Lorraine Lindberg | PT | NGPL | 2001-05-15 | 2001-08-01 |  |  | NGPL ownes current delivery meter off TW. NGPL will install an USM to deliver to TW 60-65 mmcfd. TW will piggy back flow computer.
West01020 | Matagorda 686 Crane refurbishment | I | P | A | NNG | Bob Burleson | PT |  | 2001-02-01 | 2001-05-01 | 2001-05-01 |  | Cost estimate from Matec to rebuild the Sea King 1700 Crane on Comp. Platform. E&C Lafayette
West01021 | Subsea suction/discharge bypass Mat. Is. 686 | I | P | A | NNG | Bob Burleson | PT |  | 2001-02-01 | 2001-05-01 | 2001-05-01 |  | Oceanerring quote for Suc/Dis 24" jumper line at MI 686. E&C LaFayette
West01022 | Morton Co. #1 Compressor Station | A | P | A | NNG | Penny McCarren | EF | OXY | 2001-05-29 | 2001-06-29 |  |  | Determine compression capability at zero psig suction pressure. Cost estimate for piping mods, filtration and cooling.
West01023 | ENA-Flagstaff Delivery | A | P | A | TW | Kevin Hyatt | GR | ENA | 2001-05-01 | 2001-06-29 |  |  | Evaluate capacity of 6" Flagstaff Lateral to determine if capacity available for proposed 12-15 MMcfd delivery to ENA for gas fired GenSet. Provide cost estimates for tap and measuring facilities.
West01024 | Panhandle Lateral Liquids Issue | A | O |  | TW | Rich Jolly | EF | Agave | 2001-06-13 | 2001-07-13 |  |  | Determined that liquids being produced in lateral due to Agave Red Bluff/Bitter Lakes gas quality. Propose facility mods and cost estimates to remediate gas quality to eliminate liquid production in pipeline
West01025 | Pemex - TransPecos Pipeline | A | P | A | TW,NNG | Jeff Fawcett/Kim Watson | EF | Pemex, KinderMorgan | 2001-04-18 | 2001-05-23 | 2001-05-23 |  | Provide design scope and cost estimates for new pipeline(176 mi.), compression(14000HP), and interconnect facilities (5 ea. UGM) to provide 250 and 350 MMcfd to Pemex near Elpaso, TX. Proposal would be a 50/50 joint venture with KinderMorgan
West01026 | TW Red Rock Expansion | A | P | B | TW | Lorraine Lindberg | EF |  | 2001-02-01 |  |  |  | Install new compression at TW Stations 1, 2, 3 & 4 for incremental 150 MMcfd to Ca. |  |  |  |  | 2001-06-21 | 2001-09-01 | 2001-06-01 | Project reduced to a 3 unit option @ CS 1, 2, & 3 on 6/19/01 with fourth unit to follow TBA by June 30 depending upon awarded contracts.
West01027 | Williams Beaver Co. Bi-directional Interconnect | A | P | A | NNG | Steve Weller/Mike Stage | EF | Williams FS | 2001-05-18 | 2001-06-08 | 2001-06-08 |  | Provide flow studies and cost estimate for a 200 MMcfd bi-directional interconnect with WFS in Beaver County to receive gas into the C line and deliver Gas from the D line on Beaver CS discharge. | [7 empty] | Cost estimates issued with qualification that flow study is required
West01028 | EES Gallup Powergen | A | P | B | TW | Kevin Hyatt | RM | EES | 2001-05-04 | 2001-07-06 |  |  | Mulitple 2 Mw units to be moved around quickly. Gallup the first on TW. Waiting for Engineering to complete the cost estimate.
West01029 | Unocal Storage - Keystone | A | P | B | TW | Kevin Hyatt | RM | Unocal | 1999-06-11 | 1999-12-01 | 1999-12-01 |  | Project reopened again in June, 2001. Storage field would tie to both TW and NNG.
West01030 | Ameremex Bloomfield | A | P | B | TW | Lorraine Lindberg | RM | Ameremex | 2000-04-02 | 2001-08-01 |  |  | Supply gas to Energy Farm's Ameremex plant. Still awaiting release for Ameremex.
West01031 | Elm Ridge Resources - La Plata | A | P | B | TW | Lorraine Lindberg | RM | Elmridge Rec | 1998-02-01 | 1998-05-01 | 1998-05-01 |  | Project reopened in 2001. Elm Ridge requesting larger flow (20 MMcf/d). Waiting for Engineering estimate to complete work started in 1999.
West01032 | Elpaso Window Rock | A | P | A | TW | Kim Watson | RM | Elpaso | 2001-06-15 |  |  |  | Provide cost estimate to install pressure tap for Elpaso to read TW pressure
West01033 | Sun Devil Project - Phoenix AZ | A | P | A | TW | Kevin Hyatt | RM |  | 2001-06-07 |  | 2001-07-10 |  | Provide flow studies, scope and cost estimates for 400 MMcfd expansion project to flow San Juan Basin gas to Phoenix for gas fired electric generation.
West01034 | TW San Juan Lateral and ML/LL MAOP Uprates | A | O | A | TW | Max Brown /David Johnson | EF |  | 2001-07-02 | 2001-07-06 | 2001-07-06 |  | Provide capacity evaluations for considering expanxions via MAOP uprates on ML/LL and San Juan Lateral
West01035 | Westar Diamond and Maxus Moore Co. I/C | A | P |  | NNG | Jo Williams | EF |  | 2001-07-09 | 2001-07-10 | 2001-07-10 |  | Confirm capacity volumes for subject meters for PRA filing
West01036 | Relocate NNG Gray I/C on P3 Suction | A | P | B | NNG/TW | Jo Williams/Kim Watson | EF |  | 2001-03-15 |  | 2001-05-15 | $1.3M | Relocate existing TW/NNG Gray I/C to TW's P3 suction via new tap, 1.75 mi of pipeline, and controls | $1.46M
West01037 | Latitute & Longitude for TW active POI's | A | P |  | TW | Kim Watson | PT | Enron IT | 2001-07-11 | 2001-07-13 | 2001-07-13 |  | Calculate Lat/Longs on 65 TW POI's missing from the Pipeline Profile Map and have to IT before 7/15/01 implementation signoff date.
West01038 | New well connect in Roger Mills, Okla | A | P |  | TW | Bob Burleson | PT | Producer | 2001-07-12 | 2001-07-16 | 2001-07-16 |  | Find an exisitng tap on Leedy Lat into Sec. 30, T16N, R21W Roger Mills, OK to receive 15 mmcfd for new wells.
West01039 | West Texas Lateral - NNG Halley Capacity | A | P |  | TW/NNG | Kim Watson | EF/MA |  | 2001-07-12 | 2001-07-18 |  |  | Determine firm sustainable capacity that TW can be receive at the NNG Haley POI. Main constraint will be pressure requirements at deliveries south of WT-2
West01040 | Torch-Buena Vista Field, Bakersville CA | A | P | A | EOTT | Rick Sudermann | GR | Torch | 2001-07-16 | 2001-07-20 |  |  | Provide Level A estimate for Amine Treating facilities for 10 MMcfd LNG expansion.
West01041 | EPFS - Blanco Plant and Chaco Plant I/C | A | P | A | TW | Lorraine Lindberg | RM | EPFS | 2001-08-02 |  |  |  | Provide scope an cost estimates for interconnects with EPFS at subject plants on San Juan Lateral
West01042 | Southern Trails Study | A | P | A | TW | Kim Watson | MA | Questar | 2001-08-07 |  |  |  | Perform pipeline study to determine viability of partnership or acquisition of system for TW benefit
West01043 | TW/Conoco Power Plant (Attoka #1) | A | P | A | TW | Michelle Lokay | MA | Conoco | 2001-08-06 |  |  |  | Provide cost estimate for interconnect facilities to supply power plant fuel of 80 MMcfd
West01044 | Caithness Big Sandy | A | P | A | TW | Kim Watson | RM | Caithness | 2001-06-01 |  | 6/31/01 |  | Provide cost estimates for 90 MMcfd I/C to supply fuel for power generation just downstream of Sta. 1
West01045 | CAS Pipeline Profile Dashboard | A | P |  | TW | EDS/Kim Watson | PF | Enron | 2001-04-01 | 2001-07-01 |  |  | Provide support to development of pipeline profile of capacity based upon CAS data. Intranet tool used for viewing system capacity and or constraints
West01046 | Unsubscribed Capacity Report | A | P |  | TW | EDS/Lindy Donohoe | PF/EF | EnroN | 2001-08-01 | 2001-08-10 |  |  | Provide support to EDS for development of EBB capacity reports basedCAS data. Intranet tool used for viewing system capacity and or constraints
Note on A1: Project Number will be unique for each company and start with: NNG2001001 TW2001001 FGT2001001
Note on B1: Enron: Name that most closest identifies the project to the rest of the Company.
Note on C1: Enron: Active means that some response is being worked on. Inactive means that response is completed and nothing else is required until further requested.
Note on D1: P = Planning study for Marketing O = Operations study M = Management study E = Released to Engineering
Note on E1: Estimate for project. Level A +/- 30% Level B +/- 10%
Note on G1: The name of the primary internal customer for whom work is being performed.
Note on H1: The initials of the Planner who has taken the lead on the project.
Note on I1: The name of the primary external customer for whom work is being performed.
Note on J1: Show date project was received by Planning Coordinator
Note on K1: Show the date the project is to be completed.
Note on L1: Show date that repsonse was provided to requestor.
Note on P1: Date that project was released from Planning to Engineering for construction.
Note on Q1: Work Order Number assigned to project. Put in field once all approvals have been received.
Note on R1: The date that Engineering sent bids out to contractors.
Note on S1: Date that project is awarded to contractor from bid. If project is T&M then put date that contractor gets project.
Note on T1: Date that construction is to start.
Note on U1: Date that project is ready to flow gas to customer.