## April - May
SAN JUAN AREA ANNUAL OUTAGE MEETING SUMMARY
MARCH 7, 2002
April, 2002 |  |  |  | May, 2002
|  |  | Affected Vol. |  |  | Affected Vol.
| Date | Location | (MMcf/d) | Date | Location | (MMcf/d)
TW | 2 - 5 | LaPlata | 500 | 15 | San Juan outage D/R | 625
| 8 - 10 | Bloomfield | 225 | 2 - 6 | Sta. 8 - 7 Excavations | ?
| 11 - 12 | Bisti | 150 | 8 - 18 | Sta. 5-4 Excavations | ?
| 12 - 13 | Gallup | 150 | 19 - 24 | Sta. 7-6 Excavations | ?
El Paso | 15 - 19 | Seligman ESD | 100 | 1 | Williams C | 200
| 17 - 19 | L1300 Dummy BWA-LAG | 500 | 14 | L1208 DK-LP | 360
| 22 | Leupp | 150 | 14 | Bondad | 585
| 23 | L1300 Vcity - BW | 500 | 14 | Gallup | 250
| 30 | Williams C | 200 | 16 - 17 | L1208 | 150
|  |  |  | 21 | L1208 | 150
WFS | 8 - 9 | Kutz | 55 | 7 - 8 | Milagro | 420
|  |  |  | 14 - 15 | Ignacio | 450
PNM | None Scheduled |  |  | 5 | Rio Puerco | 40
|  |  |  | 21 | Rio Puerco | 40
|  |  |  | 29 | Rio Puerco | 40
EPFS | 17 -19 | Chaco (Delete) | 450-500
Burlington | None Scheduled

## June - July
SAN JUAN AREA ANNUAL OUTAGE MEETING SUMMARY
MARCH 7, 2002
June, 2002 |  |  |  | July, 2002
|  |  | Affected Vol. |  |  | Affected Vol.
| Date | Location | (MMcf/d) | Date | Location | (MMcf/d)
TW | None Scheduled |  |  | None Scheduled
El Paso | 2 - 28 | Leupp Station | 150 | 8 | Caprock ESD | 70
| 15 - 16 | L1204 Window Rock L/R | 200 | 10 | Lincoln ESD | 90
| 18 | LPC - FLG | 150 | 15 - 31 | Pecos River PLC | 250
| 21 | L1208 V31 - FLG | 100
| 22 | L1204 L/R Vcity-WRA | 200
| 24 - 25 | L1204 FLG-WMC | 104
| 26 | White Rock B ESD | 157
| 27 | L1204 L/R NAV-DLK | 300
| 28 | Window Rock A ESD | 300
WFS | None Scheduled |  | 55
PNM | 7 | X-37 Line | 40
EPFS | 24 -28 | Blanco/Conoco | 425
Burlington | 25 | Val Verde | 50

## August - September
SAN JUAN AREA ANNUAL OUTAGE MEETING SUMMARY
MARCH 7, 2002
August, 2002 |  |  |  | September 2002
|  |  | Affected Vol. |  |  | Affected Vol.
| Date | Location | (MMcf/d) | Date | Location | (MMcf/d)
TW | None Scheduled |  |  | None Scheduled
|  |  |  | Possible LaPlata & Bisti L/R |  | 705/850
El Paso | 1 - 5 | Pecos River PLC | 250 | 10 | Rio Vista ESD | 150
| 5 or 8 | Laguna ESD | 80 | 11 | Rio Vista DOT | 100
| 14 | Navajo ESD | 280 | 14 | L1301 L/R CRK-V2 | 650
| 11 - 16 | Navajo 2C Hot Gas Path | 230 | 15 | Caprock Piping | 80
| 19 - 31 | Flagstaff Maint. | 80
WFS | None Scheduled |  |  | 10 - 11 | Kutz | 30
PNM | 31 | Rio Puerco | 20 | 5 | Rio Pueerco | 20
|  |  |  | 26 | Rio Pueerco | 20
EPFS | None Scheduled |  |  | 22-25 | Waha Plant (Monahan's Area)
Burlington | None Scheduled |  |  | None Scheduled

## October - November
SAN JUAN AREA ANNUAL OUTAGE MEETING SUMMARY
MARCH 7, 2002
October, 2002 |  |  |  | November, 2002
|  |  | Affected Vol. |  |  | Affected Vol.
| Date | Location | (MMcf/d) | Date | Location | (MMcf/d)
TW | None Scheduled |  |  | None Scheduled
| Possible LaPlata & Bisti L/R |  | 705/850 | Possible LaPlata & Bisti L/R |  | 705/850
El Paso | 1 - 21 | Hackberry 1 Regenerator | 70 | 3 - 19 | Mojave Topock PLC | 200
WFS | None Scheduled |  |  | None Scheduled
PNM | None Scheduled
EPFS | None Scheduled
Burlington | None Scheduled

## December
SAN JUAN AREA ANNUAL OUTAGE MEETING SUMMARY
MARCH 7, 2002
December, 2002
Affected Vol.
| Date | Location | (MMcf/d)
TW | None Scheduled
El Paso | None Scheduled
WFS | None Scheduled
PNM | None Scheduled
EPFS | None Scheduled
Burlington | None Scheduled