## Original 2002 capital slide
2002
Production |  | General
Round Butte - Replace Runners Unit #2 | 1917 | Mobile Communication (Radio) Improvements | 5543
Round Butte - Replace Runners Unit #3 | 1836 | Purchase/Retire Vehicles & Power Op. Equip. | 5195
Pelton-Round Butte Fish Passage | 1424 | Network Meter Reading | 4172
Colstrip | 5494 | Distributions Operations Center | 1500
Other | 12700 | Other | 13398
Total Production | 23371 | Total General | 29808
Bull Run - Decommissioning |  | Intangible
Bull Run License Surrender | 1018 | Relicensing Work | 3890
Other | 77 | Move Union and Retirees to FLEX (ERP) | 1425
Total Bull Run - Decommissioning | 1095 | CIS Replacement | 2254
|  | Other | 8819
Transmission |  | Total Intangible | 16388
Transmission Blanket Jobs | 2405
Substation Fitness | 1015 | Nonutility
Other | 6398 | Habitat MOU | 1000
Total Transmission | 9818 | Other | 4334
|  | Total Nonutility | 5334
Distribution
Blanket Jobs - General Line Work | 49803
Blanket Jobs - Connect New Customers | 37619 | Total Before Decommissioning | 206572
Network Meter Reading - Meters | 8297
Purchase Transformers for New Customers | 6197 | Decommissioning | 23429
Sunset Sub | 4772
ROW Vegetation Program | 2394 | Total 2002 | 230001
Purchase Customer Meters | 2357
Station E Capacity Addition | 2085
Substation Fitness Program | 2071
Other | 5163
Total Distribution | 120758

## Updated 2002 capital slide
2002
Production |  | General
Round Butte - Replace Runners Unit #2 | 1917 | Mobile Communication (Radio) Improvements | 5543
Round Butte - Replace Runners Unit #3 | 1836 | Purchase/Retire Vehicles & Power Op. Equip. | 5195
Pelton-Round Butte Fish Passage | 1424 | Network Meter Reading | 4172
Colstrip | 5494 | Distributions Operations Center | 1500
Other | 12700 | Other | 13398
Total Production | 23371 | Total General | 29808
Bull Run - Decommissioning |  | Intangible
Bull Run License Surrender | 1018 | Relicensing Work | 3890
Other | 77 | Move Union and Retirees to FLEX (ERP) | 1425
Total Bull Run - Decommissioning | 1095 | CIS Replacement | 2254
|  | Other | 6565
Transmission |  | Total Intangible | 14134
Transmission Blanket Jobs | 2405
Substation Fitness | 1015 | Nonutility
Other | 6398 | Habitat MOU | 1000
Total Transmission | 9818 | Other | 4334
|  | Total Nonutility | 5334
Distribution
Blanket Jobs - General Line Work | 49803
Blanket Jobs - Connect New Customers | 37619 | Total Before Decommissioning | 202196
Network Meter Reading - Meters | 8297
Purchase Transformers for New Customers | 6197 | Decommissioning | 23429
Sunset Sub | 4772
ROW Vegetation Program | 2394 | Total 2002 | 225625
Purchase Customer Meters | 2357
Station E Capacity Addition | 2085
Substation Fitness Program | 2071
Other | 3041
Total Distribution | 118636
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/2002_capital_slide.xls'#$Updated 2002 capital slide
Note on C32: E04120: Includes a plug to reduce the 2002 budget by $2181, to the amount disclosed to NNG in the Disclosure Schedule. The 2002 budget overrun is driven by IT projects that have carried over into 2002 - however we have a UE115 balancing account that provides for full cost recovery. Also, it is likely given economic conditions that actual distribution capital projects will underrun the budget.
Note on G16: E25625: reduced $2,254k due to correcting calc error

## 2002 8-21 compared to 9-13
| BUDGET as of 8/21/01 FOM (Excludes Trojan Decom) |  |  | BUDGET as of 6/27/01 FOM run (Excludes Trojan Decom) | BUDGET as of 9/13/01 FOM (Excludes Trojan Decom) | Variance
| NW Natrual Target |  |  |  | Horton Slide
| 2002 |  |  | 2002 | 2002
Generation | 21673 |  | Generation | 25118 | 21554 | -119
Colstrip | 5494 |  |  | 5494 | 5494 | 0
Transmission | 10530 |  | Transmission | 10414 | 9610 | -920
Distribution | 91978 |  | Distribution | 100144 | 102036 | 10058 | $8 million due to transp. loadings
General | 10304 |  | General | 15418 | 9388 | -916
Intangible | 0 |  | Intangible | 0 | 0 | 0
Energy Efficiency | 60 |  | Energy Efficiency | 271 | 60 | 0
Non-Utility | 2954 |  | Non-Utility | 3667 | 2699 | -255
RWIP | 5703 |  | RWIP | 6216 | 6460 | 757
Blanket Reclass (2) | 6000 |  | Blanket Reclass | 6000 | 6000 | 0
Contingency | 6468 |  |  | -11578 | -2137 | -8605
Target for Operations | 161164 |  | Original Forecast Total | 161164 | 161164
NMR - IT portion | 3603 |  | NMR | 3602 | 4708 | 1105
ERP | 4802 |  | Peoplesoft | 1877 | 4774 | -28
CIS | 2095 |  |  | -2538635508500 | 4336 | 2241
Misc. IT | 17065 |  |  | 16839 | 17041 | -24
Target for IT Projects | 27565 |  |  | -2538635486182 | 30859 | 3294
SB1149 | 718 |  |  |  | 722 | 4
Unregulated Retail | 2984 |  |  | 1996 | 1958 | -1026
NMR - non IT | 10097 |  |  | 11699 | 9732 | -365
Target for Other Projects | 13799 |  | Forecast for Other Projects | 13695 | 12412 | -1387
Total Other Projects | 41364 |  |  | -2538635472487 | 43271 | 1907
0
Total Operations and Other | 202528 |  | Total Forecasted Ops and Other | -2538635311323 | 204435
Decommissioning | 21797 |  |  |  | 23429
Subtotal | 224325 |  |  |  | 227864
additional for Decommissioning | 1632
additional CIS | 2241 | (1)
reduction to Unreg Retail | -1026 | (2)
additional for IT portion of NMR | 1105 | (3)
reduction for non-IT portion of NMR | -365
other (ERP and Misc. IT) | -48
Subtotal | 3539
Less Energy Efficiency | -60 |  |  |  | -60
Total | 227804 |  |  |  | 227804
Total reduced from 230,001 to 227,804 due to calc error in spreadsheet.
(1) Moved $2,254K from '01 to '02
(2) Incorrectly put surge protectors into a capital job. It was removed. Will put into inventory, then put to balance sheet and amortize over 2 years lease period.
(3) $500k increase in design costs from delay, the balance is '01 to '02 shift.
PGE (no subs) | 2001 per Aug FOR |  |  |  | 2002 Budget |  |  | August FOR
Generation (w/o Trojan) | 27849 |  |  |  | 27048 |  |  | Boardman | 1333
Transmission | 9878 |  |  |  | 9610 |  |  | Coyote | 1471
Distribution | 86496 |  |  |  | 112359 |  |  | Beaver | 3244
General | 20839 |  |  |  | 19120 |  |  | Relicensing | 6195
Intangible | 3758 |  |  |  | 29327 |  |  | Hydro | 15606
Energy Efficiency | 271 |  |  |  | 60
Trojan | 14 |  |  |  | 14 |  |  |  | 27849
Sub-total: Utility Ops | 149105 |  |  |  | 197538
Non-Utility | 1586 |  |  |  | 4657
RWIP | 5136 |  |  |  | 0
Blanket Reclass - 2001 | 6000 |  |  |  | 0
Overview | -3018 |  |  |  | 0
Sub-total: Operations | 9704 |  |  |  | 4657
Beaver 24MW Peaker | 12400 |  |  |  | 0
Colstrip | 3341 |  |  |  | 0
SB1149 | 5300 |  |  |  | 0
ERP | 4683 |  |  |  | 0
NMR | 5506 |  |  |  | 0
CIS | 14778 |  |  |  | 0
Port of Morrow Peaker | 26709 |  |  |  | 0
Overview | 17240 |  |  |  | 0
Sub-total: 2001 Additions | 89957 |  |  |  | 0
Decommissioning | 17892 |  |  |  | 21797
Blanket Re-class - 2000 | 0 |  |  |  | 0
Sub-total | 17892 |  |  |  | 21797
Total | 266658 |  |  |  | 223992
NNG Budget to Reconcile to | [5 empty] | 2001-02
Total with Decomm | 266658 |  |  |  | 223992 | 490650
less Overview (additions) | -17240 |  |  |  |  | -17240
plus Overview (operations) | 3018 |  |  |  | 0 | 3018
NNG Annual Op Budget | 252436 |  |  |  | 223992 | 476428
less actual costs thru Aug 2001 | -148558 |  |  |  | 0
NNG Disclosure Schedule | 103878 |  |  |  | 223992 | 327870
less Decommissioning |  |  |  |  | -21797
2002 Total w/o Decomm. |  |  |  |  | 202195
2002 Budget w/o Decomm. |  |  |  |  | 204375
2002 Under / (Over) NNG Limit |  |  |  |  | -2180 |  | Reduce 2002 budget to equal NNG Disclosure Schedule.
Current Forecast (10-22-01) | September FOR |  |  |  | 2002 Bdgt
Total with Decomm | 247418
less Overview (additions) | 0
plus Overview (operations) | 3734
NNG Annual Op Budget | 251152 |  |  |  | 223992 | 475144
Under / (Over) NNG Limit | -1284 |  |  |  | 0 | -1284 | To the extent 2001 Actuals are projected to be less than the allowed amount (primarily due to delaying projects to 2002, move other projects forward from 2002 to 2001.
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/2002_capital_slide.xls'#$2002 8-21 compared to 9-13