## Detail
Project Summer Asset Transfer Matrix - July 21, 2000 11:30am
* Note: Friction Costs assume NO partner friction costs
** T = Transfer level, S = Sever level; A/B transfer level = sever level except where noted
| Name | BU | Country; Asset; Stage | Asset | Stage | BV (mm$) | ABC Now | ABC C | ABC Y/E | Transfer Restrictions | Action Items | People/Timing | Alternative | Friction Costs* | Transfer Level (Determined by ENE/VE group 6.20**) | EI Contracts w/ ENE companies
SOUTH AMERICA
1 | Arcor | sa | Argentina; Power Plant; Purchased | Power Plant | Purchased | 13 | A | A | C | P - 100% ENE owned L - No financing R - Contract for purchase signed, but not closed (no later than 9-30-00); Need Court for the Defense of Competition for transfer of interests with control or substantial influence at any level (voting issue, not economic) to move to C | R - Obtain Court for the Defense of Competition approval to move to C - can transfer interests with 'less than substantial influence' to A | Weiland, Shapiro, Young, Brasher, Jose Martinez de Hoz (local council) Timing: R - COC: 45-75 business days [4 mo] |  | 0 | T=Enron Corp.; need more info to conclude on A/B and S levels. | None -
2 | BBPL - GTB | sa | Bolivia; Pipeline; Existing | Pipeline | Existing | 29.044 | C | C | C | P - Various rights in favor of Shell L - No lender (Petrobras/Shareholder subdebt, $283MM) issues R - Confirmed SIRESE approval not necessary b/c sale of non-controlling minority interest | P - Determine to either move to EGPP or trigger/get waiver of pref right (allocation of purchase price issue) R - No SIRESE approval necessary, but must notify and manage relationship | LF - V&E - Roark, Brasher R - Romero Guevarra (LC), Shapiro, Weiland, Young Timing: Immediately upon announcement notify SIRESE | ok | 0 | T=ACFI (& Bolivia Holdings Ltd. if not transferred to ACFI yet); S=Bolivia Holdings Ltd. and Enron Reserve 7 BV; question whether also S=Enron Transportadora de Bolivia Ltd. | None -
3 | BBPL - TBG | sa | Brazil; Pipeline; existing |  |  | see above | C | C | C | P - Various rights in favor of Shell L - Multilateral debt, but no issues b/c sovereign guarantees/local bank) | P - Determine either to move to EGPP or trigger/get waiver pref right (purchase price allocation issue) | LF - V&E - Roark, Brasher P - Young Timing: |  | 0 | T=ACFI; S=Enron Brazil Power Holdings II Ltd. | None -
4 | CEG | sa | Brazil; Gas LDC; Existing | Gas LDC | Existing | 193.267 | A | C | C | P - Various rights in favor of partners L - May have to inform Banco Bozano of COC and request Bazano acceptance R - Confirmed no reg approval necessary | P - Determine either to move at certain level or trigger/get waiver of pref right (allocation of purchase price issue) - C now if trigger pref right (recommendation- trigger pref right) L - Inform Banco Bozano if necessary R - Notify ASEP after announcement; Structure management contracts such that no reg approval needed | LF - V&E - Roark, Brasher P & R - Tozzini (LC), Shapiro, Weiland, Young, Brasher, Waddel Timing: 7/17 whether or not to trigger pref right |  | 0 | T=ACFI; S=Enron International Brazil Gas Holdings Ltd and 1% GEC Participacoes held by Enron International Brazil 1997 Ltd.
5 | CEG-Rio | sa | Brazil; Gas LDC; Existing | Gas LDC | Existing | 69.571 | A | C | C | same as CEG | same as CEG | LF - V&E - Roark, Brasher same as CEG |  | 0 | T=ACFI; S=Ementhal Participacoes Empreendimentos Ltda.
6 | Copel | sa | Brazil; Electric LDC; Existing | Electric LDC | Existing | 134.69 | C | C | C | None - Stock position |  |  | ok | 0 | T=ACFI; S=Enron Brazil Power Holdings XII Ltd. | None -
7 | Cuiaba - EPE | sa | Brazil; Power Plant; Existing | Power Plant | Existing | 119.8 | B/X | B | B | P - various rights in favor of Shell L - 1.ENE must own 25% economic interest 2. Before project completion date, can sell up to 15.625% of shares of EPE; otherwise, no transfers of any beneficial or voting interests in EPE, BasBol, GasMat, or TBS (Subject to nominal OPIC consent) 3. ENE must control ENE Power Corp during EPC contract duration 4. ENE/Shell must control for 10 yrs after completion R - Consent of ANEEL necessary unless bidding requirements can be maintained by EI; confirmed ANEEL approval not necessary b/c transfer of IPP not regulated or b/c transfer above EPE Holdings | P - Need overall Shell resolution or must be in A (In B only b/c lender issues) L - Negotiate w/ OPIC/KFW to substitute EI for ENE in hold restrictions and no ENE hold requirement in EI (If obtain, can move to A, but remains X until project completion complete per OPIC financing) R - ANEEL consent not necessary; bidders requirements met by EI; Inforn ANEEL and FURNAS | LF - V&E - Barquin, Spradling, Novak, Brasher P - Taylor, MINT L - Gathmann, Gay, Lipshutz, Mellencamp (resolve before financial closing) R - Shapiro, Weiland, Barquin, Tozzini, Bestard Timing: 7/14 whether reg approval necessary | ok | P - Unknown L - 50 - 100bps upfront fee ($1.8 - $3.6MM) | T=ACFI; S=Enron do Brazil Holdings Ltd. | None -
8 | Cuiaba - Gas Bol | sa | Bolivia; Pipeline; Existing | Pipeline | Existing | 19.871 | B | B | B | P & L - see EPE R - SIRESE consent not necessary; need to maintain original concession requirements | R - Upstream transfer will avoid SIRESE approval, EI satisfies original consession requirements | R - Guevarra, Weiland, Young, Shapiro Timing: 7/14 | no | see EPE | T=ACFI; S=Enron International Bolivia Holdings Ltd. | None -
9 | Cuiaba - GasMat | sa | Brazil; Pipeline; Exisitng | Pipeline | Existing | 35.574 | B | B | B | P & L - see EPE R - ANP consent may be necessary; maintain original concession requirements | R - No ANP approval necessary, EI satisfies original requirements | R - Tozzini, Weiland, Young, Shapiro Timing: 7/14 | ok | see EPE | T=ACFI; S=Enron Brazil Power Holdings I Ltd. | None -
10 | Cuiaba - TBS | sa | Brazil; Gas Marketing; Existing | Gas Marketing | Existing | 72.55 | B | B | B | P & L - see EPE R - No approval necessary |  |  | ok | see EPE | T=ACFI; S=TransBorder Gas Services Ltd. (and Southern Cone Gas Ltd?) | None -
11 | Elektro | sa | Brazil; Power LDC; Existing | Power LDC | Existing | 1978.22 | C | C | C | R - Need ANEEL approval | L - Take out Firefly Equity and Debt R - Get ANEEL approval | LF - Skadden - Brasher; VE - Shouse L - Lipshutz (Firefly - 8/31/00) R - Shapiro, Tozzini, MINT - 30 days | ok | 0 | T=ACFI; S=Enron Brazil Power Holdings XI Ltd and Enron Brazil Power Holdings V Ltd.
12 | Gaspart | sa | Brazil; Gas LDC; Existing | Gas LDC | Existing | 171.913 | A | C | C | P - Pref rights | P - Determine to either move at certain level or trigger/get waiver of pref right - Will be C if pref right triggered | LF - V&E - Blumental, Brasher R - Tozzini (LC), Shapiro, Weiland, Young, Waddel Timing: 7/17 | ok | 0 | T=ACFI; S=Enron International Brazil Investments 1997 Ltd. (or Global Petroleum & Gas Ltd. (Jersey)?) | None - | `
13 | TGS | sa | Argentina; Pipeline; Existing | Pipeline | Existing | 451.92 | A | A | C | P - Pref rights/tag-along rights in favor of Perez Companc extend up to ENE L - Put of $220MM Notes if ENE and Perez Companc have less than 50.1% vote of CIESA shares R - ENARGAS consent needed to move to C (COC); Need Court of Competition consent for transfers of interests with control or substantial influence at any level (voting issue, not economic) to move to C | P - Leave in A, trigger COC, trigger pref right and a consent to transfer, or get waiver of transfer restrictions L - Negotiate w/ Noteholders to substitute EI with ENE in hold restrictions and no future ENE hold restrictions R - Get ENARGAS and Court of Competition approval to move to C; structure management contract such that no reg approval needed to go to A | LF - VE - Blumental, Brasher P - Brasher, Young L - Gathmann, Gay, Lipshutz, Mellencamp (6 weeks) R - Martinez de Hoz, Weiland, Shapiro, Young, Brasher Timing: R - CoC: 75 days, ENERGAS approval (6 weeks) |  | L - 50-100bps ($1.1 - $2.2MM) | T=ACFI & EGPP; S=Enron Argentina CIESA Holding SA, Enron Pipeline Co. Argentina SA and EPCA CIESA Inversiones Ltda. | None -
14 | Transredes | sa | Bolivia; Pipeline; Existing | Pipeline | Existing | 153.822 | A | A | C | P - Various rights in favor of Shell L - No lender issues R - Confirmed SIRESE approval not necessary b/c sale of non-controlling minority interest | P - Confirm Shell's acquisition of Transredes' interest in GasBol proir to closing (to prevent default under Cuiaba OPIC financing); Move to EGPP R - Notify SIRESE immediately after announcement and manage the relationship | LF - VE - Roark, Brasher Guevarra, Shapiro, Weiland, Young, Brasher Timing: Immediately upon announcement notify SIRESE and confirm approval not necessary 2 weeks after notice |  | 0 | T=ACFI; S=Enron Transportadora Holdings Ltd. | $10MM ENE loan
15 | Argentina Trading |  | Argentina |  |  | 15.34 | A | A | C | R - Need Court of Competition consent to move to C; Need to confirm COC issues regarding power broker license | R - Obtain Ct of Competition approval to move to C; structure management contract such that no reg approval needed to go to A; Confirm COC power broker isssues | R - Martinez de Hoz, Weiland, Shapiro, Young, Brasher Timing: R - CoC: 75 dyas |  | 0
16 | Bom Retiro | sa | Brazil | PPA | Development |  | C | C | C | No issues |  |  |  | 0
17 | Dona Francisca | sa | Brazil | PPA-prepay | Adv Dev |  | C | C | C | No issues |  |  |  | 0
18 | ECE | sa | Brazil | Power Marketing |  |  | C | C | C | No issues |  |  |  | 0
19 | Electrobolt | sa | Brazil | IPP | Early |  | C | C | C | No issues |  |  |  | 0
20 | Grupo Rede | sa | Brazil | Power prepay | Adv Dev |  | C | C | C | No issues |  |  |  | 0
21 | Grupo Rede - EPA with Cuiaba II | sa | Brazil | EPA Enron/ Grupo Rede | Adv Dev |  | C | C | C | 100% ENE owned - Confirm no restrictions on upstream COC |  | LF - VE - Cerano |  | 0
22 | GTB - 2% Purchase | sa | Bolivia | Pipeline | Adv Dev |  | C | C | C | Dead deal |  |  |  | 0
23 | International E-Commerce | sa |  |  |  |  | C | C | C | No issues |  |  |  | 0
24 | Maxus Bolivia | sa | Bolivia | Gas Prepay | Adv Dev |  | C | C | C | No issues |  |  |  | 0
25 | Pactual | sa | Brazil | PPA | Development |  | C | C | C | No issues |  |  |  | 0
26 | Puerto Suarez | sa | Bolivia | IPP | Early |  | C | C | C | P - No documents executed |  |  |  | 0
27 | Rhodia | sa | Brazil | Energy Services | Development |  | C | C | C | No issues |  |  |  | 0
28 | Rio Geo | sa | Brazil | Seismic Study Project | Operating |  | C | C | C | Same as APACHI #17 |  |  |  | 0
29 | Riocell | sa | Argentina | Energy Services | Development |  | C | C | C | No issues |  |  |  | 0
30 | Rosal | sa | Brazil | Share purchase in Hydro | Development |  | C | C | C | No issues |  |  |  | 0
31 | Scraps Phase II | sa | Bolivia | Chaco (20,300 MMBtu/d) | Development |  | C | C | C | No issues |  |  |  | 0
32 | Scraps Phase III | sa | Bolivia | British Gas | Development |  | C | C | C | No issues |  |  |  | 0
33 | Scraps Phase IV | sa | Bolivia | Vintage (20,300 MMBtu/d) | Development |  | C | C | C | No issues |  |  |  | 0
34 | Software | sa | Company | Software Dev. | Advanced Dev. |  | C | C | C | No issues |  |  |  | 0
35 | South American Fiber |  | Fiber Build; In Dev |  |  |  | C | C | C | No issues |  |  |  | 0
36 | TBG | sa | Brazil | Gas Compression Service | Development |  | C | C | C | No issues |  |  |  | 0
37 | VCP | sa | Brazil | Energy Services | Development |  | C | C | C | No issues |  |  |  | 0
38 | Vintage | sa | Bolivia | Gas Supply Con. | Adv Dev |  | C | C | C | No issues |  |  |  | 0
CALME
1 | Accro | ca | Venezuela; Gas Plant; Existing | Gas Plant | Existing | 2.13 | X/B | C | C | P - Pref right for direct ENE ownership and COC issue in Members Agreement and for PDVSA and TransCanada L - OPIC Common Terms Agreement 25% voting and economic hold requirement; transferees subject to nominal OPIC consent; no transfers until after project completion (project not complete) R - Confirmed no reg approval needed | P - Need partner consent to move to C or trigger pref right L - Get OPIC consent to amend hold restrictions from ENE to EI, must also get Transcanada consent as part of Accroven board approval in order to amend financing docs; Make sure movement of financing onshore has no additional transfer restrictions; Check restrictions in current EXIM financing; Cannot transfer any interests until project completion per OPIC financing | LF - VE - Kamine, Brasher L - Gathmann, Castagnola, Lipshutz, Mellencamp (2 months) R - Travieso (LC), Weiland, Shapiro, Young Timing: Spradling to confirm no EXIM transfer restrictions by 7/17, confirm no reg approval needed by 7/17 |  | 50 - 100 bps ($1-$2MM) | T=ACFI; S=Enron Industrial de Venezuela Ltd., Enron Colombia Holdings Ltd. and Enron ACCRO BV; B=Enron Industrial de Venezuela Ltd. and Enron Colombia Holdings Ltd. | O&M Agreement w/ Accroven Sister Co
2 | Bachaquero | ca | Venezuela; Compression; Existing | Compression | Existing | 7.59 | C | C | C | P - Hanover Cayman pref purchase right L - Loan agreements prohibit COC of EI Venezuela Developments Ltd, other than to EPP, but lender is ENE entity (affiliate contracts) R - Confirmed no reg approval needed | P - Transfer upstream L - ENE Sub consent required R - Confirm no reg issues | LF - VE - Kornreich, Brasher L - Lipshutz, Walia (1 month) R - Blanco, Weiland, Shapiro Timing: Confirm regulatory by 7/17 | ok | 0 | T=ACFI; S=EI Venezuela Holdings Ltd. and Compression Projects Finance Ltd.; C=Compression Projects Finance Ltd.?
3 | Bahia Las Minas | ca | Panama; IPP; Existing | IPP | Existing | 95.51 | B | C | C | P - ENE Caribe III must own 25% of EIPSA until 1/14/04; ECIII or EIPSA must control EGEMINSA until 1/14/04 under bid rules (Govt is partner) L - No issues R - For sale of more than 51% direct or indirect interest in EIPSA, approvals from Panama Ministry of Finance (sits on board) and Ente Regulador needed to move to C | P & R - Obtain Panama Ministry of Finance and Ente Regulador Consent to move to C; Determine if Fuel Agreement will be transferred to EI | LF - VE - Cestero, Brasher R - D'Alba, Fabrica, Pinto leite, Shapiro Timing: 4-6 weeks after announcement | ok | 0 | T=ACFI; S=Enron Caribe III Ltd.
4 | Calife | ca | Venezuela; Electric LDC; Existing | Electric LDC | Existing | 31 | C | C | C | No issues |  | LF - VE - Kornreich, Brasher | ok | 0 | T=ACFI (or ENE?-top tier not clear); S=V Holdings Industries SA;
5 | Caribbean Basin Power Fund | ca | CA; Investment; Existing | Investments | Existing | 20 | C | C | C | P - No board approval needed, but investor must be an accredited investor for US Securites Law purposes | P - Confirm accredited investor | LF - VE - Sasser P - Sayer; Castagnola Timing: Confirm accredited investor by 7/21 |  | 0 | T=ACFI; S=Enron Caribbean Finance Ltd.
6 | Centragas | ca | Colombia; Pipeline; Existing | Pipeline | Existing | 36.75 | A | C | C | P - ENE must control GP interest; Need Tomen consent if ENE holds less than 25% L - 144A indenture - EDC must be GP; ENE 51% hold requirement for EDC; ENE 25% vote and value hold requirement for Centragas R - Ecogas (govt) approval required to move to C | P - Tomen consent to move to C L - Transfer 1% GP ownership to A; Transfer remaining interest to B' (25% ENE, 75% MINT) R - Get Ecogas consent to move to C | LF - VE - Geller P - Sayer; Geller L - Gathmann, Castagnola, Lipshutz, Mellencamp R - Weiland, Shapiro, Young, LC Timing: R - 3 months | ok | 0 | T=ACFI/ EGPP (49% LP) and Enron Development Corp (1% GP); S=Enron Commercial Finance Ltd. and EDC
7 | Citadel Venezolana | ca | Venezuela; Controls; Existing | Controls | Existing | 31.61 | C | C | C | P - Technical Assistance Agreement with GE - consent required?? | P - Confirm status of project and determine if any consents required | LF - VE - Kornreich Sayre |  | 0 | T=see Calife; S=Citadel Corporation Ltd.
8 | Corinto | ca | Nicaragua; IPP; Existing | IPP | Existing | 4.06 | A/B | C | C | P - Equity ROFR (can transfer upstream); ENE Caribe VI must hold 15% under Technical Services Agreement; ENE must hold 15% vote and value all the way upstream under Assumption Agreement (can satisfy through interest in MINT) L - No hold restriction but ENE has obligation to purchase vessel if default; backstopped by pro rata obligations of partners so ENE exposure is 35% | P - Negotiate w/ Centrans and CDC to substitute EI for ENE in hold requirements in Assumption Agreements L - No MARAD consent or notice needed if sell above Corinto level; MARAD backstop likely to have to stay in place | LF - Skadden - ; VE - Geller P - Sayre, Castagnola |  | 0 | T=ACFI; S=Enron Caribe VI Holdings Ltd. | ENE Gty of MARAD financing issues; Fuel Supply Agreement w/ ENE;
9 | Dolphin | ca | Middle East; Pipeline; Existing | Pipeline | Existing | 3.1 | B | B | C | P - ENE 51% hold requirement in JVA L - No issues R - No issues | P - Get Partner (Offsets and Elf) consent immediately after announcement | LF - VE - Deemer, Brasher P - Rogers - 2 weeks after announcement | ok | 0 | T=ACFI; S=Enron Gulf Holdings Ltd.
10 | EcoElectricia | ca | Puerto Rico; IPP; Existing | IPP | Existing | 80.84 | B (b/c partnership) | C | C | P - No ENE hold requirement w/ partners other than GE b/c conversion occurred 6/15/00; GE pulls in hold restrictions from credit agreement (has independent vote) L - 12.5% ENE (all the way upstream) hold requirement in Credit Agreement; 25% hold requirement for all sponsors R - No PSC approval needed, but may need Sec of State approval due to industrial tax exemption | P - Transfer upstream; GE - See lender strategy below L - Negotiate to substitute EI for ENE in lender and GE hold requirements; Confirm that Edison qualifies as a new sponsor, satisfying 25% hold requirement for sponsors (VE) or substitute EI for ENE in agreement R - Check Sec of State approval | LF - VE - Sasser L - Gathmann, Castagnola, Lipshutz, Mellencamp Timing: 2 months | ok | 50 bps ($3.7-$7.5MM) | T=ACFI; S=Enron LNG Power (Atlantic) Ltd. | ENE guaranty of a dividend of $20MM to GE for working capital purposes; ENE guaranty of EPC contract (in warranty); Phase 2 is LNG terminal and under construction
11 | Gaza | ca | Gaza; IPP; Existing | IPP | Existing | 14.11 | X/B | B | C | P - Need board of director/shareholder approvals of any transfer if transfer below ENE Palestine Inc; Waiver of Shareholder Rights Agreement has ENE hold restriction re:100 shares (tax issues); Transfer Agreement - ENE can transfer only to 'controlled affiliate' and non-ENE owners in controlled affiliate must satisfy reputation and expertise requirements L - ENE must hold 51% vote and value of EGIL R - No Consent required O - PPA may require ENE ownership; IPO on Palestinian Stock Market (ENE ownership becomes 33.5%) | P - Transfer at ENE Palenstine Inc. level to avoid some partner consent issues; Confirm tax implications (Sykes); Get PEC Plc consent; Consult w/ Local counsel re: Palestinian Securities Laws; Determine if PPA offtake consent needed L - Negotiate w/ Banks to substitute EI for ENE in hold restrictions | LF - Skadden - Hoghooghi P - Rogers, Brasher, Coles, Sykes L - Lipshutz, Mellencamp, Gathmann and Richardson (2 months) Timing: Confirm tax implications by 7/21, consult w/ local counsel by 7/14; PEC consent 4-6 weeks O: Put IPO on hold immediately; scrub PPA for ENE ownership - Skadden by 7/17 |  | 50-100bps ($250-$500MM | T=ACFI; S=Enron Palestine Inc.
12 | Haina | ca | Dom. Rep.; IPP; Existing | IPP | Existing | 57.83 | C | C | C | Sold 6/30/00; 10 year note ($9MM is asset) |  |  |  | 0
13 | Industrial Gases Limited (IGL) | ca | Jamaica; LPG Dist; Existing | LPG Dist | Existing | 29.89 | C | C | C | No issues |  | LF - VE - Kornreich, Brasher | ok | 0 | T=see Calife; S=Citadel Corporation Ltd.
14 | Land (Pakistan) | ca | Pakistan; Land; Existing | Land | Existing | 2 | C | C | C | No issues |  |  |  | 0
15a | PQPC | ca | Guatemala; IPP; Existing | IPP | Existing | 33.07 | A | C | C | P - Restrictions on transfer at project level; Pref rights at shareholder level L - IFC hold restriction | P - Sell at EGPP level or above to alleviate pref rights/ all restrictions on transfer L - If IFC paid off, asset can go to C | LF - VE - Byrd, Spivak; Brasher L - Gathmann, Castagnola, Lipshutz, Mellencamp (resolve before financial closing) | ok | 0 | T=ACFI and EGPP; S=Puerto Quetzal Power LLC and Puerto Quetzal Power Corp. | EFI Fuel Supply Agreement;
15b | PQPL |  | Guatemala; IPP; Existing |  |  |  | C | C | C | P - No issues (100% owned) | P - Transfer at ENE Guatemala Holdings L - Negotiate OPIC and MARAD fianncing with EI instead of ENE
16 | ProCaribe/Protane | ca | Puerto Rico; LPG Dist; Existing | LPG Dist | Existing | 2.22 | A | A | C | R - For COC at any level need PR Port Authority; for transfer or encumbrance at any level, need PSC consent/approval - easy to obtain | L - As result of COC, either sublease to EcoElectrica or get consent to waive sublease - (Get confirmation) R - Get PR Port Authority and PSC approval to move to C; Can transfer < 50% to A | LF - VE - Kornreich, Brasher L - Castagnola (1 month) R - Sayer, Curran, Dapena, Shapiro Timing: 2-4 months |  | 0 | T=see Calife; S=The Protane Corporation
17 | Progasco | ca | Puerto Rico; LPG Dist; Existing | LPH Dist | Existing | 14.58 | A | A | C | R - For COC at any level need PR Port Authority; for transfer or encumbrance at any level, need PSC consent/approval - easy to obtain | R - Get PR Port Authority and PSC approval to move to C; Can transfer < 50% to A | R - Sayer, Curran, Da Pena, Shapiro Timing: 2-4 months |  | 0 | T=see Calife; S=ProGasco Inc.
18 | Promigas | ca | Colombia; Pipeline; Existing | Pipeline | Existing | 137.24 | C | C | C | R - tender offer? | R - Confirmed that no tender offer needed b/c part of larger transaction | LF - VE - Shouse, Brasher R - Weiland, Shapiro, Sayre, LC Timing: 7/21 | ok | 0 | T=EGPP buys back from Condor; S=ECT Colombia Pipeline Holdings 2 Ltd.
19 | Rio Hondo |  | Guatemala; IPP; Existing |  |  |  | C | C | C | Capitalized development costs | Determine how/when to unwind ENE guarantee of loan funded to EECC | Sommers, Walia Timing: 7/21 |  | 0 | T=ACFI; S=Enron Guatemala Renewables Ltd.
20 | San Juan Gas | ca | Puerto Rico; LPG Dist; Existing | LPG Dist | Existing | 9.42 | A | A | C | L - ENE must hold 51% stock (ENE retains litigation risk) R - Need PSC approval at any level | L - Get waiver from Chase for ENE hold requirement (ENE guaranty in place) R - Get PSC Approval | LF - VE - Cestero L - Gathmann, Lipshutz (2 months) R - Sayre, Curran, Shapiro, Dapena (LC) (2-4 months) | ok | 0 | T=Enron Corp; S=San Juan Gas Co.
21 | SECLP | ca | Dom Rep; IPP; Existing | IPP | Existing | 41.05 | B/A | B/A/C | B/C | P - Consent required - difficult partner issues L - Determine whether 20% of Ventane ownership can be transferred to B, and remaining Ventane piece as well as other SECLP can go to C (Payment default; poor lender relations); ENE affiliate must perform as O&M manager; O - Agreement btw ENE and EGPP - ENE must maintain 50% ownership of EGPP while IFC financing in place or indemnify EGPP against all claims | P & L - Strip out 4/7 of 35% FinVen interest and put in B; Allow remaining 3/7 to be transferred w/ Protane to A; Remaining 50% to C (Brasher/Spradling to confirm w/ tax); Verify the structure solution alleviates partner and lender (IFC, MARAD, DEG) issues; Determine whether O&M Co can be put into A to satisfy O&M hold restrictions O - Terminate ENE hold requirement for EGPP | LF - VE - Byrd, Spivak P & L - Spradling/Brasher to determine structure given all contraints P&L - Sayre, Gathmann Timing: Determine O&M hold by 7/14 | ok | 0 | T=EGPP and Enron Americas Inc. (see Calife); S=Finven Financial Institution Ltd., Enron Dominicana Holding Ltd., Enron Dominican Republic Ltd and Ernon Dominican Republic Operations Ltd.;
22 | Ventane | ca | Venezuela; LPG Dist; Existing | LPG Dist | Existing | 138.62 | C | C | C | P - Transfer at any level could require tender offer |  | LF - VE - Kornreich, Brasher R - Shapiro, Sayre; Baker McKenzie Timing: 7/17 | ok | 0 | T=see Calife; S=V. Holdings Industries SA
23 | Colombia/ Panama Pipeline |  | Pipeline; Mid-Dev | [6 empty] | No issues |  |  |  | 0
24 | Dom Rep LNG | [5 empty] | C | C | C | MOU w/ Union Finosa for re-gas facility - No transfer restrictions |  |  |  | 0
25 | Elba Island Terminal Capacity | ca | USA | LNG Terminal | [5 empty] | Negotiating LNG put requirement - possible transfer restrictions - confirm upstream transfer avoids consent |  |  |  | 0
26 | ExMar/ 2ExMar | ca | LNG Ships | LNG Ships |  |  | C | C | C | Option may have transfer restrictions (but upstream transfer ok) - option prices are significantly in the money - ENE Corp Gty -Termination for Convenience $74.5 MM in first year and goes to $47.5 after 3 years (25 yr charter) |  |  |  | 0
27 | Hoegh Galleon (charter) Nov. 2000 | ca | LNG Ships | LNG Ships |  |  | C | C | C | Charter party w/ ENE LNG Shipping Company - no upstream restrictions - 3 years then novate into VLNG or MetGas projects - no COC - ENE Corp Gty to backstop termination for convenience agreement - $18MM for first 3 years then goes down |  |  |  | 0
28 | Israel Power |  | Israel; Electric Generation; Early Dev |  |  |  | C | C | C | No issues |  |  |  | 0
29 | Israel Telecom |  | Israel; Telecom; Early Dev |  |  |  | C | C | C | No issues |  |  |  | 0
30 | Jebel Ali Project UAE | [5 empty] | C | C | C | MOU - No transfer restrictions |  |  |  | 0
31 | Master LNG P&S Agreement w/ Adgas | [5 empty] | C | C | C | For spot market LNG - holds FERC LNG import licence which may have upstream transfer issues - confirm no other upstream transfer issues |  |  |  | 0 |  | Spot L/C w/ ENE
32 | Oman Gas Distn | ca | Dev | LNG Supply Contracts |  |  | C | C | C | No issues |  |  |  | 0
33 | PR LNG Expansion | [5 empty] | C | C | C | In Development |  |  |  | 0
34 | San Juan Gas Geo Fiber Bundle |  | Puerto Rico |  |  |  | C | C | C | No issues | R - Get PSC Approval |  |  | 0
35 | Saudi Arabian IPP | [5 empty] | C | C | C | Sadaf inside the fence power plant - draft JDA - no restrictions on tranfser - MOU |  |  |  | 0
36 | Venezuela LNG Project | [5 empty] | C | C | C | No issues at present (agreement pending) |  |  |  | 0
37 | Westinghouse Turbine | [5 empty] | C | C | C |  | Need to determine if there are transfer restrictions | Sayre by 7/17 |  | 0
38 | International E-commerce |  | Venezuela; |  |  |  | C | C | C | P - ROFR and tag-along rights at ENE Caribe Level | P - Transfer at ACFI to alleviate partner issues |  |  | 0 | T=ACFI; S=International eCommerce Inc.
39 | Lakshmi (Greenfield Shipping) | in | India | LNG Ships |  |  | A | C | C | L - ENE Corp 20% voting hold requirement | L - Amend to replace ENE with EI in hold restrictions | LF - Linklaters - Gewirtz, Andrews, Rogers, Hoghooghi, Spradling L - Castagnola, Gathmann, Lipshutz, Mellencamp Timing: 2 months |  | 50 - 100 bps ($830M - $1.6MM) | T=ACFI; S=Greenfield Holding Co. Ltd.
APACHI
1 | Advanced Agro | ap | Thailand; Bonds, Existing | Bonds | Existing | 4.094 | C | C | C | No transfer restrictions | Bonds owned by ENE CTS International, a wholly-owned sub of ENE |  |  | 0 | Transfer entity that owns bonds
2 | Australia Trading |  | Australia |  |  | 5.11 |  |  |  | Need to investigate approvals when structure determined |  | Aronowitz |  | 0
3 | Barges | ap | Nigeria; IPP; Existing | IPP | Existing | 32.6 | C | C | C | P - Asset held by LJM | P - LJM structure needs to be unwound | Lipshutz, Lynn Timing: 1 day before close | ok | 0 | Transfer at project co or above | None
4 | BASF | ap | China; IPP; Active | IPP | Active | 2.98 | C | C | C | Capitalized development costs |  |  | ok | 0
5 | Batangas | ap | Philippines; IPP; Existing | IPP | Existing | 55.42 | A | C | C | P - No issues (100% owned) L - ADB and OPIC requirement for ENE to hold 50% voting interest; Transferee subject to nominal OPIC consent R - No regulatory issues | L - Negotiate w/ OPIC and ADB to replace EI with ENE in hold requirement or voluntarily prepay; Check L/C reserve requirements (May be most economic to just pay off) | LF - Skadden - Saba, Spradling L - Gathmann, Hunt, Lipshutz, Mellencamp (2 months) Timing: Hunt, Gathmann (repayment of loan/LCs analysis - 7/24) |  | 50 - 100 bps ($100-$200M) | T=EGPP; S=Enron Power Philippines Corp.
6 | Benin | ap | Benin; IPP; Early | IPP | Early | 3.285 | C | C | C | Capitalized development costs |  |  |  | 0
7 | Bulacan | ap | Philippines; IPP; Advanced | IPP | Advanced | 2.57 | C | C | C | P - No restrictions L - October 2000 FMO financing closing | L - Anticipate there are no hold requirements | L - Quek |  | 0
8 | East Java | ap | Indonesia; PRI Claim; Existing | PRI Claim | Existing | 15 | C | C | C | Claim paid - asset deleted |  |  |  | 0
9 | Eclipse | ap | China; IPP; Existing | IPP | Existing | 111.12 | C | C | C | P &R - Can sell upstream w/o consent L - No restrictions | P - Transfer above project co; Notify MOFTEC; Cancel registration with SAIC | LF - VE Blumental | ok | 0 | T=ACFI; S=Enron International Chengdu Power Holdings Ltd.
10 | Encom | ap | Japan; Investment; Existing | Investment | Existing | -16.34 | C | C | C | P - Encom has business purpose restrictions not to compete with ENE trading business in Japan which fall away if ENE owns less than 1/3 voting stock of Encom, will review all ENE hold requirements further L - Investment has $26MM ENE demand note reflecting dollars distributed which will be used for investment | P - Determine structure of trading business in Japan to decide what amendments are necessary L - Note should be repaid, new note executed by EI, and dollars redistributed to EI | P - Baxter and Dr. Amin (Japan strategy) P - Lundstrom L - Gathmann Timing: P&L by closing; Lundstrom will review all ENE hold requirements by 7/17 | ok | 0
11 | Hainan | ap | China; IPP; Existing | IPP | Existing | 146.48 | C | C | C | P - Under termination agreement, 1 payment of $88MM remains (foreign exchange issues) |  | LF - VE - Blumental | ok | 0
12 | Humpus | ap | Indonesia; Bonds; Existing | Bonds | Existing | 17.299 | C | C | C | No transfer restrictions |  |  | ok | 0 | Transfer entity that owns bonds
13 | MISP | ap | Mozambique; Steel Plant; Early | Gas Supply | Early | 9.161 | C | C | C | Capitalized development costs |  | LF - VE - Curry, Brasher |  | 0
14 | Napa Napa | ap | PNG; Refinery; Early | Refinery | Early | 8.9 | C | C | C | Capitalized development costs P - No transfer restrictions; terminated S/H Agmt and ceased funding and retained non-voting economic interest L - No obligation to fund additional amounts | Confirm no COC restriction in shareholder agreement no longer operative | P - Lundstrom, Hunt Timing: 7/17 | ok | 0 | T=ACFI; S=Enron Papua New Guinea Ltd.
15 | Pande | ap | Mozambique; Gas Field in Dev; Early | Gas Dev. | Early | 23.169 | C | C | C | Under contract to sell gas field to SASOL for $30MM (proceeds split 20% w/ EOG) R - No restrictions (confirm with local counsel) |  | LF- VE - Curry, Brasher Hughes | ok | 0 |  | None
16 | Piti - Guam | ap | Guam; IPP; Existing | IPP | Existing | 29.34 | B | C | C | P - Cannot transfer any ownership interest in project co w/o consent of majority members; does not restrict transfers upstream L - 12.5% 'ownership interest' hold requirement R - no regulatory issues | P - Transfer upstream L - Negotiate w/ ABN/AMRO to replace EI with ENE in hold requirements or ENE to purchase 2.5% ownership interest (20% of 50% = 10% + 2.5% = 12.5%) | LF - Skadden - Thompson, Spradling L - Gathmann, Lipshutz, Mellencamp Timing:Determine purchase or negotiate by signing; if consent needed 2 months |  | 0 - 10 bps ($365M) | T=EDP Power I LLC and Enron Corp; S=Enron Development Piti Holdings Corp.
17 | Rio Geo (ApachiPortion) | ap | Brazil; Investment; Completed | Investment | Completed | 0.488 | C | C | C | P - No hold requirements if transfer above member level; ENE CTS International, wholly owned by ENE, owns 30% interest; ENE APACHI, a wholly owned sub of ENE APACHI LLC, owns a 30% interest | P - Transfer above member level | LF - VE - Coates, Brasher |  | 0 | Above member level | None
18 | Saipan | ap | Saipan; IPP; Early | IPP | Early | 0.08 | C | C | C | Capitalized development costs |  |  |  | 0
19 | SK | ap | South Korea; Gas LDC; Existing | Gas Distribution Company | Existing | 267.02 | A | C | C | P - Restriction on sale of project co interest for 3 yrs from closing date w/o SK consent (can transfer upstream); COC (reaches up to ENE) triggers buy-sell; SK will put price on table; ENE can buy or sell L - No restrictions R - No restrictions | P - Transfer upstream to satisfy restriction on sale of project co interest; For COC, try to obtain waiver or trigger buy/sell | LF - VE - Kornreich, Brasher McDonald, Lundstrom, Young Timing: 2 months |  | 0 | T=ACFI; S=Enron International Korea Holdings Corp.
20 | Soc Trang | ap | Vietnam; IPP; Early | IPP | Early | 3.59 | C | C | C | Capitalized development costs | Do not enter into transaction before closing. | LF - VE - Curry | ok | 0 | T=ACFI; S=ENE Soc Trang Power Holdings II Ltd.
21 | Subic | ap | Phillippines; IPP; Existing | IPP | Existing | 26.6 | A | A | C | P - Can't sell at project co level w/o Yuchenko consent; Yuchenko has Right of First Negotiation (no affiliate out); ENE must hold 51% voting stock of EGPP and other restrictions L - ENE 25% voting interest hold restriction; ENE must remain as guarantor on 2 contracts (Supervision Agt and Advisor Services Agt), or COC resulting in default under indenture R - no regulatory issues | P - Get Yuchenko consent and waiver of EGPP hold restriction (believe easy to obtain) L - Put in A; Post closing, consider to either get lender consent or refinance bonds (can get neutral economics, but is a timing issue) | LF - Skadden - Brasher: VE - McGown P - Hughes, Hunt L - Gathmann, Hunt, Lipshutz, Mellencamp (4 months) Timing:After closing | ok | Unknown | see Batangas
22 | Subic Bonds | ap | Philippines; Bonds; Existing | Bonds | Existing | 4.483 | C | C | C | No transfer restrictions; Bonds are owned by ENE CTS International, wholly owned sub of ENE |  |  | ok | 0 | Transfer entity that owns the asset
23 | SW Pipeline | ap | China; Pipeline; Early | Pipeline | Early | 7.544 | C | C | C | Capitalized development costs |  | LF - VE - Sasser, Brasher | ok | 0
24 | AEIA | ap | Africa | Inv. Fund | Early |  | C | C | C | No info |  |  |  | 0
25 | Bakrie | ap | Indonesia | Pipeline | Early |  | C | C | C | Early Development |  |  |  | 0
26 | Effasu | ap | Ghana | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
27 | EGAT | ap | Thailand | Financing | Early |  | C | C | C | Deal Dead |  |  |  | 0
28 | Ghana Gas | ap | Ghana | Gas Sale | Early |  | C | C | C | Deal Dead |  |  |  | 0
29 | GNPower | ap | Philippines | LNG/Re-gas | Early |  | C | C | C | Deal Dead |  |  |  | 0
30 | Internet Web development Co |  | Korea |  |  |  | C | C | C | No transfer restrictions; Equity held by ENE International Korea Resources LLC |  | Hughes, Hunt |  | 0
31 | Japan Trading | [5 empty] | C | C | C |  | Determine Japan structure | Baxter, Dr. Amin Timing: Whenever they want |  | 0
32 | Maputo Iron & Steel |  | Late dev |  |  |  | C | C | C | Duplicate to MISP |  |  |  | 0
33 | MIGA Claim |  | Insurance Claim |  |  |  | C | C | C | Duplicate to East Java |  |  |  | 0
34 | NSM | ap | Thailand | IPP | Early |  | C | C | C |  | Consider transfer to ENA; Claim in bankruptcy; Securities action pending against ENE for underwriting | Mellencamp Timing: 7/17 |  | 0
35 | Petroci Gaz | ap | Ivory Coast | Pipeline | Early |  | C | C | C | Deal Dead |  |  |  | 0
36 | Rio Geo (ApachiPortion) |  | Brazil; Investment; | [6 empty] | Duplicate to MISP |  | LF - VE - Coates, Brasher |  | 0
37 | Tema | ap | Ghana | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
38 | TLP | ap | Thailand | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
39 | TPI | ap | Thailand | IPP | Early |  | C | C | C | Deal Dead |  |  |  | 0
40 | WAGP | ap | West Africa | Pipeline | Early |  | C | C | C | Deal Dead |  |  |  | 0
WIND
1 | Aeolos | w | Greece; op | wind | operating | 12.3 | A | C | C | L - Consent or prepayment required if ENE ownership is less than 50% in EWC R - No transfer restrictions at project or immediately above, but may violate $7.5 MM Greek grant application | L - Obtain waiver to substitue EI for ENE in hold requirements or prepay $8MM debt R - Transfer at EWC or EREC level to ease concern about grant application | LF - VE - Reilly, Hoghooghi L - Gathmann, Friedlander, Lipshutz, Mellencamp (2 months) R - Shapiro, Newell (7/17) |  | $200M total friction costs for Wind | T=Enron Renewable Energy Corp.; S=Enron Renewable Energy Corp.
2 | Cabazon | w | USA; op | wind | operating | 27.88 | C | C | C | P - 60% equity in 'FOE' structure to preserve QF status; If all direct and indirect ownership interests transferred, stream of benefits true-up payment to 'FOE' L - No hold requirements or transfer restrictions | P - Obtain waiver from FOE for true-up with COC | LF - VE - Spradling, Hoghooghi |  | 0 | see Aeolos
3 | Chonos | w | Greece; dev right | wind | dev right | 0.5 |  |  |  | In development - Looking to be sold by 9-30-00 |  |  |  | 0 | see Aeolos
4 | Green Power I | w | USA; op | wind | operating | 19 | A | C | C | R - FERC approval required for COC; but COC is transfer of 10% or more | R - Section 203 filing immediately after announcement to obtain FERC approval for COC or transfer only 9.9% to an "A" company | LF - VE - Wenner (FERC Filing) R - Newell, Winner, Shapiro Timing: 2 months |  | 0 | see Aeolos
5 | Lake Benton I | w | USA; op | wind | operating | -0.2 | C | C | C | ENE ownership 1% - no restrictions |  |  |  | 0
6 | Lake Benton II | w | USA; sale to FPL?? | Wind | Sale to FPL | -3.86 | C | C | C | Sold 6-30-00 |  |  |  | 0
7 | Megalli Vrissi | w | Greece; op | wind | operating | 6.8 | A | C | C | See Aeolos |  |  |  | 0
8 | Mesa Entities | w | USA; op | wind | operating | 9.01 | A | C | C | L - TCW $4.5MM debt - COC prepayment penalty $400K - runs upstream - get consent or pay off loan | L - Amend docs to substitute EI for ENE in hold restrictions | LF - VE - Reilly, Hoghooghi L - Friedlander, Gathmann, Lipshutz, Mellencamp (2 months) Timing:Determine payoff vs. seek consent by 7/24 |  | 0 | see Aeolos | $2.5MM L/C as collateral for loan
9 | Owenreagh | w | Ireland; op | wind | operating | 0 | C | C | C | No issues |  |  |  | 0
10 | Painted Hills | w | USA; op | wind | operating | 1.1 | C | C | C | No issues |  |  |  | 0
11 | Project 251 | w | USA; op | wind | operating | 2.9 | C | C | C | No issues |  |  |  | 0
12 | San Antonio | w | USA; adv dev | wind | adv dev. | 0.3 | C | C | C | No issues |  |  |  | 0
13 | Sky River | w | USA; op | wind | operating | 0.41 | C | C | C | P - Reacquiring QF facility from 'FOE' structure L - Need CSFB consent for EWC to acquire 'FOE' interest in project; COC - CSFB; consent also required for ENE sale of EWC | P - Buy 'FOE' out of the structure (7-21-00) L - Obtain consent from CSFB | LF - VE - Reilly, Hoghooghi L - Freidlander, Gathmann, Lipshutz, Mellencamp (2 months) Timing: VE determine by 7/17 |  | 0 | see Aeolos
14 | Storm Lake I | w | USA; op | wind | operating | 0.25 | C | C | C | ENE ownership 1% - no restrictions |  | LF - VE - Reilly P - Young Timing: 7/17 |  | 0 | see Aeolos
15 | Storm Lake II | w | USA; op | wind | operating | 0.13 | C | C | C | ENE ownership 1% - no restrictions |  | LF - VE - Reilly P - Young Timing: 7/18 |  | 0 | see Aeolos
16 | Utgrunden | w | Sweden; adv dev | wind | adv dev. | 0.64 | C | C | C | Capitalized development costs |  |  |  | 0
17 | Victory Garden Phase IV | w | USA; op | wind | operating | 1.61 | C | C | C | No issues |  |  |  | 0
18 | Victory Garden Repower | w | USA; op | wind | operating | 8.15 | C | C | C | P - 60% equity in 'FOE' structure to preserve QF status; If all direct and indirect ownership interests transferred, stream of benefits true-up payment to 'FOE' L - No hold requirements or transfer restrictions | P - Get consent from FOE to waive true-up | LF - VE - Spradling, Reilly, Hoghooghi |  | 0 | see Aeolos
19 | Wind Resource Acreage | w | USA; land | land | land | 9.5 | C | C | C | No issues |  |  |  | 0
20 | Ardeche | w | France | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
21 | Cefn Croes | w | UK | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
22 | Christensen-Lazar | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
23 | Cottonwood | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
24 | Harwich | w | Offshore | wind | active dev. |  | C | C | C | Not yet closed | No issues if transfer upstream |  |  | 0
25 | Honduras | w | Honduras | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
26 | Indian Mesa II | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
27 | Kahua | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
29 | Maui | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
30 | Nicaragua | w | Nicaragua | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
31 | PSCO - Gobblers Knob | w | USA | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
32 | Puerto Rico | w | Puerto Rico | wind | active dev. |  | C | C | C | No issues |  |  |  | 0
33 | SMUD 35 | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
34 | Sweetwater | w | USA | wind | adv dev. |  | C | C | C | No issues |  |  |  | 0
35 | Tacke |  | Germany |  |  | 2.2 | C | C | C | Have not yet reviewed docs | Confirm there are no issues | LF - VE - Spradling Timing: 7/17 |  | 0 |  | Loan to EEL from Tacke
INDIA
1 | Capitalized Dev. Costs | in | India | N/A | N/A | 13 | C | C | C | No issues |  |  |  | 0
2 | Dabhol - Step 1(ENE owns 100% EMC, which owns 66% DPC; EIMC is a C entity to which 16% of DPC will be transferred by EMC by year end). At year end, EMC (100% vote and economics w/ ENE) in B; Operator and Fuel Manager must be B entities | in | India; IPP; Existing | IPP | Existing | 594.63 | B | B | 10.6%C, 89.4% B | P - ROFR/tag-along rights unless EMC continues to hold 50% DPC; various intersponsor agreements L - GOI Gty requires ENE to hold 26% ownership interest (directly or through an affiliate); Bank Group - ENE must hold 50% economic interest prior to commercial service of Phase II and LNG facility and 26% thereafter; ENE, GE, and Bechtel must own 70% of DPC shares collectively until one year after completion of Phase II and then drops to 51% of DPC shares collectively (ENE can use 5/7 of the difference between 70% collectively owned now and the 51% hold requirement). Bank group must approve new investor but not transfer (parallel path to regulatory, 8 weeks): ENE must own 50% economic interest in Offshore Power Operations C.V. and Enron Fuels International Inc. (the Operator and Fuel Manager) R - FIPB (approval for new investor to make $ investment in India - 4-6 weeks) (Need approval for sale of shares, and permission for new investor to own shares of Indian co - 2 additional weeks) / Bank group (approval of new investor, not transfer - parallel path, 8 weeks) O - EECC and Bechtel Power Coordination Agreement has EECC COC restriction (confirm reaches upstream) triggering purchase right of Bechtel to take over EPC contract for Phase II (power) | P - Pref rights have 30 day notice No shareholder approval necessary L - OPIC Global Soln; Approval of transferee indentity for 50% in A (14% in C at closing) (4 months for step 1) R - Obtain FIPB and RBI consents for investment adn transfer and pledge of shares | LF - Skadden P - Gathmann, Cline, Bhatnagar L - Gathmann, Mukerji, Lipshutz R - Katwala Timing: P - Give notice at announcement; L - 4-6 mo; R - 3 months | ok | 50 - 100 bps ($10 - 20MM) | T=ACFI; S=Travamark Two BV, Atlantic India Holdings and Enron Reserve II BV; A/B=partial transfer of DPC to New Mauritius HoldCo.
RBI (Need approval for sale of shares, and permission for new investor to own shares of Indian co - 2 additional weeks) / Bank group (approval of new investor, not transfer - parallel path, 8 weeks) O - EECC and Bechtel Power Coordination Agreement has EECC COC restriction (confirm reaches upstream) triggering purchase right of Bechtel to take over EPC contract for Phase II (power)
| Dabhol - Step 2 (Same as above but EMC will hold 26% DPC and EIMC would own 40% of DPC. Operator and Fuel Manager would be C entities at year end.) |  |  |  |  | 0 | B | B | 61%C, 39% B | Same as above | P - Trigger/obtain wiaver of shareholder rights; amend various intersponsor agreements L - Obtain lender consent to transfer shares and consent of lenders and MSEB (counterparty to contract) to assign fuel management contract to C entity and for operator to be a C entity R - Same as above | Timing: same as above (6 months if pursued first - 8 months if step 1 completed prior to step 2) |  | 0
3 | GAIL | in | India; Investment; Existing | Investment | Existing | 54.58 | C | C | C | Tax issue to moveout of EGEP - no transfer restrictions | Move out of EGEP | LF - Skadden | ok | 0
4 | Genesys | in | India; Investment; Existing | Investment | Existing | 1.5 | C | C | C | No issues if transfer upstream |  | LF - Skadden |  | 0 | Transfer above Enron India Regional Development Ltd.
5 | Ispat | in | India; IPP; Existing | IPP | Existing | 5 | B | C | C | P - ENE hold requirement of 23% applies upstream | P - Modify agreement to substitute EI for ENE and trigger or procure waiver of pref rights | LF - Skadden P - Gathmann Timing: 3 mo |  | 0 | T=ACFI; S=Enron India Regional Development Ltd.
6 | Kannur | in | India; Power Plant; Lost Bid | Power Plant | Lost Bid | 7 | C | C | C | Capitalized development costs |  |  |  | 0
7 | Metgas | in | India; Pipeline; Existing | Pipeline | Existing | 20 | A/B | C | C | O - TIGA (LNG supplier) requires 26% ENE hold requirement in all Metgas entities | O - Restructure unsigned contracts to allow new EI 26% hold and guarantees | LF - Skadden O - Anando resolve before signing the SPA with TIGA) Timing: |  | 0 | T=ACRI (or ENE if Enron Fuels Services Holding Ltd. not yet transferred); S=Enron Fuels Services Holding Ltd.
8 | Communications | in | India | Content | Providers |  | C | C | C |  |  |  |  | 0
9 | Data Center |  | Project; Development | Data Centers | Advanced Dev. |  | C | C | C | MOU only |  |  |  | 0
10 | ICO | [5 empty] | C | C | C | No issuses |  |  |  | 0
11 | India Fiber | [12 empty] | 0
13 | MSEB ROW | in | India | Fibre Optic Transmission | Advanced Dev. |  | X/B | C | C | P - Direct or indirect ENE Corp 100% hold requirement for 5 yrs | P - Evaluate possibility of obtaining waiver in context of the bid and then negotiate to obtain MSEB waiver to substitute EI for ENE in hold restrictions or wait for 5 years from to move into C | P - Katwala Timing: P - 2 weeks to determine if violates bid requirements; 2 months to get approval |  | 0
14 | Wockhardt Building | in | India | Hdqs. Bldg. | Definitive Agmt. |  | C | C | C | Disclosure issues re: Enron guaranty and imminent bond offering |  |  |  | 0
15 | Rediff.com |  | India |  |  | 0.3 | C | C | C | No issues |  |  |  | 0
EE&CC
1 | EE&CC | ee |  |  |  | 284.56 | C | C | C | CONFIDENTIAL |  |  |  | 0
| ACCRO | [8 empty] | O - Pref rights to construction consortium members triggered upon change of control. Enron Corp. must maintain 50% of share capital or voting interests in Enron Equipment Installation Company and Enron Equipment Procurement Company to avoid change of control and pref. right provisions (Onshore and Offshore Definitive Agreements).
| Piti - Guam | [8 empty] | P - Under O&M and TAA Agreements, ENE must own 50% vote or have the power to direct management or policies of ENE Guam Piti Corp and EI Asia Corp | P - V&E to confirm what needs to be done to obtain waiver
| Hardee Power Station | [8 empty] | P - The assignment clause prevents NEPCO and ENA from selling all or substantially all of their assets or an amount of stock sufficient to constitute a change of control without the prior written consent of TECO Power Services Corporation and each other. The parties may assign EPC contract to a 50% owned Affiliate | P - Sell above NEPCO to avoid restrictions
| Dabhol | [8 empty] | Upstream tansfer restriction in EECC-Bechtel Coordination Agreement

## Consents Needed
SIRESE Notification | Defense of Competition | Shell Pref Right | ASEP | ANEEL | ENERGAS | PR Port Authority/ PSC | ANP | Panama MoF and Ente Regulador
GTB | Arcor | GTB | CEG | EPE - maybe | TGS | Procaribe | Cuiaba - GasMat | BLM
Gas Bol | TGS | TGB | CEG-Rio | Elektro |  | Progasco
Transredes | Argentina Trading | Cuiaba - EPE |  |  |  | San Juan Gas
Cuiaba - GasMat
Cuiaba - GasBol
Cuiaba - TBS
Transredes