## summary
Northern Natural Gas Company
2001 Marketing Capital
CE to Plan
($MM)
|  | Discretionary | Non-Discretionary | Total
2001 PLAN |  | 16.12 | 12.16 | 28.28
1st Current Estimate Changes
| Transfer Retirements < $50,000 to Operations |  | -0.7 | -0.7
| Transfer funds from Marketing Pool to Wisconsin Gas Pool | -0.24 | 0.24 | 0
Added project for prior year's settlement
Total 1st Current Estimate |  | 15.88 | 11.7 | 27.58
2nd Current Estimate Changes
| Transfer funds from Marketing Pool to Koch Extension | -1.03 | 1.03 | 0
Koch costs over plan amount
| Return Capital Dollars from Pool | -5 |  | -5
Total 2nd Current Estimate |  | 9.85 | 12.73 | 22.58
3rd Current Estimate Changes
| Transfer funds to TW for 1/2 of Gray County | -0.69 |  | -0.69
| Return Capital Dollars from Pool | -0.5 |  | -0.5
Total 3rd Current Estimate |  | 8.66 | 12.73 | 21.39

## 3rdCE Cash Flow
NNG MARKETING
3rd CURRENT ESTIMATE - SEPTEMBER 2001
CAPITAL EXPENDITURES
(In Millions)
Total Capital by Company | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
NNG | 0.2 | 0 | 2.1 | 0.3 | 0.8 | -1.5 | 1.1 | 1.2 | 4.3 | 4.4 | 4.3 | 4.2 | 21.4
TW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Citrus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plains | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ETS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
percent / month | 0.9346% | 0% | 9.813% | 1.402% | 3.738% | -7.009% | 5.14% | 5.607% | 20.09% | 20.56% | 20.09% | 19.63%
cummulative |  | 0.9346% | 10.75% | 12.15% | 15.89% | 8.879% | 14.02% | 19.63% | 39.72% | 60.28% | 80.37% | 100%