## Summary (hidden)
|  | 1Q | 2Q | 3Q | 4Q
[6 empty] | Plan | Forecast | Variance
Total Year
NEPCO |  | 16.4 | 16 | 20.2 | 32.4 | 54 | 85 | 31
EECC |  | -8.3 | -22 | 1.8 | -1.53 | 11 | -30 | -41
| Total IBIT | 8.1 | -6 | 22 | 30.87 | 65 | 55 | -10
2ND Quarter
NEPCO |  | 6.5 | 11.4 | 11.9 | 24.2 | 11.4 | 18 | 6.6
EECC |  | 2.4 | 1.9 | 0.4 | 6.3 | 1.9 | -32.5 | -34.4
| Total IBIT | 8.9 | 13.3 | 12.3 | 30.5 | 13.3 | -14.5 | -27.8
CASH FLOW
Total Forecast |  |  |  |  | 150 |  | 150
Total Plan |  |  |  |  | 83 |  | 83
| Total Variance | 0 | 0 | 0 | 233 |  | 67

## ty (hidden)
|  | Plan | 1CE | Variance | Explanation
Projects
| Puerto Rico | 0 | -23 | -23 | Includes ($14.0) for B&V claim, ($5.0) PDM settlement, ($4.0) settlement with owner
| EPC 63/64 | 2.4 | -3 | -5.4 | Minimal recovery forecasted on claims due to Pemex failure to provide pipe on schedule and
weather delays on base scope caused by extra work provided at direction of Pemex
| Arcos | 4 | 0 | -4 | Project delayed
| Turkey | 0 | -2.1 | -2.1 | Siemens settlement and final project close out costs
| Lagos | 5.5 | 5.5 | 0
| India P.II - LNG & Marine | -0.2 | -7.7 | -7.5 | Effect of Besix and Kvaerner claims
| India P.II - Power | 0.8 | 0.8 | 0
| Poland | 0 | -1 | -1 | Failure to complete rotor repairs timely
| Cuiaba | 0 | -0.5 | -0.5 | HRSG claim with Siemens
| Accro | 0.6 | 0.6 | 0
| Other Misc. projects | 0.8 | 0.5 | -0.3 | Final close out costs
| Project Reserves | -20 | 0 | 20
| Subtotal Project Adjustments | -6.1 | -29.9 | -23.8
Accro Selldown |  | 21.5 | 21.5 | 0
Misc. Projects Solddown |  | 0 | 2.8 | 2.8 | Bachequero, Other projects
Deferred Profit Amortization |  | 1 | 1 | 0
Credit Reserve |  | 0 | -3.8 | -3.8 | Tribasa land reserve ($2.5), Severnaya ($1.0), Sonora ($.3)
G&A Expense |  | -7 | -29.1 | -22.1 | Includes ($14.3) of G&A not billed to business units. Also, includes ($7.8) of Corp. charges
associated with redeployed staff.
Business Development Expense |  | -1 | -4.4 | -3.4 | Abandoned project initiatives - Tecaso, Steel, etc.
3rd Party Interest Income |  | 2.6 | 4.9 | 2.3
Stretch |  | 0 | 7 | 7
Total IBIT - EECC |  | 11 | -30 | -41

## qtr summary
|  | 4Q |  | 4Q
|  | Plan |  | Forecast | Variance
| EECC | 8.2 |  | -22.07 | -30.27
| NEPCO | 30.1 |  | 6.4 | -23.7
| Total Project Margin | 38.3 |  | -15.67 | -53.97
G&A Expense
| EECC | -1.2 |  | -9.3 | -8.1
| NEPCO | -3.6 |  | -7.2 | -3.6
Business Development
| EECC | -0.7 |  | -1.5 | -0.8
| NEPCO | -1.6 |  | -2.5 | -0.9
3rd Party Interest Income
| EECC | 0.6 |  | 0.4 | -0.2
| NEPCO | -0.1 |  | -0.1 | 0
| Net Expenses | -6.6 |  | -20.2 | -13.6
| Total IBIT | 31.7 | * | -35.87 | -67.57
*The original plan IBIT is $30.5 million. Wholesale has requested
all business units increase their plan for the NQ Stock Option and
AESOP expenses that Corp. is not charging out. The total EEOS amount
is $1.2 million per quarter for those charges.

## 2q vs PSR (hidden)
[6 empty] | Total | Total
|  | 2Q | 2Q |  |  | Profit | Profit
|  | Plan | Fcst | Variance |  | PSR | Forecast | Variance
Projects
| Lagos | 2.2 | 2.5 | 0.3 |  | 8.2 | 8.2 | 0
| India P.II - LNG & Marine | -0.1 | -5 | -4.9 |  | 19 | 19 | 0
| India P.II - Power | 0.2 | 4.2 | 4 |  | 19.1 | 29.2 | -10.1
| EPC 63/64 | 0.2 | 1.8 | 1.6 |  | 6.2 | 6.2 | 0
| Poland | 0 | 0 | 0 |  | 5.6 | 5.6 | 0
| Cuiaba | 0 | -0.2 | -0.2 |  | 16.1 | 16.1 | 0
| Puerto Rico | 0 | 0 | 0 |  | -5 | -5 | 0
| Turkey | 0 | 0 | 0 |  | 31.5 | 31.5 | 0
| Accro | 0 | 0 | 0 |  | 40.8 | 43 | -2.2
| Peaker Closeout | 0 | 0 | 0 |  | 0 | 0 | 0
| OEC | 0.8 | 0 | -0.8 |  | 0 | 0 | 0
| Credit Reserve | 0 | -2.5 | -2.5 |  | 0 | 0 | 0
| Deferred Profit Amortization | 0.2 | 0.2 | 0 |  | 0 | 0 | 0
| Other Misc. projects | -0.5 | -1.5 | -1 | * | 6.8 | 7.5 | -0.7
| Stretch | 0 | 0 | 0 |  | 0 | 0 | 0
| Subtotal Project Margin | 3 | -0.5 | -3.5 |  | 148.3 | 161.3 | -13
G&A Expense |  | -0.5 | -8.1 | -7.6 |  | *Total CIGSA profit
Business Development Expense |  | -0.5 | -1.5 | -1
3rd Party Interest Income |  | 0.5 | 0.6 | 0.1
Total IBIT - EECC |  | 2.5 | -9.5 | -12
NEPCO |  | 12 | 10 | -2
Total IBIT - EEOS |  | 14.5 | 0.5 | -14

## EECC
|  |  | 4Q | 4Q
|  |  | Forecast | Forecast | Variance
|  | 4Q | Last | This | from Last | 1Q | 2Q | 3Q | 4Q | Total
|  | Plan | Week | Week | Week | Actual | Actual | Actual | Forecast | Year | 3CE | 1CE | Variance
Projects
| Lagos | 0 | 0 | 0 | 0 | 1.4 | 2.9 | -0.9 | 0 | 3.4 | 3.4 | 5.5 | 0
| India P.II - LNG & Marine | -0.2 | 0 | 0 | 0 | 1.4 | -4.8 | 0 | 0 | -3.4 | -3.4 | -7.7 | 0
| India P.II - Power | 0 | 0 | 0 | 0 | 0.4 | 3.2 | 0 | 0 | 3.6 | 3.6 | 0.8 | 0
| EPC 63/64 | 1.7 | 0 | 0 | 0 | -1.1 | 1.8 | 0 | 0 | 0.7 | 0.7 | -3 | 0
| Poland | 0 | -1 | -1 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | 0
| Cuiaba | 0 | 0 | 0 | 0 | 0 | -0.2 | -0.3 | 0 | -0.5 | -0.5 | -0.5 | 0
| Puerto Rico | 0 | -17 | -15 | 2 | -5 | 0 | 0 | -15 | -20 | -20 | -23 | 0
| Turkey | 0 | -5.2 | -5.2 | 0 | -2.1 | 0 | -0.3 | -5.17 | -7.57 | -7.6 | -2.1 | 0.03
| Arcos | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accro | 0 | 0 | 0 | 0 | 0.4 | 0 | -2.4 | 0 | -2 | -2 | 0.6 | 0
| Peaker Closeout | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 0
| OEC | 0 | 0.3 | 0.3 | 0 | 1.1 | 1.8 | 0.4 | 0.3 | 3.6 | 3.6 | 0 | 0
| Credit Reserve | 0 | 0 | 0 | 0 | 0 | -2.5 | -0.3 | 0 | -2.8 | -2.8 | -3.8 | 0
| Deferred Profit Amortization | 0.2 | 0.3 | 0.3 | 0 | 0.1 | 0.3 | 0.3 | 0.3 | 1 | 1 | 3.8 | 0
| Other Misc. projects | 0.2 | -0.7 | -1.5 | -0.8 | 0.3 | -0.2 | -1.9 | -1.5 | -3.3 | -3.3 | -1.1 | 0
| Overview | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0
| Subtotal Project Margin | 8.2 | -23.3 | -22.1 | 1.2 | -1.5 | 2.3 | -5.4 | -22.07 | -26.67 | -26.7 | -22.9 | 0.03
G&A Expense |  | -1.2 | -8.3 | -9.3 | -1 | -8.8 | -5.3 | -4.4 | -9.3 | -27.8 | -27.8 | -29.1 | 0
Business Development Expense |  | -0.7 | -1.5 | -1.5 | 0 | -0.7 | -5.6 | -1.5 | -1.5 | -9.3 | -9.3 | -4.4 | 0
Other Income |  | 0.6 | 0.4 | 0.4 | 0 | 2.8 | -0.9 | 0.6 | 0.4 | 2.9 | 2.9 | 4.9 | 0
Total IBIT - EECC |  | 6.9 | -32.7 | -32.5 | 0.2 | -8.2 | -9.5 | -10.7 | -32.47 | -60.87 | -60.9 | -51.5 | 0.03
NEPCO |  | 24.2 | 6.1 | -3.4 | -9.5 | 16.3 | 10 | 14.2 | -3.4 | 37.1 | 37.1 | 85 | 0
Total IBIT - EEOS |  | 31.1 | -26.6 | -35.9 | -9.3 | 8.1 | 0.5 | 3.5 | -35.87 | -23.77 | -23.8 | 33.5 | 0.03
Cash Flow | [9 empty] | 150 |  | 150 | 0
Note on S21: Erin Copeland: tempest -1.0, epc 63 -.2, demar -.3, wty -.3, dighton -.1
Note on U21: Erin Copeland: -.5 accro wty, -.2 saipuru/yapacani, -.8 Sutton bridge

## NEPCO
|  |  | 4Q | 4Q
|  |  | Forecast | Forecast | Variance
|  | 4Q | Last | This | from Last
|  | Plan | Week | Week | Week
Projects
| NEPCO-Europe/Caxios | 7.4 | 1.4 | 0.4 | -1
| GenPower/Dell | 1.3 | 1.9 | 1.7 | -0.2
| GenPower/McAdams | 1.3 | 1.2 | 0.6 | -0.6
| LS Power, Kendall | 1.4 | 0 | -5.5 | -5.5
| Cogentrix/Jenks, OK | 0.1 | 0 | -4 | -4
| NESCO/Goldendale WA | 0.8 | 2.3 | 2.7 | 0.4
| East Coast Power/Linden | 0.1 | -6.5 | -6.9 | -0.4
| Ouachita / Sterlington, LA | 1.5 | 1.3 | 1.5 | 0.2
| AES Wolf Hollow/Grandbury | 0.6 | 1.1 | 1.3 | 0.2
| Austin Energy | 0 |  | 0 | 0
| Cogentrix, Southhaven, MS | 3.8 | 1.4 | 1.3 | -0.1
| 2000 Peakers | 4.7 | 0 | 0 | 0
| LS Power, Pike County, MS | 0.9 | 0 | 0 | 0
| Gila River Power/Gila River | 0 | 5.3 | 4.3 | -1
| Union Power/El Dorado | 0 | 5.2 | 5.6 | 0.4
| Cogentrix, Caledonia, MS | 0.7 | 2.8 | 2.8 | 0
| Other Misc. projects | 5.5 | -1.5 | 0.6 | 2.1
| Subtotal Project Margin | 30.1 | 15.9 | 6.4 | -9.5
G&A Expense |  | -3.6 | -7.2 | -7.2 | 0
Business Development Expense |  | -1.6 | -2.5 | -2.5 | 0
Other Income |  | -0.1 | -0.1 | -0.1 | 0
Total IBIT - NEPCO |  | 24.8 | 6.1 | -3.4 | -9.5
Note on E23: Erin Copeland: Riogen 1.1, Eletrobolt .8, .7 indust. Div, coyote .2, overview 2.7
Note on J23: Erin Copeland: coyote .8, nelson .6, coyote springs .8, thermo .4, 3q payne creek -1.2

## up-down (hidden)
Current
|  |  | 1CE | Forecast | Upside | Downside
Total IBIT per Plan |  | $ | 11 | 11 | 11 | 11
Profit Adjustments
| Puerto Rico - $0 to ($23.0) |  | -23 | -28 | -9 | -28
| EPC 63/64 - $5.7 to $.3 |  | -5.4 | -5.8 | 0 | -9.4
| Arcos - delayed |  | -4 |  | -4 | -4
| Turkey - $33.7 to $31.5 |  | -2.145 | -2.145 | -2.1 | -7.7
* | India LNG - $26.0 to $6.3 |  | -7.5 | -5.3 | -7.5 | -5.3
| Poland - $5.6 to $3.4 |  | -1 | -2.2 | -1 | -1.7
| Cuiaba - $16.6 to $15.6 |  | -0.5 | -3.3 | -0.5 | -3.3
| Other Misc. projects |  | -0.3 |  | -0.3 | -0.3
| Project Reserves in Plan |  | 20 |  | 20 | 20
|  |  | -23.845 | -43.445 | -4.4 | -39.7
Accro Selldown |  |  | 0 | -21.5 | 0 | -21.5
India Selldown |  |  | 0 | 0 | 18 | 0
Remaining Assets Solddown |  |  | 2.8 | 0 | 12.3 | 0
Credit Reserve |  |  | -3.8 | -8.5 | -3.8 | -9.2
Additional G&A
| G&A not billed to BU's |  | -14.3 | -7.4 | -5 | -14.3
| Corporate Charges |  | -7.8 |  |  | -7.8
Increased Development Expense |  |  | -3.4 | -3.5 | -3.4 | -3.4
3rd Party Interest Income |  |  | 2.3 |  | 2.3 | 2.3
Lagos Performance Test |  |  | 0 | 0 | 4 | 0
India - 4th Tank |  |  | 0 | 0 | 0 | -16
Stretch |  |  | 7 |  | 7 | 0
Total IBIT per Forecast |  |  | -30.045 | -73.345 | 38 | -98.6
*Total profit decrease is $(7.8) offset by +$.3 of progress