## EE&CC
Schedule 5.10(a)
Principal Contracts
EECC Entities - Claims
Project | Contract type/Price | Claim | Claim Value | Discussion/Status
Puerto Rico | EPC/$446M
Puerto Rico | EECC claims submitted against Owner
Puerto Rico |  | Power Plant: EECC submitted a claim for the effects caused by hurricanes George, Lenny and Jose consisting of (i) a 29 day time extension claim valued at $4.35MM in delay LD relief and (ii) a $5.5MM cost claim for the delay. | $9.85MM | Owner response received 11 May 2000 offering an 18 day time extension and $995,000. Note, this claim offsets Owner's claim for 90 days of delay valued at $12.1MM.
Puerto Rico |  | Power Plant: PREPA power export limitations & Owner failure to provide grid access. | $2.6MM (Est.) | February 2, 2000 EECC submitted 17 day time extension claim for Owner delays. Owner response received 25 May 2000 acknowledging 4 days of delay.
Puerto Rico |  | Power Plant: Gasoline spill | 0.7 | February 3, 2000 EECC submitted 1 day time extension claim for a Force Majeure event. 6/29/00 Owner rejects impact to schedule but is willing to consider actual labor costs for interrupted activities.
Puerto Rico |  | Power Plant: 4160V Cable Bus Duct explosion | $0.6MM | February 3, 2000 EECC submitted 4 day Force Majeure claim for electrical explosion in cable bus duct. Owner rejects claims as having no basis.
Puerto Rico |  | LNG Terminal: Weather delay (Hurricanes). | $0.8MM | April 14, 2000 EECC submitted 7 day time extension claim for the effects caused by hurricanes George, Lenny and Jose.
Puerto Rico |  | LNG Terminal: Owner delay - commissioning combustion turbines on natural gas. | TBD | EECC submitted claim on 06 July requesting a six (6) day extension of time to Phase II Guaranteed Completion Date resulting from Owner directive to complete natural gas commissioning of CT's in sequence instead of in parallel as EECC planned.
Puerto Rico | EECC claims NOT YET submitted against Owner
Puerto Rico |  | EECC has another 37 Change Orders that have not yet been submitted to Owner. | $1.0MM
Puerto Rico |  | Certain portions of EECC insurance claims may be submitted to Owner if denied by the insurance companies. | TBD
Puerto Rico | Owner claims submitted against EECC
Puerto Rico |  | In 3/00 and 5/00 EPA filed a Notice of Violation (NOV) against Owner asserting numerous violations of the Clean Air and Clean Water Acts. | TBD | Owner claims any violation would have resulted from Contractor's alleged failure to satisfy applicable law requirements under the EPC (as opposed to Owner issues), and announced intention to seek indemnity from Contractor. Contractor does not admit responsibility, but is cooperating with Owner in discussions with EPA.
Cuiabá, Brazil | EPC | 480 MW Power Plant and Pipeline
Cuiaba | EECC Claims Submitted to Owner:
Cuiabá |  | HRSG Claim – Additional Site Costs expended to accelerate the schedule to mitigate the delay impact of the HRSG damaged by typhoon encountered while shipping from Korea to Brazil | $1.66 MM | SCC submitted claim to Owner, who denies Typhoon was an excusable event/FM. Discussions underway.
Cuiabá |  | HRSG Claim Rev.1- Additional Costs not submitted in Original Claim Proposal including Barge demurrage $0.100MM. Siemens site staff costs $0.216MM | $0.316MM
Cuiabá |  | Miscellaneous Outstanding Power Plant Change Orders: $13k for Demin. Plant Damages, $300k for Refund of Phase I LDDS to Siemens, and $1.1MM "Downpayment" towards Siemens' EOT Phase III Costs. | $1.413MM | Owner to review and respond.
Cuiabá |  | Pipeline: Brazil Spread 3 Standby/Demob/Remob Equipment/Labor, Misc. Standby –Ridges, Scope Changes-Rock Trench etc, | $4.4MM | SCC submitted $4.4Million claim to Owner May 18 2000.
Cuiabá |  | Pipeline: Brazil and Bolivia Changes in scopes of Work – Standby San Matias Civil Unrest, Landowner Delays, Archaeological Findings | $90k
Cuiaba | EECC Claims NOT YET Submitted to Owner:
Cuiabá |  | Extension of Time ("EOT") claim for Delay in Delivery of Gas. (05 May 2000 ready for gas) | $14.4MM (EST) | SCC has advised Owner that SCC monthly costs will be added to the $14.4 claim by Siemens at the rate of $800k/mo. Commissioning to take place using oil on "best efforts" basis.
Cuiaba |  | SCC claim for time related cost increase caused by Owner delay in gas supply that delayed commissioning. | $6.0MM | SCC to prepare claim for submission mid-August for time related cost increase resulting from Owner delay in providing fuel gas.
Cuiabá |  | Pipeline: Spread 3 Conduto - reroute of pipeline through the ridges and related delays. | $15.0MM | $15.0MM Claim received from subcontractor. EECC anticipates submitting a claim to Owner.
Cuiaba | Owner Claims Submitted to EECC
Cuiabá |  | Claim for Liquidated Damages by Owner because of alleged unavailability of CT issue. | $1.020MM | Owner submitted claim to Siemens. Siemens submitted claim to SCC. SCC has indemnified Siemens and SCC is disputing Owner claim.
Cuiabá |  | Debit Notes for CT #11 Re-Commissioning Fuel. Owner has submitted two Debit Notes to SCC for Fuel used during Re-Commissioning. One is for the amount Siemens agrees to, the other for the amount in dispute between Owner and SCC. | $1.413MM | Owner submitted the Debit Notes to SCC and not directly to Siemens. Undisputed Fuel Usage at R$1,035,017 = $0.575MM. Disputed Fuel Usage at R$187,488 = $0.104MM. Owner seeking total of $0.679MM.
Accro | EPC $357MM | Three Force Majeure delay claims submitted to date for labor unrest/site access blockage (19 days), natural calamity/floods (TBD) and permit delays (2 days). | TBD | Owner verbally agreed in mid May to 12 day FM delay but subsequently rescinded offer and currently disputes entitlement to all FM delays.
Accro |  | Subsequent Force Majeure delays occurred for an additional 20 days delay but not submitted to Owner. | TBD
Accro |  | Site Relocation. | $1.0MM
Dabhol LNG | EPC $550MM | EECC may have a claim against the Owner based on the fitness of the Quarry pending settlement of the same dispute with the subcontractor, Besix. | $57.4MM | EECC is at risk for $15 to $20MM in delay LD from Owner if Besix is successful against EECC.
Gaza | Owner's Engineer | EECC has submitted a claim for extended services. | $1.2MM | EECC committed based upon verbal approval.
Dominican Republic |  | EECC seeks recovery of settlement money from Owner out of insurance proceeds as agreed by Owner. | $2.4MM | Owner received insurance proceeds and Lenders have refused to approve our settlement. This is currently under discussion. EECC has booked this income.