## Austin
ABB Transformers - Austin
As of |  | Contract Price | 562300
2000-12-05 |  | Quantity | 2
|  | Total Price | 1124600
|  | Funding Request | Drawdown | Drawdown
|  | Date | Percent | Amount | Balance
Payments | Option Premium |  |  | 880000 | 880000
Made | Milestone Payment #1 | 2000-09-14 | 10% | 153600 | 1033600
To Date | Milestone Payment #2 |  | 25% | 240010 | 1273610
| Milestone Payment #3 |  | 65% | 737990 | 2011600
| Sale of Transformers | 2000-10-27
|  |  |  | Balance Due as of 12/05/00 | 0

## Coral
ABB Transformers - Coral
As of |  | Contract Price | 786000
2000-12-05 |  | Quantity | 1
|  | Total Price | 786000
|  | Funding Request | Drawdown | Drawdown
|  | Date | Percent | Amount | Balance
Payments | Option Premium |  |  | 181333.3333 | 181333.3333
Made | Milestone Payment #1 | 2000-09-14 | 10% | 88400 | 269733.3333
To Date | Milestone Payment #2 | 2000-11-22 | 25% | 186700 | 456433.3333
| Milestone Payment #3 | 2000-12-13 | 40% | 314400 | 770833.3333
Payments | Milestone Payment #4 | N/A | 15% | 117900 | 888733.3333
Due | Milestone Payment #5 | N/A | 10% | 78600 | 967333.3333
|  |  |  | Balance Due as of 12/05/00 | 510900
Note on E9: rwalker2: GE over-invoiced Enron for the 10% progress payment.
Note on E10: rwalker2: This payment is less than 25% of the total contract price in order to reimburse Enron for being over-billed for the first milestone payment.
Note on E11: rwalker2: Already invoiced.

## ESA
ABB Transformers - ESA
As of |  | Contract Price | 786000
2000-12-05 |  | Quantity | 2
|  | Total Price | 1572000
|  | Funding Request | Drawdown | Drawdown
|  | Date | Percent | Amount | Balance
Payments | Option Premium |  |  | 362666.6667 | 362666.6667
Made To Date | Milestone Payment #1 | 2000-09-14 | 10% | 176800 | 539466.6667
Payments Due | Cancellation Fees | N/A |  | 323200 | 862666.6667
|  |  |  | Balance Due as of 12/05/00 | 323200
Note on E9: rwalker2: Enron was over-invoiced for the 10% progress payment.

## PSCO
ABB Transformers - PSCO
As of |  | Contract Price | 786000
2000-12-05 |  | Quantity | 3
|  | Total Price | 2358000
|  | Funding Request | Drawdown | Drawdown
|  | Date | Percent | Amount | Balance
Payments | Option Premium |  |  | 544000 | 544000
Made To Date | Milestone Payment #1 | 2000-09-14 | 10% | 265200 | 809200
| Milestone Payment #2 | N/A | 25% | 560100 | 1369300
Payments | Milestone Payment #3 | N/A | 40% | 943200 | 2312500
Due | Milestone Payment #4 | N/A | 15% | 353700 | 2666200
| Milestone Payment #5 | N/A | 10% | 235800 | 2902000
|  |  |  | Balance Due as of 12/05/00 | 2092800
Note on E9: rwalker2: Enron was over-invoiced for the 10% progress payment.
Note on E10: rwalker2: 25% progress payment adjusted by the over-payment in September, 2000 -- already invoiced.

## LV Cogen
ABB Transformers - LV Cogen
As of |  | Contract Price | 782000
2000-12-05 |  | Quantity | 2
|  | Total Price | 1564000
|  | Funding Request | Drawdown | Drawdown
|  | Date | Percent | Amount | Balance
Payments | Option Premium |  |  | 346000 | 346000
Made To Date | Milestone Payment #1 | 2000-09-14 | 10% | 176000 | 522000
| Milestone Payment #2 | N/A | 25% | 371400 | 893400
Payments | Milestone Payment #3 | N/A | 40% | 625600 | 1519000
Due | Milestone Payment #4 | N/A | 15% | 234600 | 1753600
| Milestone Payment #5 | N/A | 10% | 156400 | 1910000
|  |  |  | Balance Due as of 12/05/00 | 1388000
Note on E9: rwalker2: Enron was over-invoiced for the 10% progress payment.
Note on E10: rwalker2: 25% progress payment adjusted by the over-payment in September, 2000.

## Summary By Project
| Number of | Contract | Option | Progress Payments |  |  |  |  | Total | Total Amount
Project | Transformers | Price | Premium | Payment #1 | Payment #2 | Payment #3 | Payment #4 | Payment #5 | Amount Paid | Amount Due
Austin | 2 | 1124600 | 561400 | 153600 | 240010 | 737990 | SOLD |  | 1131600 | 0
Coral | 1 | 786000 | 181333.3333 | 88400 | 186700 | 314400 | 117900 | 78600 | 275100 | 510900
ESA | 2 | 1572000 | 362666.6667 | 176800 | 323200 | Cancellation Fees |  |  | 176800 | 323200
PSCO | 3 | 2358000 | 544000 | 265200 | 560100 | 943200 | 353700 | 235800 | 265200 | 2092800
LV Cogen | 2 | 1564000 | 346000 | 176000 | 371400 | 625600 | 234600 | 156400 | 176000 | 1388000
TOTALS | 10 | 7404600 | 1995400 | [5 empty] | 2024700 | 4314900
Progress Payment has been made
Progress Payment due
Note on F6: rwalker2: Already invoiced -- scheduled to be paid by 12/13/00.
Note on G4: rwalker2: Already invoiced -- scheduled to be paid by 12/13/00.

## Summary By Unit
ABB Transformers
|  | Guaranteed Unit | Contract | Option | Progress |  | Progress | Total
Unit/ABB Item # | Project Designation | Delivery Date | Purchase Price | Premium Paid | Pymts. Made | Retainage | Pymts. Due | Purchase Price
lNL 9521-1 | Austin | 2000-10-20 | 562300 | 440000 | 569300 | 56230 | SOLD | 1009300
LNL 9521-2 | Austin | 2000-10-20 | 562300 | 440000 | 562300 | 56230 | SOLD | 1002300
LNL 9517-1 | PSCO | 2000-12-01 | 786000 | 39300 | 88400 | 78600 | 697600 | 825300
LNL 9517-2 | PSCO | 2000-11-17 | 786000 | 39300 | 88400 | 78600 | 697600 | 825300
LNL 9517-3 | PSCO | 2000-12-01 | 786000 | 39300 | 88400 | 78600 | 697600 | 825300
LNL 9517-4 | Coral | 2000-11-17 | 786000 | 39300 | 275100 | 78600 | 510900 | 825300
LNL 9517-5 | ESA | 2000-12-15 | 786000 | 440000 | 88400 | N/A | 161600 | 690000
LNL 9517-6 | ESA | 2000-12-15 | 786000 | 440000 | 88400 | N/A | 161600 | 690000
LNL 9518-1 | LV Cogen | 2001-08-01 | 782000 | 39100 | 88000 | 78200 | 694000 | 821100
LNL 9518-2 | LV Cogen | 2001-08-01 | 782000 | 39100 | 88000 | 78200 | 694000 | 821100
Total |  |  | 7404600 | 1995400 | 2024700 | 583260 | 4314900 | 8335000
Progress Payments Due |  | 4314900
Less Discount |  | -30000
Progress Payments Due |  | 4284900
Less Retainage |  | -583260 | Excludes ESA transformers
Total Amount Due |  | 3701640
1 The two units designated for ESA have been cancelled -- the progress payments due for these units are cancellation charges.
2 Retainage amount per section 6.1.3 of the Agreement.
Note on F6: rwalker2: Extra $7,000 charge for Spare bushings.

## XNPV Payments
ABB Tranformer Payments Due
2000-12-08 | 2000-12-13 | 2001-01-13 | 2001-02-13 | 2001-03-13 | 2001-04-13 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01
323200 | 874500 | 943200 | 0 | 117900 | 0 | 353700 | 371400 | 625600 | 0 | 0 | 234600
ESA Cancellation
| Coral Pymt #3 |  |  | Coral Pymt #4
| PSCO Pymt #2 | PSCO Pymt. #3 |  |  |  | PSCO Pymt #4
[7 empty] | LV Pymt #2 | LV Pymt #3 |  |  | LV Pymt #4
Discount Rate | 8%
Nominal Value | 3844100
XNPV | 3768969.3931
Discount | 75130.6069
1 Payment #5 for each set of transformers represents the 10% retainment amount to be paid the earlier of 36 months after Acceptance or 24 months after COD and is not shown in these calculations.
Note on A4: rwalker2: ESA Cancellation Charges.
Note on B4: rwalker2: Already invoiced -- Coral Payment #3 and PSCO Payment #2.
Note on C4: rwalker2: PSCO #3.
Note on E4: rwalker2: Coral #4.
Note on G4: rwalker2: PSCO #4.
Note on H4: rwalker2: LV Cogen #2.
Note on I4: rwalker2: LV Cogen #3.
Note on L4: rwalker2: LV Cogen #4.

## ABB Amounts
ABB Transformers
Progress Payments Due | 4307900
Less Discount | -30000
Progress Payments Due | 4277900
Less Retainage | -470800
Total Amount Due | 3807100
1 Retainage amount per section 6.1.3 of the Agreement.