## Sheet1
AEP-HPL TRANSITION ISSUES
System |  | Activity |  | Point | Point | Due
|  |  |  | Person | Person | Date
Global Counterparty |  |  |  | HPL | AEP
| 1 | Web page development |  | Tommy Yanowski |  | 2001-04-30
| 2 | Proceudres for Counterpary updates |  | Bill Hare |  | 2001-04-15
| 3 | Addment to Service Agreemetn |  | Tommy Yanowski |  | 2001-04-15
| 4 | Filtering Information in comments/notes |  | Bill Hare |  | 2001-04-15
| 5 | DUN's number for AEP-HPL |  | Sandy Branband/Mike Eiben |  | 2001-04-15
| 6 | Banking info from AEP |  |  | Steve Jackson/Jan with AEP | 2001-05-15
| 7 | Cross reference table for counterpary |  | Tommy Yanowski | Steve Jackson/Dan Simpson | 2001-04-30
| 8 | Enron credit information on counterparty |  | Bill Hare/Tommy Yanowski
Global Facilities
| 1 | Global facitliies maintence group split |  | Mike Eiben/Sundar |  | 2001-04-30
| 2 | Resolve new pipeline question |  | Mike Eiben/Matt Pena |  | 2001-04-15
Global Contracts
| 1 | Script to copy contract data |  | Cheryl Dudley |  | 2001-03-20
| 2 | Contracts being transferred |  | George Weissman |  | 2001-04-15
| 3 | Contract to be terminated before close |  | George Weissman |  | 2001-04-15
| 4 | Contracts to be terminated after close |  | George Weissman |  | 2001-04-15
Global Rates
| 1 | Cross reference table for rates |  | Tommy Yanowski | Don Simpson | 2001-04-30
Deal Entry
| 1 | Bridge from AEP trade blotter to Sitara |  | Tommy Yanowski | Don Simpson | 2001-04-30
| 2 | Bridge Error report |  |  | Don Simpson
| 3 | New Desks created in Sitara |  | Russ Severson |  | 2001-04-30
| 4 | Base Gas bridge and updates |  | Tommy Yanowski
| 5 | Separate copy of ERMS and CPR |  | Tommy Yanowski
Confirmations
| 1 | Will AEP use our confirmation system |  | Bob Hall | Steve Jackson | 2001-04-15
Scheduling/Allocations/Settlements
| 1 | Brideg Error-Feedback monitor training |  | Kathryn Bussell |  | 2001-05-01
| 2 | Bridge to Sitara not to trade blotter follow-up |  | Bob Hall | Steve Jackson | 2001-04-15
| 3 | Cash accounts admendment |  | Sandy Braband/Bob Hall |  | 2001-04-15
| 4 | Hard coding of Name for settlements |  | Chris Schommer |  | 2001-05-01
| 5 | HUB & EDI contracts after four months |  | Tommy Yanowski | Don Simpson | 2001-04-15
| 6 | Notice to counterparties on banking change |  | Bob Hall/Leslie Reeves | Steve Jackson | 2001-06-01
Transportation Rates
| 1 | HPL transport rates through Sitara only |  | Kim Olinger/Matt Pena |  | 2001-05-01
| 2 | Security for transport rates |  | Kim Olinger/Matt Pena |  | 2001-05-01
3
MISC
| 1 | Operational Data Web Site Adment to service agtm |  | Mike Eiben/Tommy Yanowski |  | 2001-05-01
| 2 | Tarrif filing system Adment to service agtm |  | Mike Eiben/Tommy Yanowski |  | 2001-05-01
3