## Sheet1
Appendix C
Enron
Payment - Termination Schedule
|  |  |  | Payment |  | Termination
Payment |  |  |  | Monthly % | Cumulative % | Cumulative %
Month |  | Event |  | of Contract | of Contract | of Contract
Feb-23-01 |  | Signed Agreement |  | 5% | 5% | 10%
Feb-28-01 |  | Progress Payment |  | 5% | 10% | 10%
2001-03-01 |  | Progress Payment |  | 3% | 13% | 12%
2001-04-01 |  | Progress Payment |  | 3% | 16% | 14%
2001-05-01 |  | Progress Payment |  | 3% | 19% | 16%
2001-06-01 |  | Progress Payment |  | 3% | 22% | 18%
2001-07-01 |  | Progress Payment |  | 3% | 25% | 20%
2001-08-01 |  | Progress Payment |  | 3% | 28% | 22%
2001-09-01 |  | Progress Payment |  | 3% | 31% | 24%
2001-10-01 |  | Progress Payment |  | 3% | 34% | 26%
2001-11-01 |  | Progress Payment |  | 3% | 37% | 28%
2001-12-01 |  | Progress Payment |  | 3% | 40% | 30%
2002-01-01 |  | Progress Payment |  | 3% | 43% | 32%
2002-02-01 |  | Progress Payment |  | 4% | 47% | 34%
2002-03-01 |  | Progress Payment |  | 4% | 51% | 36%
2002-04-01 |  | Progress Payment |  | 4% | 55% | 38%
2002-05-01 |  | Progress Payment |  | 4% | 59% | 40%
2002-06-01 |  | Progress Payment |  | 4% | 63% | 40%
2002-07-01 |  | Progress Payment |  | 4% | 67% | 40%
2002-08-01 |  | Progress Payment |  | 4% | 71% | 40%
2002-09-01 |  | Progress Payment |  | 4% | 75% | 40%
2002-10-01 |  | Ship GT Unit 1 |  | 20% | 95% | 40%
2002-11-01 |  | 30 Days Post GT 1 Ship Date |  | 5% | 100% | 100%
IPS 94074
2/5/01
Notes: | Payment
The initial payment is due within 3 business days of signed agreement.
The second payment is due on or before February 28, 2001.
Progress Payments are due on the 20th of the indicated month and will be billed 30 days in advance.
Payments tied to the availability to ship of equipment are due Net 30 days after receipt of invoice
and certification that equipment is available to ship.
Final payment is due Net 30 days from receipt of invoice.
Termination
The Buyer may terminate this agreement at any time upon written notification and payment of
termination charges in accordance with the schedule set forth above.
Title to terminated gas turbine-generator equipment remains with the Seller.
Termination exposure after title transfer is 100%.