## Sheet1
AS400 6-week Rolling Workplan |  | w/e 20th Oct | w/e 27th Oct | w/e 3rd Nov | w/e 10th Nov | w/e 17th Nov | w/e 24th Nov
|  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6
| David Thompson | Softs | VACATION | EOL Bridge | SAP | SAP | SAP
EOL Bridge
| Colin Walker | VACATION | CRR Report | SAP | VACATION | SAP | SAP
| David Fulton | Softs | VACATION | EOL Bridge | SAP | SAP | SAP
EOL Bridge
| Nigel Latham | GCP/SAP | SAP | VACATION | SAP | SAP | SAP
| Michael Sweeney | SAP | SAP | SAP | SAP | SAP | SAP
|  | Merchanting Support | Merchanting Support | Merchanting Support | Merchanting Support | Merchanting Support | Merchanting Support
| Andrew Davis | Softs | Softs | Softs | Softs | Softs | Softs
General support tasks excluded from detail above
Key:
Work In Progress |  | week 1: Status
SAP |  | week 1: Michael Heap co-ordinating SAP and AS400 development effort
Softs |  | week 1: Paul Sentance defining requirements and co-ordinating implementation
EOL Bridge |  | week 1: UAT and Implemenetation scheduled November
Commission new AS400 box |  | week 1: Currently behind schedule
Planned Work |  | week 1: Sponsors
Settlements/Cash Management Process Improvements |  | week 1: Esther Demetz compiling list
Daily P&L Analytical Tools |  | week 1: Andy Cornfield compiling list of requirements
New York Invoicing Functionality |  | week 1: Louis Colarusso has passed specification to Mike Sweeney
Inventory Management Tools |  | week 1: Alex Holland performing feasibility study of Global Markets newly implemented system and identifying tactical improvements
Deal Capture Process Improvements/Automation |  | week 1: Kevin Rhodes & Tim P2 preparing planning document