## Sheet1
Taxes
Point | Description | Accountability | Due Date | Status
Pis / Cofins | 3.65% charged over gross revenues of all power transactions |  |  | Done
ICMS | Unless if sold to a final customer, ICMS is not applied on power transactions |  |  | Done
CPMF | 0.30% is charged when money is taken out of the bank account |  |  | Done
Lobby for Pis / Cofins | Lobbying effort for exemption on power transactions. | Lynn Aven
Tax Reform | Keep track of what is happening | Lynn Aven
"White Paper" | Should we write a "White Paper" to present our ideas for the Tax Reform? | Lynn Aven
Legal
Point | Description | Accountability | Due Date | Status
Choice of Law | Brazilian Law | Andrea Bertone |  | Done
Choice of Jurisdiction | Brazilian Jurisdiction | Andrea Bertone |  | Done
Contracts Enforceability | Electronic Trading contracts are enforceable under Brazilian Law | Andrea Bertone |  | Done
Risk Matrix |  | Andrea Bertone | 2000-07-28
Trade Confirmation | Decide what is the confirmation process we are going to adopt | Andrea Bertone | 2000-07-31
Confirmation Document | Draft sample of confirmation document | Andrea Bertone | 2000-07-31
Define procedures | Design necessary documents to be exchanged for each transaction | Andrea Bertone | 2000-07-31
Draft GTC |  | Andrea Bertone | 2000-08-03
Draft PA and ETA |  | Andrea Bertone | 2000-08-09
Standard Contracts |  | Andrea Bertone | 2000-09-18
Regulatory
Point | Description | Accountability | Due Date | Status
Comercializadora Title | Get 2 other MAE licenses based out of Rio de Janerio & Salvador Offices | Luiz Maurer | 2000-08-31
Connectivity | Follow up with ASMAE to assure connectivity to Sinercom (automatization) | Steve Nagy / Luiz Maurer | 2000-08-31
Market Rules | Keep track of their approval or changes | Luiz Maurer
Inform Regulators about EOL | Do we need to inform MAE, or any regulatory body, about EOL? | Luiz Maurer / Team
Financial Institution | Analysis on what are the consequences of becoming a Financial Institution | Eduardo Camara /Ricardo L./D'arcy C.
(financial transactions, tax exemptions)
Define Procedures | Do we have to follow any special procedure or rule besides resolution 249/98? | Luiz Maurer
Information and Technology
Point | Description | Accountability | Due Date | Status
EnronOnline.com.br | Register name and Intellectual propriety | Steve Nagy / Andrea Bertone |  | Done
Enron.com.br | Register name and Intellectual propriety | Steve Nagy / Andrea Bertone |  | Done
Links and Redundancy cost | Feasibility US$30,000 / month | Steve Nagy |  | Done
| Installation upon 90 days notice (expected September 30) | Steve Nagy | 2000-12-31
Softwares & Applications | Identify necessity and install | Steve Nagy | 2000-08-15
Briefing of the team / detailed plan, justification, implementation, training
Deal Capture | Automatic feeding from EOL to Brazilian Book | Steve Nagy / Adriano Pereira | 2000-08-31
Enpower | Enpower Implementation Plan | Steve Nagy
Help Desk | 0800 number and link to US Help Desk | Julie Ramos | 2000-09-30
Brazilian test session | Define date. | EOL Houston / Team | 2000-10-15
Help Desk | Make sure that US will have Portuguese speakers on the phone | Remi Collonges | 2000-10-15
New Hardware | Install trading infrastructure (monitors) | Julie Ramos | 2000-10-31
Links efficiency | Test links efficiency during simulation | Julie Ramos | 2000-11-15
Password Controls | Processes and procedures | EOL Houston | 2000-11-15
| Control Group | EOL Houston | 2000-11-15
| Legal signoff | EOL Houston / Andrea Bertone | 2000-11-15
Credit
Point | Description | Accountability | Due Date | Status
Provide analysis | Provide analysis on the 18 companies information was sent (Sigma Factor) | Paul Radous | 2000-07-28
| Determine credit limit and or collateral request |  | 2000-08-15
Additional Companies | Select and inform credit about new companies to analyze credit profile | Remi C / Ricardo L | 2000-08-15
Define procedure | Define communication flow from trades to credit | Ricardo L / Paul R. | 2000-08-09
CBLC | Understand and update credit after CBLC settlement implementation | Ricardo L / Paul R. | 2000-09-02
Monitoring | Confirm monitoring process | Paul R./ EOL Houton | 2000-09-18
| Design steps needed to request new / extension of credit lines |  | 2000-09-30
Credit Exposure Report |  | Paul Radous
Back Office
Point | Description | Accountability | Due Date | Status
Define Procedures | Processes (from deal ticket to invoice approval and payment) | Odair Ribeiro / Scott Mills /Remi | 2000-08-15
Billing system | Define billing procedure | Odair Ribeiro / Scott Mills / Steve N | 2000-08-15
Define necessary tools | Prioritize implementation of Enron applications | Odair Ribeiro / Scott Mills / Steve N | 2000-08-15
Preliminary Steps | Registration of potential customers in SAP | Odair Ribeiro / Scott Mills / Paul Radous
Other steps to be defined
Staffing | Determine if additional hires are necessary | Odair Ribeiro /Remi | 2000-10-01
Marketing
Point | Description | Accountability | Due Date | Status
Marketing material | Translation of brochures | Adriana Domingues / Ricardo L / Mario P Cardoso |  | Done
Market Analysis Online | Sector fundamental analysis to be posted Online | Ricardo Lisboa | 2000-08-31
Marketing Plan | Draft Marketing Plan | Adriana Domingues / Berti | 2000-09-30
Customer presentations | Prepare Customer Presentations | Adriana Domingues / Berti | 2000-10-31
Client training | Establish client training program EOL workshops | Berti / Ricardo Lisboa | 2000-10-31
| Simulation and in-house training | Berti / Ricardo Lisboa | 2000-11-15
Contracts | Have client to sign PA | Berti | 2000-12-15
| Negotiate if necessary | Andrea Bertone / Berti | 2000-12-15
Roll Out |  |  | 2000-12-15
Commercial
Point | Description | Accountability | Due Date | Status
Products | Define products | Remi C. / Ricardo L. |  | Done
| Products review | Mario P Cardoso |  | Done
Customers | Define potential customer list | Remi C. / Ricardo L. |  | Done
Simulation | Define objectives, targets and tests to be done | Leonardo Pacheco / Ricardo Lisboa |  | 2000-10-01
Market Preference | Check market preference for our products | Luis Berti |  | 2000-10-15
Limits and Procedures | Determine operating procedures, limits and responsibilities | Remi C. |  | 2000-11-01